**NOTE FOR PAD**

Assembly Constituency Baroda Starred Question No. 14/15/48.

**To complete the Development works**

The CM Announcement Code No 25284 was announced on 20.12.2019 vide which an amount of Rs. 5.00 crores is to be released on the recommendation of MLA of constituency concerned for development works in that Assembly constituency. The estimates are received through the District Administration for approval of the development works, which were sanctioned after taking approval from the Hon'ble Chief Minister and released to the executing agency. As far as the Baroda Assembly Constituency is concerned, District Development and Panchayat Officer Sonipat sent the estimates to the Managing Director, HRDF vide letter No. 802, dated 06.03.2020 and Hon'ble Chief Minister approved the estimates amounting to Rs. 2,79,91,000/- on 12.02.2021. Accordingly, this amount was released to the Gram Panchyats concerned vide letter No.796-BAP-II-(9)-2021/2011 dated 17-05-2021 and No.796-BAP-II-(9)-2021/2009 dated 17-05-2021 for 26 works during the financial year 2021-2022 under Haryana Gramin Vikas Yojana (CM Announcement Code 25284).

 These 26 works were not started by Gram Panchayats concerned. Meanwhile as per instructions issued by Govt. vide letter no.DFA-4-2022/26278-578 dated 31.03.2022, the amount of Rs.2,39,58,000/- for 21 works (Rs.44,45,000/- on 02.05.2022, Rs.6,15,000/- on 12.05.2022 & Rs.1,88,98,000/- on 13.05.2022) was deposited in the account of Executive Engineer, Panchayati Raj Sonipat by Block Development & Panchayat Officer concerned and the amount of Rs.40,33,000/- for 5 works is lying with Gram Panchayats concerned.

 Out of 26 works, 8 works are complete, 9 are in progress and 9 are yet to be started. Out of the 9 works not started, 1 work is not feasible due to non-availability of site. Funds of Jagsi Sehrawat Panchayat have been refunded accordingly and for 8 remaining works, tenders are under process on Haryana Engineering Works Portal. The details of these 26 works are as under :-

**Completed – 8**

| **Amount : Rs. In lakh** |
| --- |
| **Sr. No.** | **CONSTITUENCY** | **BLOCK** | **VILLAGE** | **NATURE OF WORK** | **SANCTIONED AMOUNT**  | **Executing Agency** | **STATUS OF WORK** | **Remarks** |
| 1 | BARODA | Mundlana | BARODA MOR | Const of IPB Streets from Gohana Maham Road to Metal Road Kohla | 17.27 | XEN (PR) | Complete | Fund released to GP, transferred to XEN PR on 13.05.2022 |
| 2 | BARODA | Mundlana | BARODA THUTHAN | Const of Parjapat Chaupal | 10.42 | XEN (PR) | Complete | Fund released to GP, transferred to XEN PR on 13.05.2022 |
| 3 | BARODA | Mundlana | BUSANA | Completion of Sheraya pana Gen Chaupal | 10.18 | XEN (PR) | Complete | Fund released to GP, transferred to XEN PR on 13.05.2022 |
| 4 | BARODA | Mundlana | CHIRANA | Completion of Ved pana Chaupal | 8.30 | XEN (PR) | Complete | Fund released to GP, transferred to XEN PR on 13.05.2022 |
| 5 | BARODA | Mundlana | ISSAPUR KHERI | Re-Construction of Dhumra wali Chaupal | 8.00 | XEN (PR) | Complete | Fund released to GP, transferred to XEN PR on 13.05.2022 |
| 6 | BARODA | KATHURA | KATHURA | Const Balmiki Chaupal | 1.52 | GP | Complete | Fund released to GP |
| 7 | BARODA | KATHURA | MADINA | Const of IPB Strets from H/o Rammehar S/o Bhagwan to PWD Road | 8.39 | XEN (PR) | Complete | Fund released to GP, transferred to XEN PR on dated 02.05.2022 |
| 8 | BARODA | Mundlana | SHAMRI SISAN | Const of Baddi Chaupal Gen | 19.00 | XEN (PR) | Complete | Fund released to GP, transferred to XEN PR on 13.05.2022 |
|  | **Total (Completed)** | **83.08** |  |  |  |

**In Progress – 9**

| **Amount : Rs. In lakh** |
| --- |
| **SR. NO.** | **CONSTITUENCY** | **BLOCK** | **VILLAGE** | **NATURE OF WORK** | **SANCTIONED AMOUNT** | **STATUS OF WORK/ Executing Agency** | **Remarks** | **Likely date of Completion** | **Reson for Delay**  |
| 1 | BARODA | GOHANA | ANWALI | Const of IPB Streets from Nai Chaupal to School Wali Gali | 19.90 | In progress/GP | Fund with GP. work completed 50%  | 30.06.2023 | Due to pacca encroachment at some portion of street near school.  |
| 2 | BARODA | Mundlana | BARODA MOR | Const of R/wall of Ansar Pond | 4.92 | In progress/XEN (PR) | Fund transferred by GP to XEN PR on 13.05.2022  | 31.03.2023 | Fifth time tender floated (tender floated vide tender ID Ref. No. 6602 dt 13.07.2022, 7546 dt 03.08.2022, 7948 dt 12.08.2022, 8559 dt 24.08.2022). On fifth time i.e. tender ID Ref. no. 9749 dt 07.09.2022 tender received. (2) Delay due to high under-ground water table at site. |
| 3 | BARODA | Mundlana | GANGANA TANDIA PANA | Const of Community Center | 16.00 | In progress/XEN (PR) | Fund transferred by GP to XEN PR on 13.05.2022.  | 31.08.2023 | Fifth time tender floated (tender floated vide tender ID Ref. No. 6229 dt 30.06.2022, 7162 dt 28.07.2022, 7948 dt 12.08.2022, 8559 dt 24.08.2022). On fifth time i.e. tender ID Ref. no. 9745 dt 07.09.2022 tender received. Work order issued material at site. (2) Revise Admin. Approval is under process (because as per New HSR, the estimated amount increased from Rs. 16.00 lakh to Rs.23.70 lakh). |
| 4 | BARODA | KATHURA | KATHURA | Const of Mirashi Chaupal | 10.00 | In progress/XEN (PR) | Fund transferred by GP to XEN PR on 02.05.2022. | 30.06.2023 | Fifth time tender floated (tender floated vide tender ID Ref. No. 6229 dt 30.06.2022, 7162 dt 28.07.2022, 7948 dt 12.08.2022, 8559 dt 24.08.2022). On fifth time i.e. tender ID Ref. no. 9745 dt 07.09.2022 tender received. Work order issued. Material laid at site, but work stopped due to clear site not provided by GP. |
| 5 | BARODA | KATHURA | MADINA | Const of Community Center | 17.72 | In progress/XEN (PR) | Fund transferred by GP to XEN PR on dated 02.05.2022 | 31.05.2023 | Fifth time tender floated (tender floated vide tender ID Ref. No. 6229 dt 30.06.2022, 7162 dt 28.07.2022, 7948 dt 12.08.2022, 8559 dt 24.08.2022). On fifth time i.e. tender ID Ref. no. 9745 dt 07.09.2022 tender received. Work order issued. Material laid at site, but work stopped due to clear site not provided by GP. |
| 6 | BARODA | Mundlana | MUNDLANA | Const. of IPB Street from PWD road Siwanka to Sirshad | 18.35 | In progress/XEN (PR) | Fund transferred by GP to XEN PR on 13.05.2022 | 31.03.2023 | Work completed only payment is pending. |
| 7 | BARODA | Mundlana | MUNDLANA | Const. of R/wall of Pond | 9.94 | In progress/XEN (PR) | Fund transferred by GP to XEN PR on 13.05.2022 | 31.03.2023 | Fourth time tender floated (tender floated vide tender ID Ref. No. 6602 dt 13.07.2022, 7546 dt 03.08.2022, 7948 dt 12.08.2022). On fourth time i.e. tender ID Ref. no. 8559 dt 24.08.2022 tender received. Work order issued. Material at site. (2) Delay due to high under-ground water table at site. |
| 8 | BARODA | Mundlana | NURAN KHERA | Re-Construction of Balmiki Chaupal | 15.28 | In progress/XEN (PR) | Fund transferred by GP to XEN PR on 13.05.2022. Work in progress. Under CM Ann. Funds to be Refunded. | 31.03.2023 | Work in progress. Under CM Ann. Funds to be Refunded. |
| 9 | BARODA | Mundlana | SIWANKA | Const of Badi Chaupal | 9.43 | In progress/XEN (PR) | Fund transferred by GP to XEN PR on 13.05.2022. | 31.03.2023 | Work in progress. Under CM Ann. Funds to be Refunded. |
|   | **Total (In Progress)** | **121.54** |   |   |   |   |

**Not Started – 9**

| **Amount : Rs. In lakh** |
| --- |
| **SR. NO.** | **CONSTITUENCY** | **BLOCK** | **VILLAGE** | **NATURE OF WORK** | **SANCTIONED AMOUNT** | **STATUS OF WORK/ EXECUTING AGENCY** | **Remarks** | **Likely date of Completion** |
| 1 | BARODA | Mundlana | BUSANA | Re-Const. of Singhmar General Chaupal | 7.15 | Not start/XEN (PR) |  Fund transferred by GP to XEN PR on 13.05.2022. Seven time tender floated vide Ref. no.6602 dated 13.07.22, 7546 dated 03.08.22, 7948 dated 12.08.22, 8559 dated 24.08.22, 9745 dated 07.09.22, 10434 dated 19.09.22 and 10869 dated 27.09.22, but no bid received. Tender under process on HEW Portal. | 31.08.2023 |
| 2 | BARODA | Mundlana | BUTANA KUNDU | Completion of Gen New Chaupal | 2.97 | Not start/GP | Fund with GP, but tender called by XEN PR Seven time vide Ref. no.6602 dated 13.07.22, 7546 dated 03.08.22, 7948 dated 12.08.22, 8559 dated 24.08.22, 9745 dated 07.09.22, 10434 dated 19.09.22 and 10869 dated 27.09.22, but no bid received. Now, tender under process on HEW Portal at SDO Level | 31.08.2023 |
| 3 | BARODA | KATHURA | CHHAPRA | Const of IPB Streets from Main Road to H/o Dharmender | 6.15 | Not start/XEN (PR) | Fund transferred by GP to XEN PR on 12.05.2022 Tender floated on HEW Portal. open date 27.02.2023 | 31.08.2023 |
| 4 | BARODA | Mundlana | ISSAPUR KHERI | Const of Gen Community Center | 16.92 | Not start/XEN (PR) | Fund transferred by GP to XEN PR on 13.05.2022. Revised Admin Approval is under process (because as per new HSR, the estimated amount increased from Rs.16.92 lakh to Rs. 42.60 lakh). | 31.08.2023 |
| 5 | BARODA | Mundlana | JAGSI SEHRAWAT | Const. of Gen Chaupal Dholi wali | 9.90 | Not Feasible/XEN (PR) | Fund transferred by GP to XEN PR on 13.05.2022. (Not Feasible). fund refunded to GP on 17.02.2023 | -- |
| 6 | BARODA | GOHANA | JASRANA | Const of SC Chaupal | 9.82 | Not start/GP | Fund with GP. Tender under process on HEW Portal at SDO Level. | 31.08.2023 |
| 7 | BARODA | KATHURA | KATHURA | Const. of Kalyana wali Choupal | 8.34 | Not start/XEN (PR) | Fund transferred by GP to XEN PR on 02.05.2022. Seven time tender floated vide Ref. no.6229 dated 30.06.2022, 7162 dated 28.07.22, 7948 dated 12.08.22, 8559 dated 24.08.22, 9745 dated 07.09.22, 10484 dated 19.09.22 and 10869 dated 27.09.22, but no bid received. Now on HEW Portal. Tender floated open date 22.02.2023. | 31.08.2023 |
| 8 | BARODA | Mundlana | RANA KHERI | Completion of BC Chaupal | 7.92 | Not start/XEN (PR) | Fund transferred by GP to XEN PR on 13.05.2022. Revised Admin Approval is under process (because as per new HSR, the estimated amount increased from Rs. 7.92 lakh to Rs.14.53 lakh). | 31.08.2023 |
| 9 | BARODA | Mundlana | SHAMRI LOCHAB BARREN | Completion of Gen Chaupal | 6.12 | Not start/GP | Fund with GP. Tender under process on HEW Portal at SDO Level | 31.08.2023 |
|   |   **Total (Not Started)** | **75.29** |   |   |   |

**Constituency wise report of District Sonipat regarding CM Announcement Code 25284**

|  |
| --- |
| **Amount : Rs. In Lakh** |
| **Sr. No.**  | **Name of Constituency** | **Sanctioned Amount** | **No. of Sanctioned Works** | **Work Completed** | **Work in progress** | **Not started.** |
| 1 | Gohana | 309.80 | 34 | 7 | 13 | 14 |
| 2 | Ganaur | 501.51 | 44 | 25 | 5 | 14 |
| 3 | Rai | 409.49 | 40 | 8 | 21 | 11 |
| 4 | Kharkhoda | 445.53 | 35 | 11 | 18 | 6 |
| 5 | Baroda | 279.91 | 26 | 8 | 9 | 9 |
| 6 | Sonipat | 0 | 0 | 0 | 0 | 0 |
| **Total** | **1946.24** | **179** | **59** | **66** | **54** |

**Constituency wise report of State Haryana regarding CM Announcement code 25284**

| **Amount : In Lakh** |
| --- |
| **Sr NO** | **DISTRICT** | **CONSTITUENCY** | **Sanctioned Amount**  | **Sanctioned Works** | **Completed** | **InProgress** | **Not Started** |
| 1 | AMBALA | Ambala Cantt. | 0.00 | 0 | 0 | 0 | 0 |
| 2 | AMBALA | AMBALA CITY | 507.68 | 107 | 88 | 9 | 10 |
| 3 | AMBALA | MULLANA | 342.02 | 63 | 41 | 5 | 17 |
| 4 | AMBALA | NARAINGARH | 449.38 | 84 | 47 | 10 | 27 |
| 5 | BHIWANI | BAWANI KHERA | 503.14 | 32 | 32 | 0 | 0 |
| 6 | BHIWANI | BHIWANI | 380.97 | 29 | 4 | 8 | 17 |
| 7 | BHIWANI | LOHARU | 500.79 | 86 | 82 | 2 | 2 |
| 8 | BHIWANI | TOSHAM | 506.23 | 91 | 53 | 17 | 21 |
| 9 | CHARKI DADRI | CHARKI DADRI | 464.57 | 29 | 0 | 0 | 29 |
| 10 | CHARKI DADRI | BADHRA | 494.03 | 45 | 26 | 7 | 12 |
| 11 | FARIDABAD | Badkhal | 0.00 | 0 | 0 | 0 | 0 |
| 12 | FARIDABAD | Ballabhgarh | 0.00 | 0 | 0 | 0 | 0 |
| 13 | FARIDABAD | Faridabad | 0.00 | 0 | 0 | 0 | 0 |
| 14 | FARIDABAD | FARIDABAD NIT | 55.62 | 4 | 0 | 1 | 3 |
| 15 | FARIDABAD | PRITHALA | 463.39 | 69 | 56 | 0 | 13 |
| 16 | FARIDABAD | TIGAON | 423.80 | 75 | 68 | 0 | 7 |
| 17 | FATEHABAD | FATEHABAD | 505.35 | 81 | 80 | 1 | 0 |
| 18 | FATEHABAD | RATIA | 463.52 | 58 | 50 | 0 | 8 |
| 19 | FATEHABAD | TOHANA | 437.51 | 63 | 58 | 3 | 2 |
| 20 | GURUGRAM | GURUGRAM | 0.00 | 0 | 0 | 0 | 0 |
| 21 | GURUGRAM | BHADSHAHPUR | 493.29 | 35 | 30 | 0 | 5 |
| 22 | GURUGRAM | PATAUDI | 466.77 | 58 | 38 | 3 | 17 |
| 23 | GURUGRAM | SOHNA | 411.10 | 30 | 28 | 0 | 2 |
| 24 | HISAR | ADAMPUR | 46.34 | 9 | 8 | 0 | 1 |
| 25 | HISAR | BARWALA | 489.86 | 32 | 32 | 0 | 0 |
| 26 | HISAR | HANSI | 416.48 | 50 | 43 | 3 | 4 |
| 27 | HISAR | Hisar | 0.00 | 0 | 0 | 0 | 0 |
| 28 | HISAR | NALWA | 529.83 | 54 | 46 | 6 | 2 |
| 29 | HISAR | NARNAUND | 326.44 | 29 | 16 | 7 | 6 |
| 30 | HISAR | UKLANA | 494.05 | 45 | 45 | 0 | 0 |
| 31 | JHAJJAR | BADLI | 633.75 | 88 | 4 | 7 | 77 |
| 32 | JHAJJAR | BERI | 494.30 | 41 | 0 | 0 | 41 |
| 33 | JHAJJAR | BAHADURGARH | 436.16 | 2 | 0 | 0 | 2 |
| 34 | JHAJJAR | JHAJJAR | 287.94 | 24 | 2 | 6 | 16 |
| 35 | JIND | JIND | 94.53 | 12 | 12 | 0 | 0 |
| 36 | JIND | JULANA | 534.24 | 82 | 64 | 5 | 13 |
| 37 | JIND | Narwana | 403.70 | 66 | 62 | 0 | 4 |
| 38 | JIND | SAFIDON | 463.70 | 65 | 50 | 5 | 10 |
| 39 | JIND | Uchana Kalan | 508.18 | 34 | 32 | 1 | 1 |
| 40 | KAITHAL | GUHLA | 357.03 | 13 | 9 | 4 | 0 |
| 41 | KAITHAL | KAITHAL | 485.72 | 63 | 59 | 1 | 3 |
| 42 | KAITHAL | KALAYAT | 523.12 | 64 | 52 | 5 | 7 |
| 43 | KAITHAL | PUNDRI | 537.19 | 66 | 55 | 8 | 3 |
| 44 | Karnal | Assandh | 354.66 | 41 | 12 | 16 | 13 |
| 45 | Karnal | Ghraunda | 471.26 | 30 | 8 | 14 | 8 |
| 46 | Karnal | Indri | 433.65 | 48 | 42 | 4 | 2 |
| 47 | Karnal | Karnal | 0.00 | 0 | 0 | 0 | 0 |
| 48 | Karnal | Nilokheri | 557.15 | 47 | 38 | 8 | 1 |
| 49 | Kurukshetra | Ladwa | 497.17 | 100 | 72 | 4 | 24 |
| 50 | Kurukshetra | Pehowa | 300.11 | 61 | 61 | 0 | 0 |
| 51 | Kurukshetra | Shahbad | 499.87 | 72 | 69 | 1 | 2 |
| 52 | Kurukshetra | Thanesar | 10.38 | 3 | 2 | 0 | 1 |
| 53 | Mahendergarh | Ateli | 509.65 | 55 | 51 | 0 | 4 |
| 54 | Mahendargarh | Mahendergarh | 301.32 | 49 | 8 | 13 | 28 |
| 55 | Mahendergarh | Nangal Choudhary | 500.15 | 64 | 60 | 0 | 4 |
| 56 | Mahendergarh | Narnaul | 424.02 | 47 | 20 | 10 | 17 |
| 57 | Nuh | Firozpur Zirka | 509.70 | 53 | 1 | 0 | 52 |
| 58 | Nuh | Nuh | 452.51 | 52 | 13 | 0 | 39 |
| 59 | Nuh | Punhana | 484.10 | 39 | 0 | 0 | 39 |
| 60 | Palwal | Hathin | 503.71 | 38 | 28 | 6 | 4 |
| 61 | Palwal | Hodal | 414.01 | 36 | 19 | 7 | 10 |
| 62 | Palwal | Palwal | 506.12 | 50 | 48 | 0 | 2 |
| 63 | Panchkula | Panchkula | 0.00 | 0 | 0 | 0 | 0 |
| 64 | Panchkula | Kalka | 410.47 | 84 | 0 | 2 | 82 |
| 65 | Panipat | Israna | 240.93 | 35 | 15 | 3 | 17 |
| 66 | Panipat | Panipat City | 0.00 | 0 | 0 | 0 | 0 |
| 67 | Panipat | Panipat Rural | 465.69 | 28 | 11 | 4 | 13 |
| 68 | Panipat | Samalkha | 474.75 | 40 | 27 | 3 | 10 |
| 69 | Rewari | Rewari | 92.17 | 9 | 0 | 0 | 9 |
| 70 | Rewari | Bawal | 507.77 | 49 | 48 | 0 | 1 |
| 71 | Rewari | Kosli | 502.53 | 56 | 42 | 4 | 10 |
| 72 | Rohtak | Garhi Sampla Kiloi | 65.81 | 2 | 0 | 0 | 2 |
| 73 | Rohtak | Kalanaur | 246.48 | 10 | 4 | 1 | 5 |
| 74 | Rohtak | Meham | 485.86 | 52 | 52 | 0 | 0 |
| 75 | Rohtak | Rohtak | 0.00 | 0 | 0 | 0 | 0 |
| 76 | Sirsa | Dabwali | 167.49 | 21 | 17 | 0 | 4 |
| 77 | Sirsa | Ellenabad | 123.51 | 15 | 12 | 1 | 2 |
| 78 | Sirsa | Kalanwali | 376.97 | 33 | 31 | 1 | 1 |
| 79 | Sirsa | Rania | 470.49 | 29 | 26 | 1 | 2 |
| 80 | Sirsa | Sirsa | 437.47 | 33 | 33 | 0 | 0 |
| 81 | Sonepat | Baroda | 279.91 | 26 | 8 | 9 | 9 |
| 82 | Sonepat | Ganaur | 501.52 | 44 | 25 | 5 | 14 |
| 83 | Sonepat | Gohana | 309.80 | 34 | 7 | 13 | 14 |
| 84 | Sonepat | Kharkhoda | 445.53 | 35 | 11 | 18 | 6 |
| 85 | Sonepat | Rai | 409.49 | 40 | 8 | 21 | 11 |
| 86 | Sonepat | Sonepat | 0.00 | 0 | 0 | 0 | 0 |
| 87 | Yamuna Nagar | Jagadhari | 264.63 | 68 | 48 | 9 | 11 |
| 88 | Yamuna Nagar | Radaur | 473.21 | 77 | 31 | 12 | 34 |
| 89 | Yamuna Nagar | Sadhaura | 381.23 | 89 | 64 | 4 | 21 |
| 90 | Yamuna Nagar | Yamuna Nagar | 221.29 | 57 | 15 | 20 | 22 |
| **Total** | **32016.21** | **3729** | **2459** | **338** | **932** |
| **Total Amount in Crores** | **320.16** |  |   |   |   |

**uksV QkWj iSM**

**fo/kkulHkk fuokZpu {ks= cM+kSnk] rkjkafdr ç'u la[;k 14@15@48**

**fodkl dk;ksaZ dks iwjk djuk**

fnukad 20-12-2019 dks eq[;ea=h ?kks"k.kk dksM la[;k 25284 dh ?kks"k.kk dh xbZ] ftlds rgr 5-00 djksM+ :i;s dh jkf'k lacaf/kr fuokZpu {ks= ds fo/kk;d dh vuq'kalk ij muds fo/kkulHkk {ks= esa xzkeh.k fodkl dk;ksaZ ds fy, tkjh dh tkuh gSA fodkl dk;ksaZ ds vuqeksnu ds fy, ftyk ç'kklu ds ek/;e ls çkdyu çkIr gksrs gSa] ftUgsa ekuuh; eq[;ea=h ls Loh—fr çkIr dj dk;Zdkjh laLFkk dks tkjh fd;k tkrk gSA tgka rd ​​cM+kSnk fo/kkulHkk {ks= dk laca/k gS] ftyk fodkl ,oa iapk;r vf/kdkjh] lksuhir ds i= Øekad 802 fnukad 06-03-2020 ds rgr çca/k funs'kd] ,pvkjMh,Q dks çkDdyu Hksts x;s Fks tksfd ekuuh; eq[;ea=h egksn; }kjk fnukad 12-02-2021 dks 2]79]91]000@& :i;s dh Lohd`fr iznku dh xbZ FkhA rnuqlkj i=kad 796&ch,ih&f}rh;&¼9½&2021@2011 fnukad 17&05&2021 ,oa Øekad 796&ch,ih& f}rh;&¼9½&2021 ds ek/;e ls lacaf/kr xzke iapk;rksa dks ;g jkf'k gfj;k.kk xzkeh.k fodkl ;kstuk ¼lh,e ?kks"k.kk dksM 25284½ ds rgr foÙkh; o"kZ 2021&2022 ds nkSjku 26 dk;ksaZ ds fy, tkjh dh xbZ FkhA

 bu 26 dk;ksaZ dks lacaf/kr xzke iapk;rksa }kjk çkjaHk ugha fd;k x;k FkkA bl nkSjku ljdkj }kjk tkjh funsZ'kkuqlkj i= Øekad Mh,Q,&4&2022@26278&578 fnukad 31-03-2022 }kjk 21 dk;ksaZ ds fy, 2]39]58]000@& :i;s dh jkf'k ¼fnukad 02-05-2022 dks 44]45]000@& fnukad 12-05-2022 dks 6]15]000@& :0 fnukad 13-05-2022 dks 1]88]98]000@& :0½ dks lEcfU/kr [k.M fodkl ,oa iapk;r vf/kdkjh }kjk dk;Zdkjh vfHk;ark] iapk;rh jkt lksuhir ds [kkrs esa tek djk;k x;k ,oa 5 dk;ksaZ gsrq 40]33]000@& dh jkf”k lEcfU/kr xzke iapk;rksa ds ikl gSA

 bu 26 dk;ksaZ esa ls 8 dk;Z iw.kZ gks pqds gSa] 9 çxfr ij gSa rFkk 9 vHkh “kq: ugha gq, gSaA bu dk;ksaZ esa ls tkxlh lgjkor xzke iapk;r dk 1 dk;Z lkbV dh vuqiyC/krk ds dkj.k laHko ugha gS] mldk Q.M okfil dj fn;k x;k gS vkSj 8 dk;ksaZ ds VS.Mj gfj;k.kk bathfu;fjax odZ~l iksVZy ij çfØ;k/khu gSaA bu 26 dk;ksaZ dk fooj.k bl çdkj gS %&

**iw.kZ gks pqds dk;Z – 8**

| **jkf”k % yk[k : esa** |
| --- |
| **Øe la[;k** | **fuokZpu {ks=** | **CykWd**  | **Xk¡ko** | **dk;Z dk izdkj** | **Lohd`r jkf”k** | **,atslh ftl }kjk dk;Z djok;k tk jgk gS** | **dk;Z dh fLFkfr** | **fVIi.kh** |
| 1 | cM+kSnk | eqaMykuk | cjksMk eksj | xksgkuk ege jksM ls esVy jksM dksgyk rd vkbZihch xfy dk fuekZ.k | 17.27 | dk;Zdkjh vfHk;aUrk] iapk;rh jkt | iw.kZ  | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 13-05-2022 dks jkf”k LFkkukUrfjr dh xbZ |
| 2 | cM+kSnk | eqaMykuk | cjksMk FkqFku | iztkir pkSiky dk fuekZ.k | 10.42 | dk;Zdkjh vfHk;aUrk] iapk;rh jkt | iw.kZ | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 13-05-2022 dks jkf”k LFkkukUrfjr dh xbZ |
| 3 | cM+kSnk | eqaMykuk | cqlkuk | “ksz;k ikuk tujy pkSiky dks iw.kZ djuk | 10.18 | dk;Zdkjh vfHk;aUrk] iapk;rh jkt | iw.kZ | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 13-05-2022 dks jkf”k LFkkukUrfjr dh xbZ |
| 4 | cM+kSnk | eqaMykuk | fpjkuk | osn ikuk pkSiky dks iw.kZ djuk | 8.30 | dk;Zdkjh vfHk;aUrk] iapk;rh jkt | iw.kZ | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 13-05-2022 dks jkf”k LFkkukUrfjr dh xbZ |
| 5 | cM+kSnk | eqaMykuk | bLlkiqj [ksMh | nqejkokyh pkSiky dk iwu% fuekZ.k | 8.00 | dk;Zdkjh vfHk;aUrk] iapk;rh jkt | iw.kZ | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 13-05-2022 dks jkf”k LFkkukUrfjr dh xbZ |
| 6 | cM+kSnk | dFkqjk | dFkqjk | Okkyfedh pkSiky dk fuekZ.k | 1.52 | xzke iapk;r | iw.kZ | xzke iapk;r dks jkf”k tkjh dh xbZ  |
| 7 | cM+kSnk | dFkqjk | enhuk | jkeesgj iq0 Hkxoku ds ?kj ls ih0MCyq0Mh0 jksM rd vkbZihch xyh dk fuekZ.k | 8.39 | dk;Zdkjh vfHk;aUrk] iapk;rh jkt | iw.kZ | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 02-05-2022 dks jkf”k LFkkukUrfjr dh xbZ |
| 8 | cM+kSnk | eqaMykuk | “kkejh “kh”ku | cMh pkSiky tujy dk fuekZ.k | 19.00 | dk;Zdkjh vfHk;aUrk] iapk;rh jkt | iw.kZ | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 13-05-2022 dks jkf”k LFkkukUrfjr dh xbZ |
|  | **dqy ¼iw.kZ dk;Z½** | **83-08** |  |  |  |

**izxfr/khu dk;Z & 9**

| **jkf”k % yk[k : esa** |
| --- |
| **Øe la[;k** | **fuokZpu {ks=** | **CykWd**  | **Xk¡ko** | **dk;Z dk izdkj** | **Lohd`r jkf”k** | **dk;Z dh fLFkfr@ ,atslh ftl }kjk dk;Z djok;k tk jgk gS** | **fVIi.kh** | **dk;Z iw.kZ gksus dh laHkkfor frFkh** | **nsjh dk dkj.k** |
| 1 | cM+kSnk | xksgkuk | vuokyh | ukbZ pkSiky ls Ldwy okyh xyh rd vkbZihch xyh dk fuekZ.k | 19-90 | izxfr/khu@ xzke iapk;r | xzke iapk;r dks jkf”k tkjh dh xbZA dk;Z 50 izfr”kr iw.kZ  | 30-06-2023 | Ldwy ds utnhd lkbZV ij iDdk dCtk gksus ds dkj.k |
| 2 | cM+kSnk | eqaMykuk | cjksMk eksj | vulkj rkykc dh izfr/kkj.k fnokj dk fuekZ.k | 4-92 | izxfr/khu@ dk;Zdkjh vfHk;aUrk] iapk;rh jkt | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 13-05-2022 dks jkf”k LFkkukUrfjr dh xbZ | 31-03-2023 | fufonk ik¡p ckj vkeaf=r dh xbZ ¼fufonk fuEu fufonk ua0 ds }kjk vkeaf=r dh xbZ 6602 fnukad 13-07-22] 7546 fnukad 03-08-22] 7948 fnukad 12-08-22] 8559 fnukad 24-08-22½A fufonk iakpoh ckj fufonk ua0 9749 fnukad 07-09-22 ls izkIr gqbZA ¼2½ lkbZV ij mPp Hkqfe tyLrj gksus ds dkj.k foyEc gqvkA |
| 3 | cM+kSnk | eqaMykuk | xaxkuk VafM;k ikuk  | Lkkeqnkf;d dsnz dk fuekZ.k | 16-00 | izxfr/khu@ dk;Zdkjh vfHk;aUrk] iapk;rh jkt | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 13-05-2022 dks jkf”k LFkkukUrfjr dh xbZ | 31-08-2023 | fufonk ik¡p ckj vkeaf=r dh xbZ ¼fufonk fuEu fufonk ua0 ds }kjk vkeaf=r dh xbZ 6229 fnukad 30-06-22] 7162 fnukad 28-07-22] 7948 fnukad 12-08-22] 8559 fnukad 24-08-22½A fufonk iakpoh ckj fufonk ua0 9745 fnukad 07-09-22 }kjk izkIr gqbZA dk;Z dk odZ vkWMj tkjh fd;k x;kA lkbZV ij fuekZ.k lkexzh fufgr gSA ¼2½ la”kksf/kr iz”kkldh; Lohd`fr izxfr/khu gS ¼D;ksafd u, ,p0,l0vkj0 vuqlkj] vuqekfur jkf”k 16 yk[k : ls c<dj 23-70 yk[k : gks xbZ gSA  |
| 4 | cM+kSnk | dFkqjk | dFkqjk | ehjk'kh pkSiky dk fuekZ.k | 10-00 | izxfr/khu@ dk;Zdkjh vfHk;aUrk] iapk;rh jkt | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 02-05-2022 dks jkf”k LFkkukUrfjr dh xbZ | 30-06-2023 | fufonk ik¡p ckj vkeaf=r dh xbZ ¼fufonk fuEu fufonk ua0 ds }kjk vkeaf=r dh xbZ 6229 fnukad 30-06-22] 7162 fnukad 28-07-22] 7948 fnukad 12-08-22] 8559 fnukad 24-08-22½A fufonk iakpoh ckj fufonk ua0 9745 fnukad 07-09-22 }kjk izkIr gqbZA dk;Z dk odZ vkWMj tkjh fd;k x;kA lkbZV ij fuekZ.k lkexzh fufgr gSA iajUrq xzke iapk;r }kjk lkbZV [kkyh ugha djokbZ x;hA |
| 5 | cM+kSnk | dFkqjk | enhuk | Lkkeqnkf;d dsnz dk fuekZ.k | 17-72 | izxfr/khu@ dk;Zdkjh vfHk;aUrk] iapk;rh jkt | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 02-05-2022 dks jkf”k LFkkukUrfjr dh xbZ | 31-05-2023 | fufonk ik¡p ckj vkeaf=r dh xbZ ¼fufonk fuEu fufonk ua0 ds }kjk vkeaf=r dh xbZ 6229 fnukad 30-06-22] 7162 fnukad 28-07-22] 7948 fnukad 12-08-22] 8559 fnukad 24-08-22½A fufonk iakpoh ckj fufonk ua0 9745 fnukad 07-09-22 }kjk izkIr gqbZA dk;Z dk odZ vkWMj tkjh fd;k x;kA lkbZV ij fuekZ.k lkexzh fufgr gSA iajUrq xzke iapk;r }kjk lkbZV [kkyh ugha djokbZ x;hA |
| 6 | cM+kSnk | eqaMykuk | eqaMykuk | ih0MCyq0Mh0 jksM lhoaUdk ls fljln rd rd vkbZihch xyh dk fuekZ.k | 18-35 | izxfr/khu@ dk;Zdkjh vfHk;aUrk] iapk;rh jkt | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 13-05-2022 dks jkf”k LFkkukUrfjr dh xbZ | 31-03-2023 | dk;Z iw.kZ gks pqdk gS] vnk;xh “ks’k gSA |
| 7 | cM+kSnk | eqaMykuk | eqaMykuk | rkykc dh izfr/kkj.k fnokj dk fuekZ.k | 9-94 | izxfr/khu@ dk;Zdkjh vfHk;aUrk] iapk;rh jkt | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 13-05-2022 dks jkf”k LFkakukrfjr dh xbZ | 31-03-2023 | fufonk pkj ckj vkeaf=r dh xbZ ¼fufonk fuEu fufonk ua0 ds }kjk vkeaf=r dh xbZ 6229 fnukad 30-06-22] 7162 fnukad 28-07-22] 7948 fnukad 12-08-22½A fufonk iakpoh ckj fufonk ua0 8559 fnukad 24-08-22 }kjk izkIr gqbZA A lkbZV ij mPp Hkwfe tyLrj gksus ds dkj.k nsjh gqbZA |
| 8 | cM+kSnk | eqaMykuk | uqju [ksMk | Okkyfedh pkSiky dk iwu% fuekZ.k | 15-28 | izxfr/khu@ dk;Zdkjh vfHk;aUrk] iapk;rh jkt | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 13-05-2022 dks jkf”k LFkakukrfjr dh xbZA dk;Z izxfr/khu gS eq[;ea=h ?kks’k.kk ds rgr tkjh jkf”k okfil dh tkuh gSA | 31-03-2023 | dk;Z izxfr/khu gS eq[;ea=h ?kks’k.kk ds rgr tkjh jkf”k okfil dh tkuh gSA |
| 9 | cM+kSnk | eqaMykuk | floUdk | cMh pkSiky dk fuekZ.k | 9-43 | izxfr/khu@ dk;Zdkjh vfHk;aUrk] iapk;rh jkt | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 13-05-2022 dks jkf”k LFkakukrfjr dh xbZ | 31-03-2023 | dk;Z izxfr/khu gS eq[;ea=h ?kks’k.kk ds rgr tkjh jkf”k okfil dh tkuh gSA |
|  | **dqy ¼izxfr/khu dk;Z½** | **121-54** |  |  |  |  |

**“kq: ugha gq, dk;Z & 9**

| **jkf”k % yk[k : esa** |
| --- |
| **Øe la[;k** | **fuokZpu {ks=** | **CykWd**  | **Xk¡ko** | **dk;Z dk izdkj** | **Lohd`r jkf”k** | **dk;Z dh fLFkfr@ ,atslh ftl }kjk dk;Z djok;k tk jgk gS** | **fVIi.kh** | **dk;Z iw.kZ gksus dh laHkkfor frFkh** |
| 1 | cM+kSnk | eqaMykuk | cqlkuk | flagekj lkekU; pkSiky dk iqu% fuekZ.k | 7-15 | “kq: ugha gqvk@ dk;Zdkjh vfHk;aUrk] iapk;rh jkt | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 13-05-2022 dks jkf”k LFkakukrfjr dh xbZA fufonk lkr ckj vkeaf=r dh xbZ ¼fufonk fuEu fufonk ua0 6602 fnukad 13-07-22] 7546 fnukad 03-08-22] 7948 fnukad 12-08-22] 8559 fnukad 24-08-22] 9745 fnukad 07-09-22] 10434 fnukad 19-09-22 vkSj 10869 fnukad 27-09-22½ ijUrq dksbZ fufonk izkIr ugha gqbZ gSA vc ,p0bZ0MCyw0 iksVZy ij VS.Mj yxk;k tk jgk gSA | 31-08-2023 |
| 2 | cM+kSnk | eqaMykuk | cqVkuk dq.Mq | ubZ lkekU; pkSiky dks iw.kZ djuk | 2-97 | “kq: ugha gqvk@ xzke iapk;r | xzke iapk;r dks jkf”k tkjh dh xbZ] ijaUrq fufonk,s dk;Zdkjh vfHk;Urk] iapk;rh jkt }kjk lkr ckj vkeaf=r dh xbZ ¼fufonk fuEu fufonk ua0 6602 fnukad 13-07-22] 7546 fnukad 03-08-22] 7948 fnukad 12-08-22] 8559 fnukad 24-08-22] 9745 fnukad 07-09-22] 10434 fnukad 19-09-22 vkSj 10869 fnukad 27-09-22½ ijUrq dksbZ fufonk izkIr ugha gqbZ gSA mie.My vf/kdkjh }kjk ,p0bZ0MCyq0 iksVZy ij fufonk;sa vkeaf=r dh tk jgh gSaA  | 31-08-2023 |
| 3 | cM+kSnk | eqaMykuk | dFkqjk | esu jksM ls /kjeSUnz ds ?kj rd vkbZihch xyh dk fuekZ.k | 6-15 | “kq: ugha gqvk@ dk;Zdkjh vfHk;aUrk] iapk;rh jkt | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 12-05-2022 dks jkf”k LFkakukrfjr dh xbZA ,p0bZ0MCyq0 iksVZy fufonk;sa vkeaf=r dh xbZ tksfd 27-02-2023 dks [kqysaxhA | 31-08-2023 |
| 4 | cM+kSnk | eqaMykuk | bLlkiqj [ksMh | lkekU; lkeqnkf;d dsUnz dk fuekZ.k | 16-92 | “kq: ugha gqvk@ dk;Zdkjh vfHk;aUrk] iapk;rh jkt | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 13-05-22 dks LFkkukUrfjr dh xbZA la”kksf/kr iz”kkldh; Lohd`fr izxfr/khu gS ¼D;ksafd u, ,p0,l0vkj0 vuqlkj] vuqekfur jkf”k 16-92 yk[k : ls c<dj 42-60 yk[k : gks xbZ gSA | 31-08-2023 |
| 5 | cM+kSnk | eqaMykuk | tkxlh lsjkor | lkekU; pkSiky Mksyhokyh dk fuekZ.k | 9-90 | dk;Z laHko ugha @ dk;Zdkjh vfHk;aUrk] iapk;rh jkt | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 13-05-2022 dks jkf”k LFkakukrfjr dh xbZ ¼dk;Z laHko ugha½A 17-02-2023 dks jkf”k xzke iapk;r dks okfil dj nh xbZ A |  |
| 6 | cM+kSnk | Xksgkuk | tljkuk | ,l0lh0 pkSiky dk fuekZ.k | 9-82 | “kq: ugha gqvk@ xzke iapk;r | xzke iapk;r dks jkf”k tkjh dh xbZA mie.My vf/kdkjh }kjk ,p0bZ0MCyq0 iksVZy ij fufonk;sa vkeaf=r gSaA | 31-08-2023 |
| 7 | cM+kSnk | dFkqjk | dFkqjk | dy;k.kk okyh pkSiky dk fuekZ.k | 8-34 | “kq: ugha gqvk@ dk;Zdkjh vfHk;aUrk] iapk;rh jkt | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 02-05-2022 dks jkf”k LFkakukrfjr dh xbZA ¼fufonk fuEu fufonk ua0 6602 fnukad 13-07-22] 7546 fnukad 03-08-22] 7948 fnukad 12-08-22] 8559 fnukad 24-08-22] 9745 fnukad 07-09-22] 10434 fnukad 19-09-22 vkSj 10869 fnukad 27-09-22½ ijUrq dksbZ fufonk izkIr ugha gqbZ gSA vc ,p0bZ0MCyw0 iksVZy ij VS.Mj yxk;k x;k gS] tks fd 22-02-2023 dks [kqysxkA | 31-08-2023 |
| 8 | cM+kSnk | eqaMykuk | jkuk [ksMh | lkekU; pkSiky dk dk;Z iqjk djuk | 7-92 | “kq: ugha gqvk@ dk;Zdkjh vfHk;aUrk] iapk;rh jkt | xzke iapk;r dks jkf”k tkjh dh xbZ o xzke iapk;r }kjk dk;Zdkjh vfHk;Urk] iapk;rh jkt dks 13-05-22 dks jkf”k LFkkukUrfjr dh xbZA la”kksf/kr iz”kkldh; Lohd`fr izxfr/khu gS ¼D;ksafd u, ,p0,l0vkj0 vuqlkj] vuqekfur jkf”k 07-92 yk[k : ls c<dj 14-53 yk[k : gks xbZ gSA | 31-08-2023 |
| 9 | cM+kSnk | eqaMykuk | “kEeh ykspc cSjs.k | Tujy pkSiky dk dk;Z iqjk djuk | 6-12 | “kq: ugha gqvk@ xzke iapk;r | xzke iapk;r dks jkf”k tkjh dh xbZA mie.My vf/kdkjh }kjk ,p0bZ0MCyq0 iksVZy ij fufonk;sa vkeaf=r gSaA | 31-08-2023 |
|  | **dqy ¼”kq: ugha gq, dk;Z½** | **75.29** |  |  |  |

**fo/kkulHkk fuokZpu {ks= vuqlkj eq[; ea=h ?kks’k.kk dksM 25284 ckjs ftyk lksuhir dh fjiksVZ**

|  |
| --- |
| **jkf”k % : yk[kksa esa** |
| **Øe la[;k** | **fuokZpu {ks=** | **Lohd`fr jkf”k** | **Lohd`r dk;Z** | **iq.kZ dk;Z** | **izxfr/khu dk;Z** | **“kq: ugha gq, dk;Z** |
| 1 | Xkksgkuk | 309.80 | 34 | 7 | 13 | 14 |
| 2 | xUuksj | 501.51 | 44 | 25 | 5 | 14 |
| 3 | jkbZ | 409.49 | 40 | 8 | 21 | 11 |
| 4 | [kj[kksnk  | 445.53 | 35 | 11 | 18 | 6 |
| 5 | cM+kSnk | 279.91 | 26 | 8 | 9 | 9 |
| 6 | Lkksuhir | 0 | 0 | 0 | 0 | 0 |
| **dqy** | **1946.24** | **179** | **59** | **66** | **54** |

**fo/kkulHkk fuokZpu {ks= vuqlkj eq[; ea=h ?kks’k.kk dksM 25284 ckjs gfj;k.kk jkT; dh fjiksVZ**

| **jkf'k % yk[k esa** |
| --- |
| **Ø0la0** | **ftyk** | **fuokZpu{ks=** | **Lohd`r jkf'k** | **Lohd`r dk;Z** | **iw.kZ dk;Z** | **izxfr/khu dk;Z** | **'kq: ugha gq, dk;Z** |
| 1 | vEckyk | vEckyk dSaV | 0.00 | 0 | 0 | 0 | 0 |
| 2 | vEckyk | vEckyk flVh | 507.68 | 107 | 88 | 9 | 10 |
| 3 | vEckyk | eqykuk | 342.02 | 63 | 41 | 5 | 17 |
| 4 | vEckyk | ukjk;.kx<+ | 449.38 | 84 | 47 | 10 | 27 |
| 5 | fHkokuh | cokuh [ksM+k | 503.14 | 32 | 32 | 0 | 0 |
| 6 | fHkokuh | fHkokuh | 380.97 | 29 | 4 | 8 | 17 |
| 7 | fHkokuh | yksgk: | 500.79 | 86 | 82 | 2 | 2 |
| 8 | fHkokuh | rks'kke | 506.23 | 91 | 53 | 17 | 21 |
| 9 | pj[kh nknjh | pj[kh nknjh | 464.57 | 29 | 0 | 0 | 29 |
| 10 | pj[kh nknjh | ck<M+k | 494.03 | 45 | 26 | 7 | 12 |
| 11 | Qjhnkckn | cM[ky | 0.00 | 0 | 0 | 0 | 0 |
| 12 | Qjhnkckn | cYyHkx<+ | 0.00 | 0 | 0 | 0 | 0 |
| 13 | Qjhnkckn | Qjhnkckn | 0.00 | 0 | 0 | 0 | 0 |
| 14 | Qjhnkckn | Qjhnkckn ,uvkbZVh | 55.62 | 4 | 0 | 1 | 3 |
| 15 | Qjhnkckn | i`Fkyk | 463.39 | 69 | 56 | 0 | 13 |
| 16 | Qjhnkckn | frxkao | 423.80 | 75 | 68 | 0 | 7 |
| 17 | Qrsgkckn | Qrsgkckn | 505.35 | 81 | 80 | 1 | 0 |
| 18 | Qrsgkckn | jfr;k | 463.52 | 58 | 50 | 0 | 8 |
| 19 | Qrsgkckn | Vksgkuk | 437.51 | 63 | 58 | 3 | 2 |
| 20 | xq:xzke | xq:xzke | 0.00 | 0 | 0 | 0 | 0 |
| 21 | xq:xzke | ckn'kkgiqj | 493.29 | 35 | 30 | 0 | 5 |
| 22 | xq:xzke | iVkSnh | 466.77 | 58 | 38 | 3 | 17 |
| 23 | xq:xzke | lksguk | 411.10 | 30 | 28 | 0 | 2 |
| 24 | fglkj | vkneiqj | 46.34 | 9 | 8 | 0 | 1 |
| 25 | fglkj | cjokyk | 489.86 | 32 | 32 | 0 | 0 |
| 26 | fglkj | gkalh | 416.48 | 50 | 43 | 3 | 4 |
| 27 | fglkj | fglkj | 0.00 | 0 | 0 | 0 | 0 |
| 28 | fglkj | uyok | 529.83 | 54 | 46 | 6 | 2 |
| 29 | fglkj | ukjukSan | 326.44 | 29 | 16 | 7 | 6 |
| 30 | fglkj | mdykuk | 494.05 | 45 | 45 | 0 | 0 |
| 31 | >Ttj | cknyh | 633.75 | 88 | 4 | 7 | 77 |
| 32 | >Ttj | csjh | 494.30 | 41 | 0 | 0 | 41 |
| 33 | >Ttj | cgknqjx<+ | 436.16 | 2 | 0 | 0 | 2 |
| 34 | >Ttj | >Ttj | 287.94 | 24 | 2 | 6 | 16 |
| 35 | thUn | thUn | 94.53 | 12 | 12 | 0 | 0 |
| 36 | thUn | tqykuk | 534.24 | 82 | 64 | 5 | 13 |
| 37 | thUn | ujokuk | 403.70 | 66 | 62 | 0 | 4 |
| 38 | thUn | lQhnkas | 463.70 | 65 | 50 | 5 | 10 |
| 39 | thUn | mpkuk dyka | 508.18 | 34 | 32 | 1 | 1 |
| 40 | dSFky | xqgyk | 357.03 | 13 | 9 | 4 | 0 |
| 41 | dSFky | dSFky | 485.72 | 63 | 59 | 1 | 3 |
| 42 | dSFky | dyk;r | 523.12 | 64 | 52 | 5 | 7 |
| 43 | dSFky | iq.Mjh | 537.19 | 66 | 55 | 8 | 3 |
| 44 | djuky | vla/k | 354.66 | 41 | 12 | 16 | 13 |
| 45 | djuky | ?kjkSaMk | 471.26 | 30 | 8 | 14 | 8 |
| 46 | djuky | bUnzh | 433.65 | 48 | 42 | 4 | 2 |
| 47 | djuky | djuky | 0.00 | 0 | 0 | 0 | 0 |
| 48 | djuky | uhyks[ksM+h | 557.15 | 47 | 38 | 8 | 1 |
| 49 | dq:{ks= | ykMok | 497.17 | 100 | 72 | 4 | 24 |
| 50 | dq:{ks= | isgok | 300.11 | 61 | 61 | 0 | 0 |
| 51 | dq:{ks= | 'kkgckn | 499.87 | 72 | 69 | 1 | 2 |
| 52 | dq:{ks= | Fkkuslj | 10.38 | 3 | 2 | 0 | 1 |
| 53 | egsUnzx<+ | vVsyh | 509.65 | 55 | 51 | 0 | 4 |
| 54 | egsUnzx<+ | egsUnzx<+ | 301.32 | 49 | 8 | 13 | 28 |
| 55 | egsUnzx<+ | ukaxy pkS/kjh | 500.15 | 64 | 60 | 0 | 4 |
| 56 | egsUnzx<+ | ukjukSy | 424.02 | 47 | 20 | 10 | 17 |
| 57 | uwag | fQjkstiqj f>jdk | 509.70 | 53 | 1 | 0 | 52 |
| 58 | uwag | uwag | 452.51 | 52 | 13 | 0 | 39 |
| 59 | uwag | iqUgkuk | 484.10 | 39 | 0 | 0 | 39 |
| 60 | iyoy | gFkhu | 503.71 | 38 | 28 | 6 | 4 |
| 61 | iyoy | gksMy | 414.01 | 36 | 19 | 7 | 10 |
| 62 | iyoy | iyoy | 506.12 | 50 | 48 | 0 | 2 |
| 63 | iapdwyk | iapdwyk | 0.00 | 0 | 0 | 0 | 0 |
| 64 | iapdwyk | dkydk | 410.47 | 84 | 0 | 2 | 82 |
| 65 | ikuhir | bljkuk | 240.93 | 35 | 15 | 3 | 17 |
| 66 | ikuhir | ikuhir flVh | 0.00 | 0 | 0 | 0 | 0 |
| 67 | ikuhir | ikuhir :jy | 465.69 | 28 | 11 | 4 | 13 |
| 68 | ikuhir | leky[kk | 474.75 | 40 | 27 | 3 | 10 |
| 69 | jsokM+h | jsokM+h | 92.17 | 9 | 0 | 0 | 9 |
| 70 | jsokM+h | ckoy | 507.77 | 49 | 48 | 0 | 1 |
| 71 | jsokM+h | dkslyh | 502.53 | 56 | 42 | 4 | 10 |
| 72 | jksgrd | xM+h lkaiyk fdyksbZ | 65.81 | 2 | 0 | 0 | 2 |
| 73 | jksgrd | dykukSj | 246.48 | 10 | 4 | 1 | 5 |
| 74 | jksgrd | ege | 485.86 | 52 | 52 | 0 | 0 |
| 75 | jksgrd | jksgrd | 0.00 | 0 | 0 | 0 | 0 |
| 76 | fljlk | Mcokyh | 167.49 | 21 | 17 | 0 | 4 |
| 77 | fljlk | ,yukckn | 123.51 | 15 | 12 | 1 | 2 |
| 78 | fljlk | dkykaokyh | 376.97 | 33 | 31 | 1 | 1 |
| 79 | fljlk | jkfu;ka | 470.49 | 29 | 26 | 1 | 2 |
| 80 | fljlk | fljlk | 437.47 | 33 | 33 | 0 | 0 |
| 81 | lksuhir | cjkSnk | 279.91 | 26 | 8 | 9 | 9 |
| 82 | lksuhir | xUukSj | 501.52 | 44 | 25 | 5 | 14 |
| 83 | lksuhir | xksgkuk | 309.80 | 34 | 7 | 13 | 14 |
| 84 | lksuhir | [kj[kkSnk | 445.53 | 35 | 11 | 18 | 6 |
| 85 | lksuhir | jkbZ | 409.49 | 40 | 8 | 21 | 11 |
| 86 | lksuhir | lksuhir | 0.00 | 0 | 0 | 0 | 0 |
| 87 | ;equk uxj | txk/kjh | 264.63 | 68 | 48 | 9 | 11 |
| 88 | ;equk uxj | jknkSj | 473.21 | 77 | 31 | 12 | 34 |
| 89 | ;equk uxj | l<kSjk | 381.23 | 89 | 64 | 4 | 21 |
| 90 | ;equk uxj | ;equk uxj | 221.29 | 57 | 15 | 20 | 22 |
| **Dqy** | **32016.21** | **3729** | **2459** | **338** | **932** |
| **dqy jkf'k ¼djksM esa½** | **320.16** |   |   |   |   |