**To Complete the Development Works under VAGY**

**\*58 SH. INDU RAJ (Baroda) :**

Will the Development & Panchayats Minister be pleased to state:-

**a)** whether it is a fact that the amount of Rs.1,99,10,000 was released for the development works of Baroda Assembly Constituency under the Vidhayak Adarsh Gram Yojana on 30.03.2021 together with the number of works from the said announcement which have been completed alongwith the number of works which are lying incomplete; and

 **b)** the reasons for which these works have not been completed so far together with the time by which the said works are likely to be completed along with the complete details thereof ?

**DEVENDER SINGH BABLI, DEVELOPMENT & PANCHAYATS MINISTER, HARYANA**

**a)** Yes Sir, an amount of Rs.1,99,10,000 was released for 26 development works of Baroda Assembly Constituency under the Vidhayak Adarsh Gram Yojana for the FY 2019-20. Out of a total number of 26 development works, 12 works have been completed, 6 works are in progress and 8 works are yet to be started.

**b)** The detail of these works of Baroda Constituency along with its status is at annexure.

**विधायक आदर्श ग्राम योजना के अन्तर्गत विकास कार्य पूरे करना**

**\*58** श्री इंदु राज (बड़ौदा) :

क्या विकास एवं पंचायत मंत्री कृपया बताएंगे किः-

क) क्या यह तथ्य है कि बड़ौदा विधानसभा निर्वाचन क्षेत्र में दिनांक 30.03.2021 को विधायक आदर्श ग्राम योजना के अन्तर्गत विकास कार्यों के लिए रुपये 1,99,10,000 की राशि जारी की गई थी तथा उक्त घोषणा के अन्तर्गत पूरे किए गए कार्यों की संख्या कितनी है तथा कितने कार्य अधूरे पड़े है; तथा

ख) इन कार्यों के अब तक पूरा न किए जाने के क्या कारण है तथा उक्त कार्य कब तक पूरा किए जाने की संभावना है तथा उसका ब्यौरा क्या है?

**देवेंद्र सिंह बबली, विकास एवं पंचायत मंत्री, हरियाणा**

क) हां महोदय, बड़ौदा विधानसभा निर्वाचन क्षेत्र में विधायक आदर्श ग्राम योजना के अन्तर्गत वित्त वर्ष 2019-20 के लिए 26 विकास कार्यों के लिए 1,99,10,000 रुपये की राशि जारी की गई थी। कुल 26 विकास कार्यों में से 12 कार्य पूर्ण हो चुके हैं, 6 कार्य प्रगति पर हैं तथा 8 कार्य अभी प्रारंभ होने हैं।

ख) बड़ौदा निर्वाचन क्षेत्र के कार्यों का ब्यौरा स्थिति सहित अनुलग्नक पर है।

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|   |   |   |   |   |   |   |   |   |   | **(Annexure)**  |
| **Sh. Induraj Narwal, Hon'ble MLA Baroda Constituency** |
| **Completed** |
| **Sr. No.** | **Village**  | **Block**  | **Name of works** | **Est. Cost (Rs. in lacs)** | **Exp.****(Rs. in lacs)** | **Balance** |  **Date of Start** | **Date of Completion**  | **Status** | **Remarks**  |
| 1 | Chhichhrana | Kathura | Const. of Brick on edge rasta from H/o Rampat S/o Sh. Dhansingh to H/o Hawasingh S/o Sh. Balmat | 8.30 | 8.30 | 0.00 | 24-02-2022 | 23-05-2022 | Complete |   |
| 2 | Chhichhrana | Kathura | Const. of Brick on edge rasta from main road to H/o Surender S/o Sh. Rammehar | 9.33 | 8.99 | 0.34 | 21-02-2022 | 20-05-2022 | Complete |   |
| 3 | Dhanana | Kathura | Const. of IPB Street Ex. Sarpanch Home to Main Gali | 5.33 | 3.03 | 2.30 | 07-03-2022 | 06-06-2022 | Complete |   |
| 4 | Dhanana | Kathura | Const. of Jatayanpana Chaupal  | 12.78 | 1.50 | 11.28 | 25-03-2022 | 24-08-2022 | Complete | Only 1.50 lakhs utilized remaining Work completed by Beneficiary from there own contribution  |
| 5 | Kathura | Kathura | Const. of Narwal Bhawan Auditorium Hall  | 10.13 | 9.99 | 0.14 | 29-03-2022 | 31-12-2022 | Complete |   |
| 6 | Rindhana Jitsthar Pana | Kathura | Const. of R/wall of Pond | 18.80 | 17.15 | 1.65 | 29-03-2022 | 28-08-2022 | Complete |  |
| 7 | Rindhana  | Kathura | Const. of Rasta from village Firni to Sitla Mata Mandir Gate | 18.17 | 11.55 | 6.62 | 14-04-2022 | 31-12-2022 | Complete |   |
| 8 | Rindhana  | Kathura | Pavement of Biram Wala Rasta from Julana road to H/o Dilbag S/o Lakhmi | 19.16 | 13.65 | 5.51 | 07-03-2022 | 31-12-2022 | Complete |   |
| 9 | Anwali | Gohana | Const. of Cow Ghat on Ohla pond | 2.88 | 0.00 | 2.88 | 24-06-2022 | 13-08-2022 | Complete | Work Completed by GP |
| 10 | Bhanwar Bura | Kathura | Installation of Open Gym | 1.92 | 1.20 | 0.72 | 10-02-2023 | 28-02-2023 | Complete |  |
| 11 | Banwasa | Kathura | Installation of Open Gym | 1.92 | 1.20 | 0.72 | 10-02-2023 | 28-02-2023 | Complete |  |
| 12 | Rindhana  | Kathura | Installation of Open Gym | 1.92 | 1.20 | 0.72 | 10-02-2023 | 10-03-2023 | Complete |  |
| **Total** | **110.64** | **77.76** | **32.88** |  |  |  |  |

|  |
| --- |
| **Sh. Induraj Narwal, Hon'ble MLA Baroda Constituency** |
| **In Progress** |
| **Sr. No.** | **Village**  | **Block**  | **Name of works** | **Est. Cost (Rs. in lacs)** | **Exp.****(Rs. in lacs)** | **Balance** |  **Date of Start** | **Date of Completion**  | **Status** | **Remarks**  |
| 1 | Madina | Kathura | Installation of Open Gym | 1.92 | 1.00 | 0.92 | 10-02-2023 | 31-03-2023 | In Progress | Delay due to finalization of DC rate for GYM equipments |
| 2 | Rindhana  | Kathura | Const. of Balmiki Chaupal | 11.44 | 5.00 | 6.44 | 15-04-2022 | 30-06-2023 | In Progress | Work delay due to Court stay for aaprox. 5 months . Work in progress |
| 3 | Katwal  | Gohana | Const. of Rasta & B/wall in Shamshan Ghat | 5.38 | 4.52 | 0.86 | 15-06-2022 | 31-03-2023 | In Progress | Work delay due to low lying area of Shamshan ghat. Stagnation of rain water occurred, Now site clear  |
| 4 | Katwal  | Gohana | Comp. of Bhura & Madan Pana Chaupal | 5.39 | 3.00 | 2.39 | 12-04-2022 | 31-05-2023 | In Progress | Villagers demand other works instead of approved chaupal. Now work of chaupal is in progress.  |
| 5 | Mundlana | Mundlana  | Comp. of Shamtaan Pana Chaupal | 8.40 | 6.43 | 1.97 | 25-05-2022 | 15-04-2023 | In Progress | Finishing works pending  |
| 6 | Mundlana | Mundlana  | Comp. of Himtan pana Chaupal | 5.50 | 4.75 | 0.75 | 25-08-2022 | 15-04-2023 | In Progress | Electric works pending  |
| **Total** | **38.03** | **24.70** | **13.33** |  |  |  |  |

|  |
| --- |
| **Sh. Induraj Narwal, Hon'ble MLA Baroda Constituency** |
| **Not Started** |
| **Sr. No.** | **Village**  | **Block**  | **Name of works** | **Est. Cost (Rs. in lacs)** | **Exp.****(Rs. in lacs)** | **Balance** | **Status** | **Remarks**  |
| 1 | Mundlana | Mundlana  | Comp. of Harijjan Chaupal | 3.50 | 0.00 | 3.50 | Not Started | 16th time tender re-call memo No. 2018 dated 02-03-2022, no. 2739 dated 24-03-2022, no. 3095 dated 31-03-2022 no. 3431 dated 12-04-2022, no. 3641 dated 21-04-2022, no. 4095 dated 04-05-2022, no. 4561 dated 13-05-2022, no. 5833 dated 10-06-2022, no. 6099 dated 28-06-2022, no. 6389 dated 07-07-2022, no. 6768 dated 19-07-2022, no. 7162 dated 28-07-2022, no. 7948 dated 12-08-2022, no. 8559 dated 24-08-2022, no. 9745 dated 07-09-2022, no. 10434 dated 19-09-2022, no. 10869 dated 27-09-2022, but tender not received. Now, Tender under Process on HEW Portal. |
| 2 | Bichpari | Mundlana  | Comp. of Dholi Chaupal (Puniya Pana) Gen | 2.47 | 0.00 | 2.47 | Not Started | 16th time tender re-call memo No. 2018 dated 02-03-2022, no. 2739 dated 24-03-2022, no. 3095 dated 31-03-2022 no. 3431 dated 12-04-2022, no. 3641 dated 21-04-2022, no. 4095 dated 04-05-2022, no. 4561 dated 13-05-2022, no. 5833 dated 10-06-2022, no. 6099 dated 28-06-2022, no. 6389 dated 07-07-2022, no. 6768 dated 19-07-2022, no. 7162 dated 28-07-2022, no. 7948 dated 12-08-2022, no. 8559 dated 24-08-2022, no. 9745 dated 07-09-2022, no. 10434 dated 19-09-2022, no. 10869 dated 27-09-2022, but tender not received. Now, Tender under Process on HEW Portal. |
| 3 | Katwal  | Gohana | Const. of Hall near Mata Masani Mandir | 5.16 | 0.00 | 5.16 | Not Started | 16th time tender re-call memo No. 2018 dated 02-03-2022, no. 2739 dated 24-03-2022, no. 3095 dated 31-03-2022 no. 3431 dated 12-04-2022, no. 3641 dated 21-04-2022, no. 4095 dated 04-05-2022, no. 4561 dated 13-05-2022, no. 5833 dated 10-06-2022, no. 6099 dated 28-06-2022, no. 6389 dated 07-07-2022, no. 6768 dated 19-07-2022, no. 7162 dated 28-07-2022, no. 7948 dated 12-08-2022, no. 8559 dated 24-08-2022, no. 9745 dated 07-09-2022, no. 10434 dated 19-09-2022, no. 10869 dated 27-09-2022, but tender not received. Now, Tender under Process on HEW Portal. |
| 4 | Bhainswal Khurd | Kathura | Const. of Punia Chaupal/ Community Centre | 15.55 | 0.00 | 15.55 | Not Started | Work order issued on dated 28.02.2022. Gram Panchayat write to B&R Department on dated 19-05-2022 and B&R Department declared it condemned vide letter no. 856 dated 11-07-2022. After that Gram Panchayat Complete auction process on dated 06-092022. Meanwhile agency denied to do the owrk. Now tender is under process on HEW Portal.  |
| 5 | Katwal  | Gohana | Const. of IPB Street from H/o Hariom S/o Sh. Mange to Bhali Braman Rasta | 2.98 | 0.00 | 2.98 | Not Started | After re-call 3rd time, bid received on 31-03-2022. Dispute on site. Now as per consent of Hon'ble MLA estimate of ' Const. of Room at General Shamshan Ghat' is under Process.  |
| 6 | Katwal  | Gohana | Const. of B/wall of SC Chaupal  | 1.92 | 0.00 | 1.92 | Not Started | After re-call 3rd time, bid received on 31-03-2022. Dispute on site. Now as per consent of Hon'ble MLA estimate of ' Const. of Room at General Shamshan Ghat' is under Process.  |
| 7 | Rukhi Khas | Gohana | Const. of Cow Ghat on Ghotda pond | 2.88 | 0.00 | 2.88 | Not Started | 10th time tender re-called vide memo no. 2739 dated 24-03-2022, no. 3095 dated 31-03-2022 , no. 3431 dated 12-04-2022, no. 3641 dated 21-04-2022, no. 4095 dated 04-05-2022, no. 4561 dated 13-05-2022, 5833 dated 10-06-2022. 11th time bid received. This work was not started due to approx. 6 to 7 fit water at the site. At present there is no vacant site near by pond to drain the pond water. SDO (PR) reported that work will be done after wheat harvesting.  |
| 8 | Bhainswal Khurd | Kathura | Const. of Malik Chaupal/ Community Centre | 15.55 | 0.00 | 15.55 | Not Started | Work order issued on dated 07.03.2022. Gram Panchayat write to B&R Department on dated 19-05-2022 and B&R Department declared it condemned vide letter no. 856 dated 11-07-2022. After that Gram Panchayat Complete auction process on dated 06-092022. Meanwhile agency denied to do the owrk. Now tender is under process on HEW Portal.  |
| **Total** | **50.01** | **0.00** | **50.01** |  |  |