**STARRED ASSEMBLY QUESTION NO. \*58**

**NOTE FOR PAD**

**VIDHAYAK ADARSH GRAM YOJANA**

Vidhayak Adarsh Gram Yojana (VAGY) is a State sponsored Scheme which was started in 2015 on the pattern of Saansad Adarsh Gram Yojana (SAGY). Under this scheme, initially, Hon’ble MLA was allowed to recommend/opt village having population of 3000-7000 in the plain area and 1000-3000 in hilly area of his/her constituency for development through the convergence mode. In case of urban constituency, Hon’ble MLA can identify any village from a nearby rural constituency. As per State Govt. decision dated 26.12.2018, Rs.2.00 crore is provided to each constituency every year for the development works of the village on the basis of population of the village. Hon’ble MLA can recommend works upto Rs.50.00 lacs in a village having population at least 5000, upto Rs.1.00 crore in a village having population 5000-10000 and upto Rs.2.00 crore in a village having population more than 10,000. Deputy Commissioner is the District Nodal Officer and responsible for implementation of the scheme.

This scheme was put on hold after a decision taken in an All Party Meeting on 08.04.2020 during the lockdown for combating the Coronavirus pandemic. The implementation has been re-commenced after the conclusion of the General Elections to Panchayati Raj Institutions in December, 2022. The proposals will be considered on the basis of feasibility and as and when they are received.

The status of funds released and works undertaken under this scheme for the years 2018-19 and 2019-20 is as under:-

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Funds sanctioned for the Year** | **Funds released during the year** | **Amount Sanctioned**  **(Rs. in crore)** | **Exp.**  **(Rs. in crore)** | **Works Undertaken** | **Works Completed** |
| 2018-19 | 2019-20 | 27.34 | 29.91 | 388 | 359 |
| 2020-21 | 6.15 |
| **Sub Total** | | **33.49** |
| 2019-20 | 2019-20 | 37.00 | 119.19 | 1829 | 1379 |
| 2020-21 | 120.49 |
| 2021-22 | 11.30 |
| **Sub Total** | | **168.79** |
| **Grand Total** | | **202.28** | **149.10** | **2217** | **1738** |

Constituency-wise detail of funds released and expenditure are at Annexure “B”.

**Status of funds released for the financial year 2022-23**

|  |  |  |  |
| --- | --- | --- | --- |
| **Amount Sanctioned**  **(Rs. in crore)** | **Exp.**  **(Rs. in crore)** | **Works Undertaken** | **Works Completed** |
| 3.00 | 0.00 | 21 | 0 |

An amount of Rs.1,99,10,000 was sanctioned for the development of 26 works identified by Sh. Induraj Narwal, Hon’ble MLA, Baroda Constituency for the FY 2019-20. Out of a total number of 26 works, 12 works have been completed, 6 works are in progress and 8 works are yet to be started.

**Detail of in progress works**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Sr. No.** | **Name of Village** | **Name of Works** | **Date of Start** | **Date of Completion** | **Remarks** |
| 1 | Madina | Installation of Open Gym | 10-02-2023 | 15-03-2023 | Delay due to finalization of DC rate for GYM equipments. |
| 2 | Rindhana | Const. of Balmiki Chaupal | 15-04-2022 | 30-06-2023 | Work delay due to court stay. |
| 3 | Katwal | Const. of Rasta & B/wall in Shamshan Ghat | 15-06-2022 | 31-03-2023 | Work delay due to low lying area of Shamshan Ghat. Stagnation of rain water occurred. |
| 4 | Katwal | Comp. of Bhura & Madan Pana Chaupal | 12-04-2022 | 31-03-2023 | Villagers demanded other work instead of approved Chaupal. Now, work of Chaupal is in progress. |
| 5 | Mundlana | Comp. of Shamtaan Pana Choupal | 25-05-2022 | 15-02-2023 | Finishing work pending |
| 6 | Mundlana | Comp. of Himtan Pana Choupal | 25-08-2022 | 15-02-2023 | Electric work pending |

**Detail of not started works**

|  |  |  |  |
| --- | --- | --- | --- |
| **Sr. No.** | **Name of Village** | **Name of Works** | **Remarks** |
| 1 | Mundlana | Comp. of Harijan Chaupal | 16th time tender re-called but tender not received. Now, tender under Process on HEW Portal. |
| 2 | Bichpari | Comp. of Dholi Chaupal (Puniya Pana) Gen | 16th time tender re-called but tender not received. Now, tender under Process on HEW Portal. |
| 3 | Katwal | Const. of Hall near Mata Masani Mandir | 16th time tender re-called but tender not received. Now, tender under Process on HEW Portal. |
| 4 | Bhainswal Khurd | Const. of Punia Chaupal/ Community Centre | Work order issued on 28.02.2022 but agency denied to start this work. Now tender is under process on HEW portal. |
| 5 | Katwal | Const. of IPB Street from H/o Hariom S/o Sh. Mange to Bhali Braman Rasta | Dispute on site. Now, as per consent of Hon’ble MLA, estimate of ‘Const. of room at General shamshaan ghat’ is under process in place of these two works. |
| 6 | Katwal | Const. of B/wall of SC Chaupal |
| 7 | Rukhi Khas | Const. of Cow Ghat on Ghotda pond | This work was not started due to approx. 6 to 7 ft. water at the site. At present there is no vacant site nearby pond to drain the pond water. This work will be executed after wheat harvesting. |
| 8 | Bhainswal Khurd | Const. of Malik Chaupal/  Community Centre | Work order issued on 07.03.2022. Agency denied to the work. Now tender is under process on HEW Portal. |

**तारांकित विधान सभा प्रश्न सं \*58**

**नोट फार पैड**

**विधायक आदर्श ग्राम योजना**

विधायक आदर्श ग्राम योजना एक राज्य प्रायोजित योजना है जोकि सांसद आदर्श ग्राम योजना की तर्ज पर 2015 में लागू की गई थी। आरम्भ में इस योजना के अन्तर्गत माननीय विधायक द्वारा अपने निर्वाचन क्षेत्र के मैदानी क्षेत्र में 3000-5000 और पहाड़ी क्षेत्र में 1000-3000 जनसंख्या वाले गांव के विकास का सहभागिता के माध्यम से चयन करने की अनुमति दी गई थी। शहरी विधान सभा क्षेत्र के मामले में माननीय विधायक अपने नजदीकी ग्रामीण विधान सभा क्षेत्र के किसी गांव का चयन कर सकते है। राज्य सरकार द्वारा दिनांक 26.12.2018 को निर्णय लिया गया कि प्रत्येक विधान सभा क्षेत्र के विकास कार्यों के लिए प्रति वर्ष गांव की जनसंख्या के आधार पर 2.00 करोड़ रूपए की राशि उपलब्ध करवाई जाएगी। माननीय विधायक 5000 तक की आबादी वाले गांव के लिए 50.00 लाख रूपए, 5000-10000 तक की आबादी वाले गांव के लिए 1.00 करोड़ रूपए व 10000 से अधिक आबादी वाले गांव के लिए 2.00 करोड़ रूपए के कार्यों की सिफारिश कर सकते हैं। उपायुक्त जिले के नोडल अधिकारी हैं और योजना के कार्यान्वयन के लिए जिम्मेवार है।

कोरोना वायरस महामारी से निपटने के लिए लॉक डाउन के दौरान सर्वदलीय बैठक दिनांक 08.04.2020 को निर्णय के बाद इस योजना को रोक दिया गया था। दिसंबर, 2022 में पंचायती राज संस्थाओं के आम चुनाव संपन्न होने के बाद कार्यान्वयन को फिर से शुरू किया गया है। प्रस्ताव पर व्यवहार्यता के आधार पर जैसे ही वे प्राप्त होंगे, विचार किया जाएगा।

इस योजना के अन्तर्गत वर्ष 2018-19 व 2019-20 में जारी की गई राशि व लिए गए कार्यों का ब्यौरा निम्न प्रकार से हैः-

(**रूपए करोड़ों में**)

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **वर्ष** | **वर्ष के दौरान स्वीकृत की गई राशि** | **जारी की गई राशि** | **खर्च की गई राशि** | **किए गए कार्य** | **पूर्ण किए गए कार्य** |
| 2018-19 | 2019-20 | 27.34 | 29.91 | 388 | 359 |
| 2020-21 | 6.15 |
| **जोड़** | | 33.49 |
| 2019-20 | 2019-20 | 37.00 | 119.19 | 1829 | 1379 |
| 2020-21 | 120.49 |
| 2021-22 | 11.30 |
| **जोड़** | | 168.79 |
| **कुल जोड़** | | **202.28** | **149.10** | **2217** | **1738** |

जारी की गई निधियां और व्यय का निर्वाचन क्षेत्र-वार ब्यौरा अनुलग्नक बी पर है।

**वित्तीय वर्ष 2022-23 के लिए जारी धनराशि की ब्यौरा**

|  |  |  |  |
| --- | --- | --- | --- |
| **जारी की गई राशि**  (**रूपए करोड़ों में**) | **खर्च की गई राशि**  (**रूपए करोड़ों में**) | **किए गए कार्य** | **पूर्ण किए गए कार्य** |
| 3.00 | 0.00 | 21 | 0 |

श्री इंदु राज नरवाल, माननीय विधायक, बड़ौदा निर्वाचन क्षेत्र द्वारा वित्त वर्ष 2019-20 के लिए चयन किए गए 26 कार्यों के विकास के लिए 1,99,10,000 रुपये की राशि स्वीकृत की गई थी। कुल 26 कार्यों में से12 कार्य पूर्ण हो चुके हैं, 6 कार्य प्रगति पर हैं तथा8 कार्य अभी प्रारंभ होने हैं।

**प्रगति कार्यों का ब्यौरा**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **क्र0**  **सं0** | **गांव का नाम** | **कार्य का नाम** | **प्रारंभ की तिथि** | **पूर्ण होने की तिथि** | **टिप्पणी** |
| 1 | मदीना | ओपन जिम की स्थापना | 10.02.2023 | 15.03.2023 | डी.सी रेट फाईनल न होने के कारण जिम उपकरणों को खरीदने में देरी हुई है। |
| 2 | रिंधाना | बाल्मीकि चौपाल का निर्माण | 15.04.2022 | 30.06.2023 | कोर्ट स्टे की वजह से काम में देरी हुई है। |
| 3 | कटवाल | श्मशान घाट में रास्ता और चारदीवारी का निर्माण | 15.06.2022 | 31.03.2023 | श्मशान घाट की जगह गहरी होने से उसमें बारिश के पानी के ठहराव के कारण काम में देरी हुई है। |
| 4 | कटवाल | भूरा व मदन पाना चौपाल को पूर्ण कराना | 12.04.2022 | 31.03.2023 | ग्रामीणों ने चौपाल के स्थान पर अन्य काम की मांग की है। अब कार्य प्रगति पर है। |
| 5 | मुंडलाना | शमतान पाना चौपाल को पूर्ण करना | 25.05.2022 | 15.02.2023 | फिनिशिंग का काम बाकी है |
| 6 | मुंडलाना | हिमतान पाना चौपाल को पूर्ण करना | 25.08.2022 | 15.02.2023 | बिजली का काम बाकी है |

**शुरू नही हुए कार्यों का ब्यौरा**

|  |  |  |  |
| --- | --- | --- | --- |
| **क्र0 सं0** | **गांव का नाम** | **कार्य का नाम** | **टिप्पणी** |
| 1 | मुंडलाना | हरिजन चौपाल को पूर्ण करना | 16 बार टेडंर लगाया गया परन्तु टेडंर किसी के द्वारा प्राप्त नही किया गया। अब टेडंर एच.ई.डब्ल्यू.पोर्टल पर प्रक्रियाधीन है। |
| 2 | बिचपड़ी | ढ़ौली चौपाल (पुनिया पाना) सामान्य को पूर्ण करना | 16 बार टेडंर लगाया गया परन्तु टेडंर किसी के द्वारा प्राप्त नही किया गया। अब टेडंर एच.ई.डब्ल्यू.पोर्टल पर प्रक्रियाधीन है। |
| 3 | कटवाल | माता मसानी मंदिर के पास हाल का निर्माण करना | 16 बार टेडंर लगाया गया परन्तु टेडंर किसी के द्वारा प्राप्त नही किया गया। अब टेडंर एच.ई.डब्ल्यू.पोर्टल पर प्रक्रियाधीन है। |
| 4 | भैंसवाल खुर्द | पुनिया चैपाल/सामुदायिक केन्द्र का निर्माण | कार्य आदेश 28.02.2022 को जारी किया गया था परन्तु ऐजैंसी ने काम शुरू करने से मना कर दिया था। अब टेडंर एच.ई.डब्ल्यू. पोर्टल पर प्रक्रियाधीन है। |
| 5 | कटवाल | हरिओम पुत्र श्री मांगे के घर से भाली ब्रह्रामण रास्ता तक आई.पी.बी. गली का निर्माण | कार्य स्थल पर विवाद है। अब माननीय विधायक की सहमति अनुसार दो कार्यों के स्थान पर जनरल श्मशान घाट के कमरे के कार्य का निर्माण का प्राक्कलन अब प्रगति पर है। |
| 6 | कटवाल | एस.सी चौपाल की चारदीवारी का निर्माण |
| 7 | रूखी खास | गोठडा तालाब पर गाय घाट का निर्माण | कार्य स्थल पर लगभग 6-7 फुट पानी होने के कारण कार्य शुरू नही किया गया था। इस समय तालाब के पास खाली जगह न होने के कारण तालाब का पानी नही निकाला जा सकता। गेँहू कटवाने के बाद कार्य शुरू कर दिया जाएगा। |
| 8 | भैंसवाल खुर्द | मलिक चौपाल/ सामुदायिक केंद्र का निर्माण | कार्य आदेश 07.03.2022 को प्रदान किया गया था परन्तु ऐजैंसी ने काम शुरू करने से मना कर दिया था। अब कार्य एच.ई.डब्ल्यू. पोर्टल पर प्रक्रियाधीन है। |

Annexure "B"

RURAL DEVELOPMENT DEPARTMENT, HARYANA, CHANDIGARH

Constituency-wise Statement showing physical and financial status of (2.00 crore) Vidhayak Adarsh Gram Yojana for the year of 2018-19 (after 26.12.2018 )

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr.**  **No.** | **Name of District** | **Name of MLA** | **Name of Constituency** | **No. of Villages** | **Population** | **Sanctioned Date** | **Sanctioned Amt. (Rs.in crore)** | **Expenditure Amt. (Rs. in**  **crore)** | **Total No. of works**  **Sanctioned** | **Works Completed** | **Works-In- Progress** | **Yet to Start** |
| **1** | Ambala | Smt.Santosh Chauhan  Sarwan | Mullana | Mullana | 5056 | 10.09.2019/  5.10.2020 | 0.99 | 0.33 | 7 | 4 | 2 | 1 |
| 2 | Bhiwani | Sh. Ghanshyam Dass  Saraf | Bhiwani | 3 villages (Kayla, Phoolpura and  Devsar) | More than 10000 | 10.09.2019 | 1.63 | 1.39 | 9 | 6 | 3 | 0 |
| 3 | Bhiwani | Sh. Bishamber Singh | Bawani Khera | 3 villages (Dhanana-II, Badesara and  Dhani Chang) | More than 10000 | 10.09.2019 | 1.25 | 1.19 | 8 | 8 | 0 | 0 |
| 4 | Bhiwani | Sh.Om Parkash Bharwa | Loharu | 4 villages (Damkora, Bhidhnoi, Morka,  Budhshely) | More than 10000 | 10.09.2019 | 1.90 | 1.90 | 19 | 19 | 0 | 0 |
|  |  |  |  |  |  | **Total** | **4.78** | **4.48** | **36** | **33** | **3** | **0** |
| 5 | Ch.Dadri | Sh. Sukhvinder Mandhi | Badra | 6 villages (Mahda, Maikalan, Rambass, Jhojhu Khurd, Bhadwa,  Kanhda) | More than 10000 | 11.09.2019/  5.10.2020 | 1.04 | 0.62 | 4 | 3 | 0 | 1 |
|  | Ch.Dadri | Sh. Sukhvinder Mandhi | Badra | 4 villages (Badhara, Jagram Bass,  Khorda, Rambass) | More than 10000 | 20.09.2019/  5.10.2020 | 0.91 | 0.75 | 2 | 1 | 0 | 1 |
|  |  |  |  |  |  | **Total** | **1.94** | **1.37** | **6** | **4** | **0** | **2** |
| 6 | Faridabad | Sh.Tek Chand Sharma | Prithala | Hirapur | 3145 | 06.09.2019 | 0.38 | 0.38 | 16 | 16 | 0 | 0 |
| 7 | Fatehabad | Sh.Subash Barala | Tohana | Samain | 10892 | 10.09.2019 | 1.00 | 0.00 | 12 | 0 | 0 | 12 |
| 8 | Gurugram | Sh.Rao Narbir Singh | Badhshapur | 5 villages (Kakrola, Dhankot, Teekli, Gadhi Harsaru, Vandu) | More than 10000 | 10.09.2019 | 1.97 | 1.81 | 10 | 10 | 0 | 0 |
| 9 | Jind | Sh. Jasbir Deswal | Safidon | Datrath | 8795 | 30.07.2019 | 0.17 | 0.17 | 1 | 1 | 0 | 0 |
| 10 | Jind | Smt. Prem Lata | Uchana | Khanda | 3620 | 12.09.2019 | 0.50 | 0.50 | 5 | 5 | 0 | 0 |
|  |  |  |  |  |  | **Total** | **0.67** | **0.67** | **6** | **6** | **0** | **0** |
| 11 | Jhajjar | Sh.Om Parkash Dhankar | Badli | Patoda | 7447 | 03.09.2019 | 0.32 | 0.32 | 3 | 3 | 0 | 0 |
|  | Jhajjar | Sh.Om Parkash Dhankar | Badli | Dhakala | 4333 | 12.09.2019 | 0.50 | 0.50 |
|  |  |  |  |  |  | **Sub Total** | **0.82** | **0.82** | **3** | **3** | **0** | **0** |
| 12 | Jhajjar | Sh.Naresh Kaushik | Bahadurgarh | 3 villages (Kassar, Barahi, Sankhol) | More than 10000 | 16.09.2019 | 1.25 | 1.25 | 4 | 4 | 0 | 0 |
|  |  |  |  |  |  | **Total** | **2.08** | **2.08** | **7** | **7** | **0** | **0** |

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr.**  **No.** | **Name of District** | **Name of MLA** | **Name of Constituency** | **No. of Villages** | **Population** | **Sanctioned Date** | **Sanctioned Amt. (Rs.in crore)** | **Expenditure Amt. (Rs. in**  **crore)** | **Total No. of works**  **Sanctioned** | **Works Completed** | **Works-In- Progress** | **Yet to Start** |
| 13 | Hisar | Capt.Abhimanyu | Narnaund | Puthi Samain & Petwar | More than 10000 | 30.07.2019/  07.10.2020 | 0.24 | 0.24 | 3 | 3 | 0 | 0 |
| 14 | Karnal | Sh. Bakhshish Singh Virk | Assandh | (22 villages) Bandrala, Bassi, Bilona, Chogama, Danoli, Dera Gama, Dera Gujratia, Dera Phoola Singh, Dera Pindoria, Dera Pindoria, Dupedi, Kherisarfali, Khidrabad, Mardanheri, Padhana, Popra, Rahra, Rattak, Rugsana, Salwan, Thal, Thari | More than 10000 | 10.09.2019 | 2.00 | 1.88 | 43 | 42 | 0 | 1 |
| 15 | Karnal | Sh. Bhagwan Dass Kabir  Panthi | Nilokheri | Naraina | 3553 | 30.07.2019 | 0.08 | 0.08 | 2 | 2 | 0 | 0 |
|  | Karnal | Sh. Bhagwan Dass Kabir Panthi | Nilokheri | (13 villages) Sultanpur, Dayanagar, Brahman Majra, Bukhapuri, Dabarthala, Sambhi, Shekanpur, Parwala, Nigdhu, Majra Roran, Budhera Kalsha, Barana | More than 10000 | 20.09.2019/  07.10.2020 | 1.07 | 0.56 | 17 | 13 | 2 | 2 |
|  |  |  |  |  |  | **Sub Total** | **1.15** | **0.64** | **19** | **15** | **2** | **2** |
|  |  |  |  |  |  | **Total** | **3.15** | **2.52** | **62** | **57** | **2** | **3** |
| 16 | Kurukshetra | Sh. Subhash Sudha | Thanesar | (12 villages) Amin, Alampur, Bahri, Barwa, Bir Amin, Doda Kheri, Dabkheri, Jyotisar, Patti Kaserla, Partap Garh, Rattan Dera, Tigri Khalsa | More than 10000 | 10.09.2019 | 2.00 | 2.00 | 24 | 24 | 0 | 0 |
| 17 | Kurukshetra | Sh.Krishan Kumar Bedi | Shahbad | (13 villages) Sudhpur, Khera, Macchaurali, Rawa, Yara, Kalsana, Maddipur, Saidpur Barwala, Ram Nagar, Boripur, Raipur/Raimajra, Thaska Ali, Berthali | More than 10000 | 12.09.2019 | 0.93 | 0.90 | 14 | 13 | 1 | 0 |
|  |  |  |  |  |  | **Total** | **2.93** | **2.90** | **38** | **37** | **1** | **0** |
| 18 | Kaithal | Sh.Randeep Singh Surjewala | Kaithal | (21 villages) Kutubpur , Dillonwali, SangatPura , Malkheri, Sirta, Manas Patti , Baba Ladana , Nouch, Ujhana, Sajuma, Kathwar , Guhna , Dhons, Dayohra, Sirta , Budhakhera , Shakti Nagar , Deodkheri, Patti Khot , Padla | More than 10000 | 10.09.2019 | 1.00 | 1.49 | 34 | 33 | 1 | 0 |
|  | Kaithal | Sh.Randeep Singh Surjewala | Kaithal | (9 villages) Sirta, Baba Ladana, Patti Khot , Mundri, Dehora, Chak Padla,  Guhna, Bhanpura, Padla | More than 10000 | 11.09.2019 | 0.50 |

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr.**  **No.** | **Name of District** | **Name of MLA** | **Name of Constituency** | **No. of Villages** | **Population** | **Sanctioned Date** | **Sanctioned Amt. (Rs.in crore)** | **Expenditure Amt. (Rs. in**  **crore)** | **Total No. of works**  **Sanctioned** | **Works Completed** | **Works-In- Progress** | **Yet to Start** |
| 19 | Kaithal | Sh.Kulwant Singh Bazigar | Guhla | (18 villages) Tatiana, Mengra, Bhuna, Baupur, Landheri, Theh Banhera, Umedpur, Majri , Ramdasspura, Khanpur, Kangthali, Gohran, Kekyor Majra , Pissol, Parbhawat, Kheri Gulam Ali, Malikpur, Siwan | More than 10000 | 10.09.2019 | 1.00 | 1.00 | 11 | 11 | 0 | 0 |
|  |  |  |  |  |  | **Total** | **2.50** | **2.49** | **45** | **44** | **1** | **0** |
| 20 | M/Garh | Sh.Ram Bilas Sharma | M/Garh | (2 villages) Zerpur, Malra Bass, | More than 10000 | 10.09.2019 | 1.00 | 1.00 | 8 | 8 | 0 | 0 |
| 21 | M/Garh | Dr.Abhay Singh Yadv | Nangal Chodhary | (10 ) Ajmabad Mokhuta, Pavera,GhataSher,Brahamanwas, Niyajalipur, Bhankhri, Totahedi,  Dokhera, Mulodi,Bhedanti | More than 10000 | 10.09.2019 | 1.00 | 1.00 | 15 | 15 | 0 | 0 |
| 22 | M/Garh | Smt.Santosh Yadav | Ateli | (2 villages) Kheri, Rattan Kalan | More than 10000 | 11.09.2019 | 0.97 | 0.97 | 22 | 22 | 0 | 0 |
|  |  |  |  |  |  | **Total** | **2.97** | **2.97** | **45** | **45** | **0** | **0** |
| 23 | Palwal | Sh.Karan Singh Dalal | Palwal | Samain | More than 10000 | 10.09.2019/  5.10.2020 | 0.95 | 0.89 | 7 | 7 | 0 | 0 |
| 24 | Panchkula | Sh. Gyan Chand Gupta | Panchkula | Rattewali | 2812 | 30.07.2019 | 0.50 | 0.50 | 7 | 7 | 0 | 0 |
| 25 | Rewari | Dr.Banwari Lal | Bawal | (19 villages) Bidawas, Tankri, Nangli Parsapur, Mangleshwar , Dharan, Khandoda, Bishanpur, Chirhara, Tihara , Pranpura, Suthana, Nandrampur Bass, Bhatwas, Khijuri, Bhatsana , Dhani Sundroj, Kolana, Khatela, Mailawas | More than 10000 | 10.09.2019 | 0.50 | 0.50 | 6 | 6 | 0 | 0 |

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr.**  **No.** | **Name of District** | **Name of MLA** | **Name of Constituency** | **No. of Villages** | **Population** | **Sanctioned Date** | **Sanctioned Amt. (Rs.in crore)** | **Expenditure Amt. (Rs. in**  **crore)** | **Total No. of works**  **Sanctioned** | **Works Completed** | **Works-In- Progress** | **Yet to Start** |
| 26 | Sirsa | Sh.Balkaur Singh | Kalanwali | (15 villages) Baguwali, Dhani Khuwali, Biruwala Gudha, Farwai Kalan, Jhopra, Takhatmal, Handi Khera, Bharokhan, Ranga, Bhawdin, Farwai Khurd, Dhani Ram Pura, Ahamadpur , Jhorarrohi, Daulatpur  Khera, | More than 10000 | 10.09.2019 | 2.00 | 2.00 | 19 | 19 | 0 | 0 |
| 27 | Sirsa | Smt. Naina Chautala | Dabwali | (6 villages) Dabwali, Nilliawali , Panna, Panniwala Ruldu, Sawantkhera, Jandwala Jattan | More than 10000 | 18.07.2019 | 0.99 | 0.95 | 14 | 13 | 0 | 1 |
|  | Sirsa | Smt. Naina Chautala | Dabwali | -do- | More than 10000 | 06.02.2020/  17.09.2020 | 0.95 | 0.85 | 14 | 13 | 0 | 1 |
|  |  |  |  |  |  | **Sub Total** | **1.93** | **1.79** | **28** | **26** | **0** | **2** |
|  |  |  |  |  |  | **Total** | **3.93** | **3.79** | **47** | **45** | **0** | **2** |
| 28 | Y/Nagar | Sh.Shyam Singh Rana | Radour | (17 villages) Baindi, Nagal, Kanju, Topra Kalan, Ghilor, Lal Chappar, Jathlana, Palaka, Rapri, Mohri, Saran, Golni, Golanpur, Lakshibans, Rattangarh Majri, Rattangarh, Hartan | More than 10000 | 11.09.2019 | 0.89 | 0.89 | 14 | 14 | 0 | 0 |
|  | Y/Nagar | Sh.Shyam Singh Rana | Radour | (14 villages) Sadura, Silikhurd, M.T. Karhera, Silikalan, Marupur, Lakshibans, Unheri, Kandroli Dholra, Jaguri, Lal Chhapar, Fatehpur, Bhogpur  Kajibans | More than 10000 | 10.09.2019 | 1.11 | 1.11 | 14 | 14 | 0 | 0 |
|  |  |  |  |  |  | **Total** | **2.00** | **2.00** | **28** | **28** | **0** | **0** |
|  |  |  |  |  |  | **Grand Total** | **33.49** | **29.91** | **388** | **359** | **9** | **20** |

|  |
| --- |
| **RURAL DEVELOPMENT DEPARTMENT, HARYANA, CHANDIGARH** |
| **Constituency-wise Statement showing physical and financial status of (2.00 crore) Vidhayak Adarsh Gram Yojana for the year of 2019-20** |

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr.**  **No.** | **Name of District** | **Name of MLA** | **Name of Constituency** | **No. of Villages** |  | **Sanctioned Date** | **Sanctioned Amt.**  **(Rs.in crore)** | **Expenditure Amt. (Rs.in crore)** | **Total No. of works**  **Sanctioned** | **Works Completed** | **Works-In- Progress** | **Yet to Start** |
| 1 | Ambala | Sh.Aseem Goel | Ambala City | (3 villages) Ugara, Jansui, Naneola | 1258, 2845, 4184 | 14.10.2020 | 1.31 | 0.86 | 27 | 21 | 4 | 2 |
|  | Ambala | Sh.Aseem Goel | Ambala City | (2 villages) Ugara, Jansui | 1258, 2845 | 14.01.2021 | 0.15 | 0.15 | 2 | 2 | 0 | 0 |
|  | Ambala | Sh.Aseem Goel | Ambala City | (2 villages) Batrohan, Jansui | 1449, 2845 | 18.03.2021 | 0.45 | 0.45 | 6 | 6 | 0 | 0 |
|  | Ambala | Sh.Aseem Goel | Ambala City | Batrohan | 1449 | 21.02.2022 | 0.04 | 0.04 | 1 | 1 | 0 | 0 |
|  | Ambala | Sh.Aseem Goel | Ambala City | Batrohan | 1449 | 25.03.2022 | 0.04 | 0.01 | 1 | 0 | 1 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.52** | **37** | **30** | **5** | **2** |
| 2 | Ambala | Sh.Anil Vij | Ambala Cantt. | (9 villages) Bara, Barnala, Brahman Majra, Dhankour, Garnala, Janetpur, Khatouli, Panjokhra Sahib, Tundli | More than 10000 | 1.12.2020 | 1.86 | 1.47 | 25 | 25 | 0 | 0 |
|  | Ambala | Sh.Anil Vij | Ambala Cantt. | 2 villages) Dhankaur & Janetpur | 1445 & 814 | 8.2.2021 | 0.14 | 0.14 | 2 | 2 | 0 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.60** | **27** | **27** | **0** | **0** |
| 3 | Ambala | Smt.Shalley Chaudhary | Naraingarh | (24 villages) Chechi Majra, Ferozpur Kath, Hadhbon, Miyanpur, Dehar, Lakhnaura , Shahpur Nurd, Rau Majra, Hussani, Kala Amb, Jauli, Nakhdoli, Badi Ujwal , Majri, Wasalpur , Shahzadpur, Naggawa, Tasrouli, Tandwal, Nasrouli, Fatehgarh, Jatwar, Handi Khera, Bheron | More than 10000 | 8.12.2020 | 1.29 | 0.92 | 30 | 23 | 6 | 1 |
|  | Ambala | Smt.Shalley Chaudhary | Naraingarh | (8 villages) Khudda Kalan, Hasanpur, Chhoti Bassi, Andheri, Bibipur, Nek Nawan, Khuddi, Rollon | More than 10000 | 01.02.2021 | 0.71 | 0.54 | 16 | 14 | 2 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.46** | **46** | **37** | **8** | **1** |
| 4 | Ambala | Smt.Santosh Chauhan Sarwan | Mullana | Saha | 8100 | 10.09.2019/  5.10.2020 | 1.00 | 0.78 | 7 | 2 | 4 | 1 |
|  | Ambala | Sh.Varun Chaudhary | Mullana | (4 villages) Zaffarpur, Ugala, Allahpur, Samlehri | 2443, 7307, 4115 | 28.01.2021 | 0.88 | 0.23 | 5 | 1 | 3 | 1 |
|  | Ambala | Sh.Varun Chaudhary | Mullana | Adhoi |  | 18.03.2021 | 0.12 | 1 | 0 | 1 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.01** | **13** | **3** | **8** | **2** |
|  |  |  |  |  |  | **Total** | **8.00** | **5.59** | **123** | **97** | **21** | **5** |
| 5 | Bhiwani | Sh. Bishamber Singh | Bawani Khera | Ratera | 5572 | 30.07.2019 | 0.20 | 0.20 | 1 | 1 | 0 | 0 |
|  | Bhiwani | Sh. Bishamber Singh | Bawani Khera | Tigrana | 10712 | 03.09.2019 | 0.81 | 0.81 | 5 | 5 | 0 | 0 |
|  | Bhiwani | Sh.Bishamber Singh | Bawani Khera | 2 villages (Gushkani & Sai) | 3070, 6080 | 06.02.2020 | 0.99 | 0.64 | 6 | 4 | 1 | 1 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.65** | **12** | **10** | **1** | **1** |
| 6 | Bhiwani | Smt.Kiran Chaudhary | Tosham | Lohani | More than 10000 | 04.09.2019 | 1.00 | 0.93 | 14 | 13 | 0 | 1 |
|  | Bhiwani | Smt.Kiran Chaudhary | Tosham | 2 villages (Isharwal and Garanpura Kalan) | 3950, 3719 | 31.12.2019 | 0.95 | 0.17 | 6 | 1 | 5 | 0 |
|  | Bhiwani | Smt.Kiran Chaudhary | Tosham | Sandwa |  | 18.03.2021 | 0.05 | 0.00 | 1 | 0 | 0 | **1** |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.10** | **21** | **14** | **5** | **2** |
| 7 | Bhiwani | Sh.Jai Parkash Dalal | Loharu | (20 Villages) Ahmadwas Khera, Sohansda, Gagadwas, Kudal, Garva, Naloi, Gurera, Kikral, Kalod, Talwani, Bidhwan, Dhani Bhakra, Obra, Sahryarpur, Sudhiwas, Hariyawas, Sherala, Baran, Dhani Gujran Sahryarpur, Budhedi | More than 10000 | 18.03.2020/  5.10.2020 | 2.00 | 1.49 | 23 | 15 | 8 | **0** |

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr.**  **No.** | **Name of District** | **Name of MLA** | **Name of Constituency** | **No. of Villages** |  | **Sanctioned Date** | **Sanctioned Amt.**  **(Rs.in crore)** | **Expenditure Amt. (Rs.in crore)** | **Total No. of works**  **Sanctioned** | **Works Completed** | **Works-In- Progress** | **Yet to Start** |
| 8 | Bhiwani | Sh. Ghanshyam Dass Saraf | Bhiwani | Sanga | 4539 | 30.07.2019 | 0.50 | 0.50 | 3 | 3 | 0 | 0 |
|  | Bhiwani | Sh. Ghanshyam Dass Saraf | Bhiwani | Menheru | 8214 | 10.09.2019 | 0.50 | 0.50 | 3 | 3 | 0 | 0 |
|  | Bhiwani | Sh.Ghanshyam Saraf | Bhiwani | Dhareru | 5491 | 26.03.2021 | 0.64 | 0.00 | 5 | 0 | 0 | **5** |
|  |  |  |  |  |  | **Sub Total** | **1.64** | **1.00** | **11** | **6** | **0** | **5** |
|  |  |  |  |  |  | **Total** | **7.64** | **5.25** | **67** | **45** | **14** | **8** |
| 9 | Ch.Dadri | Sh.Sombir Sangwan | Ch.Dadri | Charkhi | 6822 | 12.03.2020/  5.10.2020 | 0.88 | 0.55 | 2 | 1 | 1 | 0 |
|  |  |  |  |  |  | **Sub Total** | **0.88** | **0.55** | **2** | **1** | **1** | **0** |
| 10 | Ch.Dadri | Sh. Sukhvinder Mandhi | Badra | Jhoju Kalan | 8621 | 05.07.2019 | 0.61 | 0.20 | 4 | 4 | 0 | 0 |
|  | Ch.Dadri | Sh. Sukhvinder Mandhi | Badra | Jhoju Kalan | 8621 | 2.08.2019 | 0.39 | 1 | 1 | 0 | 0 |
|  | Ch.Dadri | Smt.Naina Chautala | Badra | (5 villages) Reharodi, Kaliyana, Mauri, Bhadra, Nanda | 2839, 4188, 3253,  26895, 3707 | 21.01.2021 | 0.92 | 0.11 | 6 | 0 | 6 | 0 |
|  | Ch.Dadri | Smt.Naina Chautala | Badra | Chirriya |  | 5.2.2021 | 0.08 | 0.00 | 1 | 0 | 1 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **0.31** | **12** | **5** | **7** | **0** |
|  |  |  |  |  |  | **Total** | **2.88** | **0.86** | **14** | **6** | **8** | **0** |
| 11 | Palwal | Sh.Tek Chand Sharma | **Prithala (villages identified in Palwal Distt.)** | Baghola | 5413 | 09.08.2019 | 0.97 | 0.97 | 10 | 10 | 0 | 0 |
|  | Palwal | Sh.Nayan Pal Rawat | **Prithla (villages identified under Palwal distt.)** | (9 villages) Alawalpur, Harfali, Sikanderpur, Bhurja, Amarpur, Kharjuka, Jalhaka | More than 10000 | 05.02.2021 | 0.97 | 0.73 | 9 | 6 | 3 | 0 |
|  | Faridabad | Sh.Nayan Pal Rawat | Prithala | Behbalpur |  | 29.03.2022 | 0.05 | 0.00 | 1 | 0 | 1 | 0 |
|  |  |  |  |  |  | **Sub Total** | **1.99** | **1.70** | **20** | **16** | **4** | **0** |
| 12 | Faridabad | Sh.Narender Gupta | **Faridabad (villages identified of Prithala Const. being Faridabad urban Const.)** | Harphala | 945 | 28.01.2021 | 0.38 | 0.20 | 3 | 1 | 1 | 1 |
|  | Faridabad | Sh.Narender Gupta | **Faridabad (villages identified of Ballabgarh Const. being Faridabad urban Const.)** | Mohla | 1625 | 05.02.2021 | 0.28 | 0.13 | 3 | 1 | 1 | 1 |
|  | Palwal | Sh.Narender Gupta | **Faridabad (villages identified of Palwal Const. being Faridabad urban Const.)** | Kushak | 13477 | 08.01.2021 | 0.30 | 0.95 | 6 | 5 | 1 | 0 |
|  | Palwal | Sh.Narender Gupta | **Faridabad (villages identified of Palwal Const. being Faridabad urban Const. and villages under Palwal distt.)** | (2 villages) Devli & Mandkola | 2958 & 2808 | 05.02.2021 | 0.66 |
|  |  |  |  |  |  | **Sub Total** | **1.61** | **1.27** | **12** | **7** | **3** | **2** |

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr.**  **No.** | **Name of District** | **Name of MLA** | **Name of Constituency** | **No. of Villages** |  | **Sanctioned Date** | **Sanctioned Amt.**  **(Rs.in crore)** | **Expenditure Amt. (Rs.in crore)** | **Total No. of works**  **Sanctioned** | **Works Completed** | **Works-In- Progress** | **Yet to Start** |
| 13 | Faridabad | Sh.Neeraj Sharma | NIT Faridabad | (3 villages) Gothra Mohabatabad, Madalpur, Kureshipur | 3396, 1944, 2166 | 8.2.2021 | 0.75 | 0.25 | 4 | 1 | 2 | 1 |
|  | Faridabad | Sh.Neeraj Sharma | NIT Faridabad | Dhauj |  | 31.03.2021 | 0.81 | 0.16 | 1 | 0 | 1 | 0 |
|  |  |  |  |  |  | **Sub Total** | **1.56** | **0.41** | **5** | **1** | **3** | **1** |
| 14 | Faridabad | Sh.Mool Chand Sharma | Ballabgarh | Aterna | 3878 | 25.02.2021 | 0.37 | 0.09 | 6 | 2 | 2 | 2 |
|  | Faridabad | Sh.Mool Chand Sharma | Ballabgarh | (2 villages) Junhera, Garhkhera | 2544, 3878 | 18.03.2021 | 0.88 | 0.33 | 8 | 4 | 4 | 0 |
|  | Faridabad | Sh.Mool Chand Sharma | **Ballabgarh Const. (villages identified of Prithala Const. being Ballabgarh urban Const.)** | Ladholi | 2225 | 29.03.2022 | 0.38 | 0.00 | 1 | 0 | 0 | 1 |
|  |  |  |  |  |  | **Sub Total** | **1.63** | **0.42** | **15** | **6** | **6** | **3** |
| 15 | Faridabad | Sh.Rajesh Nagar | Tigaon | Gharoda, Kaurali | 2028, 4089 | 25.02.2021 | 0.78 | 0.40 | 2 | 0 | 1 | 1 |
|  | Faridabad | Sh.Rajesh Nagar | Tigaon | Adhana Patti Tigaon | 10000 | 29.03.2022 | 0.94 | 0.00 | 1 | 0 | 1 | 0 |
|  |  |  |  |  |  | **Sub Total** | **1.73** | **0.40** | **3** | **0** | **2** | **1** |
| 16 | Faridabad | Smt.Seema Trikha | **Badkhal Const. (villages identified of NIT Faridabad Const. being Badkhal urban Const.)** | Nekpur, Paota, Mangar | 1290, 2820, 1965 | **29.03.2022** | **1.33** | **0.30** | **12** | **3** | **6** | **3** |
|  | Faridabad | Smt.Seema Trikha | **Badkhal Const. (villages identified of Tigaon Const. being Badkhal urban Const.)** | Badrola | 2970 | **29.03.2022** | **0.37** | **1** | **1** | **0** | **0** |
|  |  |  |  |  |  | **Sub Total** | **1.70** | **0.30** | **13** | **4** | **6** | **3** |
|  |  |  |  |  |  | **Total** | **10.22** | **4.50** | **68** | **34** | **24** | **10** |
| 17 | Fatehabad | Sh.Dura Ram | Fatehabad | (8 villages) Barseen, Basti Bhima, Banawali, Bhattu, Ramsara, Sinthla, Nehla & Bhattu Mandi | More than 10000 | 28.09.2020 | 0.95 | 0.95 | 8 | 8 | 0 | 0 |
|  | Fatehabad | Sh.Dura Ram | Fatehabad | (12 villages) Khara Kheri, MP Rohi-I, MP-Rohi-2, Chinder, Dhani Majra, Salam Khera, Dharnia, Bhattu Mandi, Mehwala, Dhani Gopal, Baijalpur | More than 10000 | 1.12.2020 | 1.05 | 1.05 | 12 | 12 | 0 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **2.00** | **20** | **20** | **0** | **0** |

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr.**  **No.** | **Name of District** | **Name of MLA** | **Name of Constituency** | **No. of Villages** |  | **Sanctioned Date** | **Sanctioned Amt.**  **(Rs.in crore)** | **Expenditure Amt. (Rs.in crore)** | **Total No. of works**  **Sanctioned** | **Works Completed** | **Works-In- Progress** | **Yet to Start** |
| 18 | Fatehabad | Sh.Laxman Napa | Ratia | (12 villages) Haroli, Noorki Ahli, MadH, Jallopur, Lali, Nagpur, Khai, Nangal, Lamba, Kanana, Dariyapur, Bhirdana | More than 10000 | 13.10.2020 | 2.00 | 1.49 | 27 | 14 | 1 | 12 |
| 19 | Fatehabad | Sh.Subash Barala | Tohana | Samain | 10892 | 02.08.2019 | 1.00 | 0.78 | 17 | 7 | 0 | 10 |
|  | Fatehabad | Sh.Devender Babli | Tohana | (5 villages) Jandli Kalan, jandli Khurd, Bosti, Haiderwala,  Dher | 5212, 4670, 5405,  1440, 1755 | 25.02.2021 | 1.00 | 0.80 | 8 | 7 | 0 | 1 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.57** | **25** | **14** | **0** | **11** |
|  |  |  |  |  |  | **Total** | **6.00** | **5.06** | **72** | **48** | **1** | **23** |
| 20 | Gurugram | Sh.Satya Prakash Jrawta | Pataudi | (2 villages) Nanu Kalan & Khod | 4095 & 4933 | 03.12.2020 | 1.24 | 0.53 | 9 | 3 | 4 | 2 |
| 21 | Gurugram | Sh.Sanjay Singh | Sohna | (3 villages) Sarmathla, Hazipur, Garhi Wajidpur | 2377, 1876, 2719 | 04.02.2021 | 1.40 | 0.29 | 4 | 0 | 4 | 0 |
| 22 | Gurugram | Sh.Rakesh Daultabad | Badshahpur | (5 villages) Kherki, Makrola, Saketpur, Mubarakpur, Judola | 1648,2378, 1657,  2944, 2641 | 08.02.2021 | 2.00 | 0.97 | 16 | 8 | 5 | 3 |
|  |  |  |  |  |  | **Total** | **4.65** | **1.79** | **29** | **11** | **13** | **5** |
| 23 | Hisar | Sh.Anoop Dhanak | Uklana | (6 villages) Pabda, Bhada Kheda, Panihari, Badhawad, Matloda & Sarheda | More than 10000 | 03.01.2020 | 0.98 | 0.98 | 12 | 12 | 0 | 0 |
|  | Hisar | Sh.Anoop Dhanak | Uklana | (8 villages) Sarsana, Badha Khera, Matloda, Bhanbhori, Surhera, Kumbha Khera, Kharkara , Panihari | More than 10000 | 11.03.2020 | 0.75 | 0.75 | 12 | 12 | 0 | 0 |
|  | Hisar | Sh.Anoop Dhanak | Uklana | (4 villages) Landheri, Panihari, Kirori & Faridpur | More than 10000 | 19.03.2020 | 0.27 | 0.27 | 3 | 3 | 0 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **2.00** | **27.00** | **27.00** | **0.00** | **0.00** |
| 24 | Hisar | Sh.Jogi Ram Sihag | Barwala | (11 villages) Kharkri, PanaMharana (Mirjapur), Mayar, Satrod Kalan, Ladwa, Alipur, Niyana, Dhansu, Dhani Khan Bahadur, Sarsoud, Juglan | More than 10000 | 20.02.2020 | 2.00 | 1.61 | 11 | 10 | 1 | 0 |
| 25 | Hisar | Sh.Ranbir Singh Gangwa | Nalwa | (3 villages) Daya, Shahpur, Kirtan | More than 10000 | 13.03.2020 | 2.00 | 1.90 | 21 | 19 | 2 | 0 |
| 26 | Hisar | Sh.Vinod Bhayana | Hansi | (19 villages)Bara Jaggamal, Kheri Gagan, Kumbha, Kanwari, Hazampur, Dhani Pirwali, Dhani Kumharan, Muzadpur, Channot, Bhatla, Mamanpura, Dhani Kundanpur, Dhana khurd, Dhamana, Rampura, Jamawari, Bhatol Jatan, Bhatol Rangran, Dhani Peeran | More than 10000 | 11.12.2020 | 2.00 | 1.86 | 21 | 20 | 0 | 1 |
| 27 | Hisar | Dr.Kamal Gupta | Hisar **(villages identified of Barwala Const. being Hisar urban const.)** | Kharar | 4789 | 21.01.2021 | 0.50 | 0.88 | 3 | 3 | 0 | 0 |
|  | Hisar | Dr.Kamal Gupta | Hisar **(villages identified of Barwala Const. being Hisar urban const.)** | (8 villages) Satrod Kalan, Mirjapur, Mirkan, Bahbalpur, Jewera, Rajli, Bichpadi, Sarsod | More than 10000 | 31.03.2021 | 1.45 | 8 | 2 | 3 | 3 |
|  |  |  |  |  |  | **Sub Total** | **1.95** | **0.88** | **11** | **5** | **3** | **3** |

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr.**  **No.** | **Name of District** | **Name of MLA** | **Name of Constituency** | **No. of Villages** |  | **Sanctioned Date** | **Sanctioned Amt.**  **(Rs.in crore)** | **Expenditure Amt. (Rs.in crore)** | **Total No. of works**  **Sanctioned** | **Works Completed** | **Works-In- Progress** | **Yet to Start** |
| 28 | Hisar | Sh.Kuldeeep Bishnoi | Adampur | (9 villages) Dhobi, Chandan Nagar, Kalirawan, Adampur, Chaudharywali, Khara Barwala,Dhani Mobbatpur, Mobbatpur, Mandi Adampur | More than 10000 | 8.2.2021 | 0.48 | 0.35 | 10 | 9 | 0 | 1 |
|  | Hisar | Sh.Kuldeeep Bishnoi | Adampur | (9 villages) Balsamand, Chandan Nagar, Mallpur, Sadalpur, Mandi Adampur, Asrwan, Kohli, Bhana, Siswal | More than 10000 | 25.02.2021 | 1.47 | 0.45 | 11 | 5 | 6 | 0 |
|  | Hisar | Sh.Kuldeeep Bishnoi | Adampur | Sadalpur |  | 29.03.2022 | 0.05 | 0.00 | 1 | 0 | 0 | 1 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **0.80** | **22** | **14** | **6** | **2** |
| 29 | Hisar | Capt.Abhimanyu | Narnaund | Puthi Samain & Petwar | More than 10000 | 30.07.2019/  07.10.2020 | 1.00 | 0.75 | 8 | 7 | 0 | 1 |
|  | Hisar | Sh.Ram Kumar Gautam | Narnaund | (8 villages) Kapro, Kheri Lochab, Petwar, Data, Gurana, Singhwa Khas, Puthi Smain, Badchapper | More than 10000 | 26.03.2021 | 1.00 | 0.33 | 11 | 5 | 5 | 1 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.09** | **19** | **12** | **5** | **2** |
|  |  |  |  |  |  | **Total** | **13.95** | **10.15** | **132** | **107** | **17** | **8** |
| 30 | Jind | Sh.Dushyant Chautala | Uchana Kalan | (2 villages) Baroda, Chhatar, | 8595, 12095 | 28.09.2020 | 1.96 | 1.81 | 17 | 15 | 1 | 1 |
|  | Jind | Sh.Dushyant Chautala | Uchana Kalan | Chattar |  | 25.01.2021 | 0.04 | 0.03 | 3 | 3 | 0 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.85** | **20** | **18** | **1** | **1** |
| 31 | Jind | Sh.Subash Gangoli | Safidon | (2 villages) Nimnabad, Malikpur | 2970, 3017 | 08.10.2020 | 0.99 | 0.99 | 25 | 25 | 0 | 0 |
|  | Jind | Sh.Subash Gangoli | Safidon | (10 villages) Dhathrath, Gangoli, Budha Khera, Bhartana, Kharak Gagar, Muana, Ramnagar, Malar, Paju Khurd, Anchara Kalan | More than 10000 | 14.01.2021 | 0.86 | 0.86 | 12 | 11 | 1 | **0** |
|  | Jind | Sh.Subash Gangoli | Safidon | Gangoli | 5579 | 01.02.2021 | 0.15 | 0.15 | 2 | 2 | 0 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **2.00** | **39** | **38** | **1** | **0** |
| 32 | Jind | Sh.Amarjeet Dhanda | Julana | (4 villages) Dhigana, Hathwala, Ponkhri Kheri, Rajpura | 4882, 4074, 3616,  4864 | 11.12.2020 | **1.94** | 1.65 | 25 | 22 | 3 | 0 |
|  | Jind | Sh.Amarjeet Dhanda | Julana | Siwaha |  | 25.02.2021 | **0.06** | 0.06 | 7 | 7 | 0 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.71** | **32** | **29** | **3** | **0** |
| 33 | Jind | Dr.Krishan Lal Middha | Jind | (4 villages) Roopgarh, Manoharpur, Ahirka, Intal Kalan | 4205, 3382, 4011,  3048 | 01.02.2021 | 1.58 | 1.47 | 16 | 14 | 2 | 0 |
|  | Jind | Dr.Krishan Lal Middha | Jind | Amarheri | 4298 | 08.02.2021 | 0.42 | 0.42 | 1 | 1 | 0 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.89** | **17** | **15** | **2** | **0** |
| 34 | Jind | Sh.Ram Niwas Surjakhera | Narwana | (9 villages) Jajanwala, Hatho, Khanpur, Sishar, Gurthali, Kalwan, Rasidan, Sainthali, Dhamtan Sahib | More than 10000 | 05.02.2021 | 1.55 | 1.55 | 27 | 27 | 0 | 0 |
|  | Jind | Sh.Ram Niwas Surjakhera | Narwana | (3 villages) Danoda Kalan, Dharodi, Frain Kalan | 2011, 6737, 4656 | 08.03.2021 | 0.45 | 0.45 | 4 | 4 | 0 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **2.00** | **31** | **31** | **0** | **0** |
|  |  |  |  |  |  | **Total** | **10.00** | **9.44** | **139** | **131** | **7** | **1** |
| 35 | Jhajjar | Smt.Geeta Bhukkal | Jhajjar | (4 villgaes) Bhadani, Salhawas, Birdhana, Birohar | 4076, 5964, 5181,  6436 | 14.10.2020 | 1.62 | 0.99 | 5 | 1 | 2 | 2 |
|  | Jhajjar | Smt.Geeta Bhukkal | Jhajjar | (3 villages) Bhadani, Birdhana, Salhawas | 4076, 5181, 5964 | 25.03.2021 | 0.32 | 3 | 1 | 0 | 2 |
|  |  |  |  |  |  | **Sub Total** | **1.94** | **0.99** | **8** | **2** | **2** | **4** |
| 36 | Jhajjar | Sh.Naresh Kaushik | Bahadurgarh | Bamnoli | 5141 | 10.09.2019 | 1.00 | 1.00 | 3 | 3 | 0 | 0 |
|  | Jhajjar | Sh.Rajender Singh Joon | Bahadurgarh | (9 villages) Assoda Siwan, Bamnoli, Jakhoda, Kheri Jassor, Kanonda, Ladrawan, Noona Majra, Nilothi, Parnala | More than 10000 | 18.03.2021 | 1.00 | 0.25 | 13 | 9 | 2 | 2 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.25** | **16** | **12** | **2** | **2** |

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr.**  **No.** | **Name of District** | **Name of MLA** | **Name of Constituency** | **No. of Villages** |  | **Sanctioned Date** | **Sanctioned Amt.**  **(Rs.in crore)** | **Expenditure Amt. (Rs.in crore)** | **Total No. of works**  **Sanctioned** | **Works Completed** | **Works-In- Progress** | **Yet to Start** |
| 37 | Jhajjar | Sh.Om Parkash Dhankar | Badli | Patoda | 7447 | 03.09.2019 | 1.00 | 1.00 | 3 | 3 | 0 | 0 |
|  | Jhajjar | Sh.Kuldeep Vats | Badli | (3 villages) Silani Kesho, Silani Zalim, Jahangirpur | 3297, 3246, 4990 | 18.03.2021 | 1.00 | 0.34 | 13 | 4 | 2 | 7 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.34** | **16** | **7** | **2** | **7** |
| 38 | Jhajjar | Dr.Raghuvir Singh Kadian | Beri | (18 villages) Rohad, Matan, Rewari Khera, Barhana, Jahazgarh, Malikpur, Dubaldhan (G), Dimana, Chamanpura, Silothi, Palra, Baghpur, Wazirpur | More than 10000 | 18.03.2021 | 1.72 | **0.49** | 18 | 6 | 3 | 9 |
|  |  |  |  |  |  | **Total** | **7.66** | **4.06** | **58** | **27** | **9** | **22** |
| 39 | Karnal | Sh.Harwinder Singh Kalyan | Gharaunda | (9 villages) NaglaMegha, Jamalpur, Kutail, Arainpura, Kohand, Dinger Majra, GarhiBharal(Kashyap), Devipura, NalviKalan | More than 10000 | 10.09.2019 | 1.00 | 1.00 | 11 | 11 | 0 | 0 |
|  | Karnal | Sh.Harvinder Singh Kalyan | Gharaunda | (4 villages) Arainpura, Bastara, Kutail & Mohidinpur | More than 10000 | 12.03.2020/  08.10.2020 | 1.00 | 0.72 | 8 | 5 | 1 | 2 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.72** | **19** | **16** | **1** | **2** |
| 40 | Karnal | Sh. Bakhshish Singh Virk | Assandh | Jalmana | 5864 | 01.07.2019 | 1.00 | 0.94 | 19 | 19 | 0 | 0 |
|  | Karnal | Sh.Shamsher Singh Gogi | Assandh | (8 villages) Popran, Bahri, Phaphrana, Dupedi, Khizrabad,  Dera Gama, Jai Singhpura, Thari | More than 10000 | 12.03.2020/  08.10.2020 | 1.00 | 0.56 | 11 | 4 | 6 | 1 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.51** | **30** | **23** | **6** | **1** |
| 41 | Karnal | Sh. Bhagwan Dass Kabir Panthi | Nilokheri | (12 villages) Sawant, Mohri Jagir, Dadupur, Sholo, Jamba, Sitamai, Seedpur, Khawajamedpur, Kamalpur, Haibatpur, Abli Khalsha, Kamalpur | More than 10000 | 20.09.2019/  07.10.2020 | 1.00 | 0.47 | 16 | 7 | 0 | 9 |
|  | Karnal | Sh.Dharampal Gonder | Nilokheri | (10 villages) Gittalpur, Kamalpur, Mohri Jagir, Sagga, Sounkra, Pujam, Bastli, Brass, Ranjeet Nagar & Guniana | More than 10000 | 19.03.2020/  07.10.2020 | 1.00 | 0.67 | 8 | 3 | 4 | 1 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.13** | **24** | **10** | **4** | **10** |
| 42 | Karnal | Sh.Karan Dev Kamboj | Indri | 2 villages (Jattpura, Kurak Jagir) | 3365 | 20.09.2019/  07.10.2020 | 0.63 | 0.26 | 13 | 9 | 1 | 3 |
|  | Karnal | Sh.Ram Kumar Kashyap | Indri | (8 villages) Garhi Birbal, Garhi Birbal (Kharak), Gorgarh, Khanpur, Rasulpur, Umarpur, Jattpura & Nagala Roran | More than 10000 | 12.03.2020/  24.11.2020 | 1.37 | 0.61 | 14 | 5 | 7 | 2 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **0.87** | **27** | **14** | **8** | **5** |
| 43 | Karnal | Sh.Manohar Lal Khattar | Karnal | (6 villages) Pundrak, Rattangarh, Kalampura, Kachwa,  Dabri, Zarifabad | More than 10000 | 25.03.2021 | 2.00 | 1.29 | 23 | 3 | 19 | 1 |
|  |  |  |  |  |  | **Total** | **10.00** | **6.52** | **123** | **66** | **38** | **19** |
| 44 | K/Shetra | Sh.Sandeep Singh | Pehowa | (21 villages) Bhatt Majra, Zulmat, Talheri, Sandhola , Arnaicha, Dera Fateh Singh, Thana, Kheri Shishgran, Diwana, Murtzapur, Seonsar, Kakrala Gujjaran, Harigarh Bhorakh, Dera Khara Ssingh, Satora, Dhoolgarh, Dunia Majra, Bilochpura, Bhorsaidin, Nanakpura, Jalbehra | More than 10000 | 18.02.2020 | 2.00 | 2.00 | 28 | 28 | 0 | 0 |
| 45 | Kurukshetra | Sh. Subhash Sudha | Thanesar | Mirzapur | 5490 | 30.07.2019 | 0.99 | 0.99 | 10 | 10 | 0 | 0 |
|  | K/Shetra | Sh.Subash Sudha | Thanesar | (5) Rao Garh, Amargarh Majhra, Partapgarh, Amin & Kheri  Markanda | More than 10000 | 11.03.2020/  08.10.2020 | 1.01 | 0.85 | 9 | 8 | 1 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.84** | **19** | **18** | **1** | **0** |
| 46 | K/Shetra | Sh.Mewa Singh | Ladwa | 38 villages | More than 10000 | 28.09.2020 | 1.95 | 1.90 | 48 | 48 | 0 | 0 |
|  | K/Shetra | Sh.Mewa Singh | Ladwa | Bhootmajra |  | 25.01.2021 | 0.04 | 0.04 | 1 | 1 | 0 | 0 |
|  | K/Shetra | Sh.Mewa Singh | Ladwa | Kalal Majra |  | 25.02.2021 | 0.01 | 0.01 | 1 | 1 | 0 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.96** | **50** | **50** | **0** | **0** |

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr.**  **No.** | **Name of District** | **Name of MLA** | **Name of Constituency** | **No. of Villages** |  | **Sanctioned Date** | **Sanctioned Amt.**  **(Rs.in crore)** | **Expenditure Amt. (Rs.in crore)** | **Total No. of works**  **Sanctioned** | **Works Completed** | **Works-In- Progress** | **Yet to Start** |
| 47 | Kurukshetra | Sh.Krishan Kumar Bedi | Shahbad | (9 villages) Saidpur Barwalia, Patti Sahzadpur, Raipur Rai Majra, Ajrana Kalan, Sarai Sukhi, Buhawa, Ajrani, Dhurala, Adhon | More than 10000 | 09.07.2019 | 0.65 | 0.65 | 13 | 13 | 0 | 0 |
|  | Kurukshetra | Sh.Krishan Kumar Bedi | Shahbad | (7 villages) Katalahri, Mohri, Ahmedpur, Rewa, Macchaurali, Buhawa, Berthali, | More than 10000 | 02.08.2019 | 0.35 | 0.29 | 7 | 6 | 1 | 0 |
|  | Kurukshetra | Sh.Ramkaran | Shahbad | (12 villages) Chanarthal, Dholamajra, Saidpur Barwalia, Kharindwa, Mohri, Sulkhani, Tangor, Teora , Fatehgarh Jhorli/Jhorli Kalan, Fatehgarh Jhorli/ Jhorli Kalan, Yari, Arjana Khurd | More than 10000 | **25.02.2021** | **1.00** | **0.53** | **24** | **19** | **1** | **4** |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.47** | **44** | **38** | **2** | **4** |
|  |  |  |  |  |  | **Total** | **8.00** | **7.27** | **141** | **134** | **3** | **4** |
| 48 | Kaithal | Sh.Dinesh Kaushik | Pundri | Sirsal & Teontha | More than 10000 | 02.08.2019 | 1.00 | 0.99 | 14 | 14 | 0 | 0 |
|  | Kaithal | Sh.Randhir Singh Gollen | Pundri | (5 villages) Barsana, Habri, Kheri Sikander, Sangroli & Pai | More than 10000 | 24.01.2020 | 1.00 | 1.00 | 13 | 13 | 0 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.99** | **27** | **27** | **0** | **0** |
| 49 | Kaithal | Sh.Jai Parkash | Kalayat | Serdha | 8163 | 16.09.2019 | 0.39 | 0.38 | 3 | 3 | 0 | 0 |
|  | Kaithal | Sh.Jai Parkash | Kalayat | Saran | 1367 | 20.09.2019 | 0.27 | 0.24 | 3 | 3 | 0 | 0 |
|  | Kaithal | Smt.Kamlesh Dhanda | Kalayat | (23 villages) Roherian, Titram, Chandana, Kakut, Ramgarh Pandwa, Balu Gadra, Sinand, Haripura, Dhundwa, Badsikri Khurd, Sinand, Kurar, Batta, Bhalang, Kaliram, Kasan, Galiyana, Songal, Rohera, JakholiDabdal, Jakholi Kaman, Birthebhari, Mandwal | More than 10000 | 12.03.2020/  21.09.2020 | 1.30 | 1.01 | 25 | 17 | 5 | 3 |
|  | Kaithal | Smt.Kamlesh Dhanda | Kalayat | Rohera |  | 18.03.2021 | 0.04 | 0.04 | 1 | 1 | 0 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.68** | **32** | **24** | **5** | **3** |
| 50 | Kaithal | Sh.Randeep Singh Surjewala | Kaithal | Kutubpur , Dillonwali, SangatPura , Malkheri, Sirta, Manas Patti , Baba Ladana , Nouch, Ujhana, Sajuma, Kathwar , Guhna , Dhons, Dayohra, Sirta , Budhakhera, Shakti Nagar , Deodkheri, Patti Khot, Padla | More than 10000 | 10.09.2019 | 1.00 | 1.00 | 14 | 14 | 0 | 0 |
|  | Kaithal | Sh.Leela Ram Gurjar | Kaithal | (3 Villages) Kathwar, Dhons & Deyora | 3782, 3507, 4954 | 28.09.2020 | 1.00 | 1.00 | 15 | 15 | 0 | **0** |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **2.00** | **29** | **29** | **0** | **0** |
| 51 | Kaithal | Sh.Kulwant Singh Bazigar | Guhla | (18 villages) Tatiana, Mengra, Bhuna, Baupur, Landheri, Theh Banhera, Umedpur, Majri , Ramdasspura, Khanpur, Kangthali, Gohran, Kekyor Majra , Pissol, Parbhawat, Kheri Gulam Ali, Malikpur, Siwan | More than 10000 | 10.09.2019 | 1.00 | 1.00 | 12 | 12 | 0 | 0 |
|  | Kaithal | Sh.Ishwar Singh | Guhla | (9 villages)Sarola, Tarawali, Parbhot, Kharkan, Nangal, Kakrala Anayat, Ladana Chaku, Ajit Nagar, Polad | More than 10000 | 13.10.2020 | 1.00 | 1.00 | 28 | 28 | 0 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **2.00** | **40** | **40** | **0** | **0** |
|  |  |  |  |  |  | **Total** | **7.99** | **7.66** | **128** | **120** | **5** | **3** |

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr.**  **No.** | **Name of District** | **Name of MLA** | **Name of Constituency** | **No. of Villages** |  | **Sanctioned Date** | **Sanctioned Amt.**  **(Rs.in crore)** | **Expenditure Amt. (Rs.in crore)** | **Total No. of works**  **Sanctioned** | **Works Completed** | **Works-In- Progress** | **Yet to Start** |
| 52 | M/Garh | Dr.Abhe Singh Yadv | Nangal Chodhary | (11) Janipur,Nangal Kaliya, Amarpura,Thanwas,Nangal Sodha,Rai Milakpur, Kultajpur, Goad, Maksaudpur, Dhanota, Thana | More than 10000 | 10.09.2019 | 1.00 | 1.00 | 17 | 17 | 0 | 0 |
|  | M/Garh | Dr. Abhe Singh Yadav | Nangal Chaudhary | (13 villages) Bayal, Islampra, Nangal Durgu, Bigopur, Basirpur, Azmabad Mokhuta, Maghot Hala, Dholda, Banihari, Dhani Prema (Niyamatpur), Morund, Nayan, Nagal Soda | More than 10000 | 12.03.2020/  1.12.2020 | 1.00 | 0.92 | 13 | 12 | 1 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.92** | **30** | **29** | **1** | **0** |
| 53 | M/Garh | Smt.Santosh Yadav | Ateli | (2 villages) Kakrala, Bihali, | More than 10000 | 06.09.2019 | 1.00 | 1.00 | 16 | 16 | 0 | 0 |
|  | M/Garh | Sh.Sita Ram Yadav | Ateli | (5 villages) Ateli, Bazar, Chandpura, Ganiyar, Sujapur | 1373, 1251, 1846,  2778, 1187 | 12.03.2020/  1.12.2020 | 1.00 | 1.00 | 6 | 6 | 0 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **2.00** | **22** | **22** | **0** | **0** |
| 54 | M/Garh | Sh.Ram Bilas Sharma | M/Garh | (2 villages) Chitlang, Nanwan | More than 10000 | 06.09.2019 | 1.00 | 1.00 | 7 | 7 | 0 | 0 |
|  | M/Garh | Sh.Rao Dan Singh | M/Garh | (20) Nangal Harnath, Buchawas, Jhasawas, Basdi, Bass, Majra Khurd, lawan, Majra Kalan, Malra Sarai, Kheri, Bucholi, Patharwas, Aakoda, Gadadwas, Jat, Kheri, Nihalawas, Riwasha, Gadania. | More than 10000 | 3.12.2020 | 1.00 | 0.95 | 21 | 10 | 11 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.95** | **28** | **17** | **11** | **0** |
| 55 | M/Garh | Sh.Om Parkash Yadav | Narnaul | (9 villages) Dublana, Rampura, Nangal Khatha, Seka, Mohenpur Hamidhka, Dohar Khurd, Deroli Ahir, Sihma, Guawani | More than 10000 | 16.12.2020 | 2.00 | 1.55 | 9 | 6 | 3 | 0 |
|  |  |  |  |  |  | **Total** | **8.00** | **7.42** | **89** | **74** | **15** | **0** |
| 56 | Mewat | Sh.Aftab Ahmed | Nuh | (17 villages) Tapkan, Badka, Udaka, Atta, Maroda,Kalinjar, Raipuri, Hussainpur (Satputiyaka), Muradbass, Khanpur (Raisika), Paldi, Ghaseda, Salahedi, Basai, Alawalpur, Mewli, Akeda | More than 10000 | 13.10.2020 | 2.00 | 1.93 | 21 | 21 | 0 | 0 |
| 57 | Mewat | Sh.Mohd.Iliyas | Punhana | (10 villages)Sultanpur Punhana, Pingwan, Siroli, Piproli, Jakhopur , Neemka, Hajipur, Jamalgarh, Mubarikpur, Naharpur | More than 10000 | 13.10.2020 | 2.00 | 1.79 | 21 | 19 | 2 | 0 |
| 58 | Nuh (Mewat) | Sh.Naseem Ahmed | Ferozepur Jhirka | Nagina | 11417 | 02.08.2019 | 1.00 | 1.00 | 8 | 8 | 0 | 0 |
|  | Mewat | Sh.Mamman Khan | Ferozepur Jhirka | (18 villages) Sakras,Patanudaypuri, Pathkhori,Ranyala Patakpur, Mahu, Dholi G.P. Neemakhera, Sulatanpur Nuh, Nagina, Bajidpur, Dungeja Dhana, Kherdli Khurd, Raniyala, Khanpur Ghatti, Dhadoli Kalam, Dhadola, Jhimrawat, Khedla Khurd | More than 10000 | 21.01.2021 | 1.00 | 0.93 | 20 | 19 | 1 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.93** | **28** | **27** | **1** | **0** |
|  |  |  |  |  |  | **Total** | **6.00** | **5.65** | **70** | **67** | **3** | **0** |
| 59 | Panipat | Sh.Dharam Singh Chhoker | Samalkha | (2 villages) Kiwana, Narayana | 8136, 7305 | 21.12.2020 | 1.88 | 1.71 | 13 | 9 | 4 | **0** |
| 60 | Panipat | Sh.Balbir Singh Balmiki | Israna | (3 villages) Dumiyana, Sutana, Shahpur | 1424, 6268, 3472 | 04.02.2021 | 1.75 | 0.06 | 16 | 2 | 13 | 1 |
|  | Panipat | Sh.Balbir Singh Balmiki | Israna | Sutana | 6268 | 29.03.2022 | 0.25 | 0.00 | 8 | 0 | 0 | 8 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **0.06** | **24** | **2** | **13** | **9** |

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr.**  **No.** | **Name of District** | **Name of MLA** | **Name of Constituency** | **No. of Villages** |  | **Sanctioned Date** | **Sanctioned Amt.**  **(Rs.in crore)** | **Expenditure Amt. (Rs.in crore)** | **Total No. of works**  **Sanctioned** | **Works Completed** | **Works-In- Progress** | **Yet to Start** |
| 61 | Panipat | Sh.Mahipal Dhanda | Panipat Rural | (3 villages) Palheri, Risalu, Kutani | 1893, 3722, 2684 | 26.03.2021 | 0.44 | 0.24 | 7 | 5 | 0 | 2 |
|  | Panipat | Sh.Mahipal Dhanda | Panipat Rural | Shimla Molana |  | 31.03.2021 | 0.36 | 0.00 | 1 | 0 | 1 | 0 |
|  |  |  |  |  |  | **Sub Total** | **0.79** | **0.24** | **8** | **5** | **1** | **2** |
| 62 | Panipat | Sh.Parmod Kumar Vij | **Panipat City Constituency (against Panipat Rural Constituency being Panipat City urban Constituency)** | Assan Kalan | 6150 | **31.03.2022** | **0.99** | **0.00** | **5** | **0** | **0** | **5** |
|  |  |  |  |  |  | **Total** | **5.66** | **2.01** | **50** | **16** | **18** | **16** |
| 63 | Panchkula | Sh.Pardeep Chaudhary | Kalka | (41) Gorkhnath, Thane ki Sair, Kaniyala, Khoi, Jholuwal, Chikan, Kedarpur, Bhoj Balak, Thandog, Bhoj Rajpura, Bhoj Kothi, Sabilpur, Thapli, Raipurrani, Firozpur, Sarakpur, Bharoli, Ganoli, Debar, Mouli, Rattadibbi, Gobindpur, Mandlia, Bhanvli, Hangola, Sultanpur, Sahjahpur, Mirpur, Rehna, Baghwala, Rampur, Kakrali, Samanva, Kambala (Tapria Barwala), Hangoli, Narainpur, Khairwali Parwala, Shahpur, Tapriyan, | More than 10000 | 17.03.2020 | 1.87 | 1.87 | 38 | 38 | 0 | 0 |
|  | Panchkula | Sh.Pardeep Chaudhary | Kalka | (5 villages) Jaspur, Samlehri, Bhud, Badhaur, Mandlai | 805, 1283, 399, 1790,  811 | 1.12.2020 | 0.13 | 0.12 | 3 | 3 | 0 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **2.00** | **41** | **41** | **0** | **0** |
| 64 | Panchkula | Sh.Gian Chand Gupta | Panchkula | (4 villages) Shamtoo, Dhandaurru, Boonga, Tibbi | 1886, 1149, 1725,  1153 | 14.10.2020 | 1.22 | 1.22 | 22 | 22 | 0 | 0 |
|  | Panchkula | Sh.Gian Chand Gupta | Panchkula | (2 villages) Rattewali, Khetpurali | 2812, 986 | 25.02.2021 | 0.78 | 0.78 | 10 | 10 | 0 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **2.00** | **32** | **32** | **0** | **0** |
|  |  |  |  |  |  | **Total** | **4.00** | **3.99** | **73** | **73** | **0** | **0** |
| 65 | Palwal | Sh.Karan Singh Dalal | Palwal | (8 villages) Ghori, Chandhat, Mala Singh Farm, Dhatir,  Rajolaka, Bela, Atohan, Bilochpur | More than 10000 | 02.08.2019 | 1.00 | 1.00 | 9 | 9 | 0 | 0 |
|  | Palwal | Sh.Deepak Mangla | Palwal | (2 villages) Asawta, Tikri Gurjar | 3857, 1979 | 13.10.2020 | 0.89 | 0.89 | 11 | 9 | 2 | 0 |
|  | Palwal | Sh.Deepak Mangla | Palwal | Asawta | 3857 | 4.12.2020 | 0.10 | 0.10 | 1 | 1 | 0 | 0 |
|  | Palwal | Sh.Deepak Mangla | Palwal | Bagpur |  | 25.01.2021 | 0.01 | 0.01 | 1 | 1 | 0 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **2.00** | **22** | **20** | **2** | **0** |
| 66 | Palwal | Sh.Praveen Dagar | Hathin | Mandkola | 10773 | 26.02.2020/  1.12.2020 | 2.00 | 0.00 | 1 | 0 | 1 | 0 |
| 67 | Palwal | Sh.Jagdish Nayar | Hodal | Pingaltu, Godhota, Khambi | 4315,4855, 7769 | 25.02.2021 | 1.99 | 0.49 | 13 | 5 | 8 | 0 |
|  |  |  |  |  |  | **Total** | **5.99** | **2.49** | **36** | **25** | **11** | **0** |
| 68 | Rohtak | Sh.Balraj Kundu | Meham | (8 villages) Lakhan Majra, Sundarpur, Garavathi, Gugaheri, Bahu Akbarpur, Samar Gopalpur, Singpura Kalan, Bhagvatipur, | More than 10000 | 04.03.2020/  08.10.2020 | 2.00 | 2.00 | 16 | 16 | 0 | 0 |
| 69 | Rohtak | Smt.Shakuntla Khatak | Kalanaur | Baland | 7129 | 13.10.2020 | 0.53 | 0.53 | 3 | 3 | 0 | 0 |
|  | Rohtak | Smt.Shakuntla Khatak | Kalanaur | (10 vilages)Karontha, Ritauli, Kharawar, Saimpal, Nigana, Patwapur, Masudpur, Pilana, Ballab, Karor, Kharawar | More than 10000 | 8.12.2020 | 1.47 | 1.47 | 17 | 17 | 0 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **2.00** | **20** | **20** | **0** | **0** |

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr.**  **No.** | **Name of District** | **Name of MLA** | **Name of Constituency** | **No. of Villages** |  | **Sanctioned Date** | **Sanctioned Amt.**  **(Rs.in crore)** | **Expenditure Amt. (Rs.in crore)** | **Total No. of works**  **Sanctioned** | **Works Completed** | **Works-In- Progress** | **Yet to Start** |
| 70 | Rohtak | Sh.Bharat Bhushan Batra | Rohtak **(villages identified of Kalanaur Const. being Rohtak urban const.)** | (10 villages) Dobh/Baniyani, Jindran, Kherari, Lahali, Kakrana, Ballab, Basana, Marodhi Rangdha, Anwal, Nigana | More than 10000 | 3.12.2020 | 2.00 | 2.00 | 9 | 9 | 0 | 0 |
| 71 | Rohtak | Sh.Bhupinder Singh Hooda | Garhi-Sampla-Kiloi | (18 villages) Khidwali, Katwara, Sanghi, Ladhot, Kansala, Bakheta, Assan, Ismaila-II, Ghuskani, Bhiyanpur, Ghilor Kalan, Garhi Sampla, Morkheri, Brahamanwas, Dhamer, Humayunpur, Chuliyana Duhan | More than 10000 | 8.12.2020 | 2.00 | 2.00 | 22 | 22 | 0 | 0 |
|  |  |  |  |  |  | **Total** | **8.00** | **8.00** | **67** | **67** | **0** | **0** |
| 72 | Rewari | Dr.Banwari Lal | Bawal | (19 villages) Bidawas, Tankri, Nangli Parsapur, Mangleshwar , Dharan, Khandoda, Bishanpur, Chirhara, Tihara , Pranpura, Suthana, Nandrampur Bass, Bhatwas, Khijuri, Bhatsana , Dhani Sundroj, Kolana, Khatela, Mailawas | More than 10000 | 10.09.2019 | 1.00 | 1.58 | 8 | 7 | 0 | 1 |
|  | Rewari | Dr.Banwari Lal | Bawal | (16 villages) Keshopur, Ramsingpura, Rajpura Istmurar, Shbazpur Istmurar, Nagal Jamalpur, Khaleta, Nandha, Cheetadungra, Dhani Bhandor, Basduda, Tint, Bhalkhi Majra, Dhani Sobha, Rampura, Nandrampur Bas, Devlawas | More than 10000 | 18.03.2020/  08.10.2020 | 1.00 | 8 | 6 | 1 | 1 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.58** | **16** | **13** | **1** | **2** |
| 73 | Rewari | Sh.Laxman Singh yadav | Kosli | (21 villages) Bahlaa, Bawwa, Bhakli-I, Garhi, Gujarwas, Jharauda, Karoli, Khurshid Nagar, Kosli, Lilodh, Lukhi, Lula Ahir, Rattan Sathal, Musepur, Nangal Pathani, Nangal, Bhagwanpur (Nangal), Kahri, Kheri (Ramgarh), Ramgarh, Rampuri | More than 10000 | 18.03.2020/  08.10.2020 | 2.00 | 1.62 | 26 | 20 | 1 | 5 |
| 74 | Rewari | Sh.Chiranjeev Rao | Rewari | (12 villages) Hansaka, Meerpur, Chiller, Gokulgarh, Saharanwas, Fetehpuri , Turkiyawas, Ramgarh, Bhagwanpur, Kaluwas, Ghatal Mahaniawas, Dhakia | More than 10000 | 08.02.2021 | 1.98 | 0.27 | 19 | 4 | 8 | 7 |
|  |  |  |  |  |  | **Total** | **5.98** | **3.48** | **61** | **37** | **10** | **14** |
| 75 | Sonepat | Sh.Jagbir Singh Malik | Gohana | (7 villages) Bohla, Bhutana, Jafrabad, Juan-I, Pinana, Jauli, Lath & Mehalana | More than 10000 | 20.03.2020/  08.10.2020 | 1.25 | 0.75 | 13 | 9 | 3 | 1 |
|  | Sonepat | Sh.Jagbir Singh Malik | Gohana | (4 villages) Jaully, Dubheta, Bhatgaon Dungran, Bhatgaon  Malyan | 5963, 6789, 3594 | 8.12.2020 | 0.75 | 0.32 | 7 | 4 | 0 | 3 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.07** | **20** | **13** | **3** | **4** |
| 76 | Sonepat | Sh.Mohan Lal Badoli | Rai | (6 villages) Jakhauli, Akbarpur Barota, Safiyabad,  Badhmalik, Jainpur, Asadhpur | More than 10000 | 14.10.2020 | 1.35 | 0.56 | 8 | 3 | 0 | 5 |
|  | Sonepat | Sh.Mohan Lal Badoli | Rai | Ashadpur | 2695 | 8.12.2020 | 0.37 | 0.00 | 2 | 0 | 1 | 1 |
|  | Sonepat | Sh.Mohan Lal Badoli | Rai | Barauli |  | 31.03.2022 | 0.28 | 0.00 | 2 | 0 | 0 | 2 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **0.56** | **12** | **3** | **1** | **8** |
| 77 | Sonepat | Sh.Jaiveer Singh | Kharkhoda | (14 villages) Rohat, Pai, Kidoli, Barona, Jharoth, Farmana, Sisana- I, Mandora, Mandori, Sisana-II, Jharoth, Gorar, Firojpur Bangar, Naklio, Khurmpur | More than 10000 | 01.02.2021 | 2.00 | 1.95 | 17 | 13 | 4 | 0 |
| 78 | Sonepat | Smt. Nirmal Rani | Ganaur | Purkhas Rathi, Purkhas Dhiran | 3304 & 4052 | 01.02.2021 | 1.00 | 0.34 | 9 | 0 | 5 | 4 |
|  | Sonepat | Smt. Nirmal Rani | Ganaur | Panchi Jatan | 6580 | 18.03.2021 | 1.00 | 0.00 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **0.34** | **9** | **0** | **5** | **4** |

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr.**  **No.** | **Name of District** | **Name of MLA** | **Name of Constituency** | **No. of Villages** |  | **Sanctioned Date** | **Sanctioned Amt.**  **(Rs.in crore)** | **Expenditure Amt. (Rs.in crore)** | **Total No. of works**  **Sanctioned** | **Works Completed** | **Works-In- Progress** | **Yet to Start** |
| 79 | Sonepat | Sh.Indu Raj Narwal | Baroda | (8 villages) Mundlana, Jagsi Sahrawat, Bhainswal Khurad, Chhichhrana, Dhanana, Kathura, Katwal | More than 10000 | 26.03.2021 | 1.13 | 1.02 | 14 | 9 | 3 | 2 |
|  | Sonepat | Sh.Indu Raj Narwal | Baroda | (8 villages) Bhanwar Bura, Banwasa, Madina, Rindhana Jitsthar Pana , Rindhana, Ruhki Khas, Anwali, Katwal | More than 10000 | 31.03.2021 | 0.86 | 12 | 3 | 3 | 6 |
|  |  |  |  |  |  | **Sub Total** | **1.99** | **1.02** | **26** | **12** | **6** | **8** |
| 80 | Sonepat | Sh.Surender Panwar | Sonepat **(villages identified of Kharkhoda Const. being Sonepat urban const.)** | Kakroi, Harsana, Rohat | 5023, 5133, 4678 | **31.03.2022** | **0.48** | **0.00** | **5** | **0** | **0** | **5** |
|  |  |  |  |  |  | **Total** | **10.47** | **4.93** | **89** | **40** | **21** | **28** |
| 81 | Sirsa | Smt. Naina Chautala | Dabwali | (6 villages) Dabwali, Nilliawali , Panna, Panniwala Ruldu, Sawantkhera, Jandwala Jattan | More than 10000 | 03.01.2020 | 1.06 | 1.06 | 16 | 16 | 0 | 0 |
|  | Sirsa | Sh.Amit Sihag | Dabwali | (3 villages) Abubshahar, Maujghar, Odhan | 8912, 3962, 8643 | 14.10.2020 | 0.94 | 0.51 | 8 | 3 | 5 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.57** | **24** | **19** | **5** | **0** |
| 82 | Sirsa | Sh.Gopal Kanda | Sirsa | (3 villages) Jodhkan, Gadali, Rajpura Kairanwali | 7533, 1092, 2670 | 4.12.2020 | 1.21 | 1.21 | 14 | 14 | 0 | 0 |
|  | Sirsa | Sh.Gopal Kanda | Sirsa | (4 villages) Shamshabad Patti, Phulkan, Nattar , Tajjia Khera | 1190, 2614, 4619,  1989 | 08.03.2022 | 0.61 | 0.12 | 5 | 0 | 5 | 0 |
|  |  |  |  |  |  | **Sub Total** | **1.82** | **1.33** | **19** | **14** | **5** | **0** |
| 83 | Sirsa | Sh.Balkaur Singh | Kalanwali | (20 villages) Phaggu, Bhima, Sahuwala-1st, Baragudha, Thiraj, Bupp, Rori, Baragudha, Pacca Sahidan, Rohan, Sangar Srista, Ranga, Patli Dabar, Jhopra, Biruwala Gudha, Bhawdin, Raghuana, Malhri, Dhani Khuwali, Raghuana, | More than 10000 | 10.09.2019 | 1.00 | 0.93 | 13 | 12 | 0 | 1 |
|  | Sirsa | Sh.Shishpal Singh Keharwala | Kalanwali | (9 villages) Bhadra, Tilokewala, Bupp, Kurangwali, Bagguwali, Bhima, Sikanderpur, Dhani Khuwali (Dhani Majra), Jhiri, Desukhurd | More than 10000 | 8.12.2020 | 1.00 | 0.89 | 9 | 8 | 1 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.82** | **22** | **20** | **1** | **1** |
| 84 | Sirsa | Ch.Ranjit Singh | Rania | (4) Moujdeen, Nathor, Nakora, Khai Shergarh | 1935,3977,2203,  2734 | 07.12.2021 | 1.97 | 1.44 | 8 | 2 | 6 | 0 |
| 85 | Sirsa | Sh.Abhay Singh Chautala | Ellenabad | (19 villages) Rattakhera, Daya Singh Thed, Amritsar Khurd, Amritsar Kalan, Karmsana, Mojukhera, Himayukhera, Rampura Dhilon, Raipur, Gudia Khera, Kheri, Chaharwala, Ludesar, Baruwali-II, Khari Surera , Shahpuria, Bakriawali , Barasari, Sakkar Mandori | More than 10000 | 25.03.2022 | 1.93 | 1.10 | 21 | 8 | 12 | 1 |
|  | Sirsa | Sh.Abhay Singh Chautala | Ellenabad | Patti Kirpal, Chaharwala | 513, 5881 | 29.03.2022 | 0.07 | 0.00 | 2 | 0 | 0 | 2 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.10** | **23** | **8** | **12** | **3** |
|  |  |  |  |  |  | **Total** | **9.79** | **7.25** | **96** | **63** | **29** | **4** |

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr.**  **No.** | **Name of District** | **Name of MLA** | **Name of Constituency** | **No. of Villages** |  | **Sanctioned Date** | **Sanctioned Amt.**  **(Rs.in crore)** | **Expenditure Amt. (Rs.in crore)** | **Total No. of works**  **Sanctioned** | **Works Completed** | **Works-In- Progress** | **Yet to Start** |
| 86 | Y/Nagar | Sh.Shyam Singh Rana | Radour | Gumthala | 4455 | 05.07.2019 | 0.50 | 0.76 | 18 | 13 | 5 | 0 |
|  | Y/Nagar | Sh.Shyam Singh Rana | Radour | (7 villages) Potli, Palewala, Baghwangarh, Fatehgarh, Jhiverhedi, Unheri, Rajheri | More than 5000 | 02.08.2019 | 0.50 |
|  | Y/Nagar | Sh.Bishan Lal Saini | Radaur | (5 villages) Damla, Road Chhapar, Saran, Sili Khurd, Amloha | More than 10000 | 20.02.2020/  07.09.2020 | 1.00 | 0.97 | 8 | 7 | 0 | 1 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **1.73** | **26** | **20** | **5** | **1** |
| 87 | Y/Nagar | Sh.Kanwar Pal | Jagadhri | Begampur | 2198 | 20.02.2020/  07.09.2020 | 0.47 | 0.47 | 4 | 4 | 0 | 0 |
|  | Y/Nagar | Sh.Kanwar Pal | Jagadhri | Chhachrouli, Jaidhar | 12672, 4761 | 29.03.2022 | 1.53 | 0.00 | 2 | 0 | 2 | 0 |
|  |  |  |  |  |  | **Sub Total** | **2.00** | **0.47** | **6** | **4** | **2** | **0** |
| 88 | Y/Nagar | Sh.Ghanshyam Dass Arora | Yamunanagar | (5 villages) Mukarakpur, Ratanpur (Kayampura), Bibipur &  Kanalsi | More than 10000 | 12.03.2020/  07.09.2020 | 1.94 | 1.74 | 38 | 36 | 2 | 0 |
| 89 | Y/Nagar | Sh.Balwant Singh | Sadhaura | Talakaur | 3303 | 03.09.2019 | 0.22 | 0.22 | 3 | 3 | 0 | 0 |
|  | Y/Nagar | Sh.Balwant Singh | Sadhaura | Talakaur | 3303 | 10.09.2019 | 0.28 | 0.28 | 3 | 3 | 0 | 0 |
|  | Y/Nagar | Smt.Renu Bala | Sadhaura | (7 villages) Rulakheri, Mehlanwali, Ariyanwala, Satari,  Saidupur, Sangholi, Mohideenpur | More than 10000 | 14.10.2020 | 1.41 | 1.30 | 27 | 25 | 2 | 0 |
|  | Y/Nagar | Smt.Renu Bala | Sadhaura | Ariyanwala |  | 1.12.2020 | 0.07 | 0.07 | 1 | 1 | 0 | 0 |
|  |  |  |  |  |  | **Sub Total** | **1.98** | **1.87** | **34** | **32** | **2** | **0** |
|  |  |  |  |  |  | **Total** | **7.92** | **5.81** | **104** | **92** | **11** | **1** |
|  |  |  |  |  |  | **Grand Total** | **168.79** | **119.19** | **1829** | **1379** | **278** | **172** |
| **(Rs. in crore)** | | | | | | | | | | | | |
|  | **Year** | **No. of MLAs** | **Funds Sanctioned** | **Funds Utilized** | **Total Villages** | **Completed works** |  | | | | | |
| (2018-19) | 28 | 33.49 | 29.91 | 196 | 359 |
| (2019-20) | 89 | 168.79 | 119.19 | 958 | 1379 |
| **Total** |  | **202.28** | **149.10** | **1154** | **1738** |

Constituency-wise Statement showing physical and financial status of (2.00 crore) Vidhayak Adarsh Gram Yojana for the year of 2022-23

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr.**  **No.** | **Name of District** | **Name of MLA** | **Name of Constituency** | **No. of Villages** | **Sanctioned Date** | **Sanctioned Amt. (Rs.in crore)** | **Total No. of works Sanctioned** |
| **1** | M/garh | Sh.Abhay Singh Yadav | Nangal Chaudhary | 8 | 23-02-2023 | 1.50 | 10 |
| **2** | M/garh | Sh.Sita Ram Yadav | Ateli | 4 | 03-03-2023 | 1.50 | 11 |
| **Total** | | | | **12** |  | **3.00** | **21** |