**Development Works Under the VAGY**

**87**  **Sh.NEERAJ SHARMA (Faridabad NIT)**

Will the Development and Panchayats Minister be pleased to state:-

1. whether it is a fact that the villages Dhauj, Gothda Mohbtabad, Madalpur and Kureshipur were adopted under the Vidhayak Adarsh Gram Yojana in the year 2019-20 in the Faridabad NIT Assembly Constituency;
2. whether the works of development in the above said villages under the said Yojana have been completed; if so, the details of the completion certificate thereof; and
3. if not, the reasons therefore together with the time by which the above said works are likely to be completed?

**DEVENDER SINGH BABLI, DEVELOPMENT & PANCHAYATS MINISTER, HARYANA**

1. Yes Sir, it is a fact that the villages Dhauj, Gothda Mohbtabad, Madalpur and Kureshipur were adopted under the Vidhayak Adarsh Gram Yojana in the year 2019-20 in the Faridabad NIT Assembly Constituency.
2. One work of Madalpur village has been completed under the said Yojana. Details are at Annexure.
3. One work of Gothda Mohbtabad village will be completed by 31.03.2023 and remaining 2 works of Dhauj and Kureshipur villages will be completed by 30.04.2023. One work of Gothda Mohbtabad village has not been started due to site dispute.

**विधायक आदर्श ग्राम योजना के अन्तर्गत विकास कार्य**

87 **श्री नीरज शर्मा (फरीदाबाद एनआईटी):**

**क्या विकास एवं पंचायत मंत्री कृपया बताएंगे किः-**

क) क्या यह तथ्य है वर्ष 2019-20 में फरीदाबाद एन.आई.टी विधानसभा निर्वाचन क्षेत्र में विधायक आदर्श ग्राम योजना के अन्तर्गत धौज, गोठड़ा मोहबताबाद, मादलपुर तथा कुरैशीपुर गांव गोद लिए गए थे;

ख) क्या उक्त योजना के अन्तर्गत उपरोक्त गांवों में विकास कार्यों को पूरा किया गया है; यदि हां, तो उसके समापन प्रमाण-पत्र (कंप्लीशन सर्टीफिकेट) का ब्यौरा क्या है; तथा

ग) यदि नहीं, तो उसके क्या कारण हैं तथा उपरोक्त कार्यों के कब तक पूरा किए जाने की संभावना है?

**देवेंद्र सिंह बबली, विकास एवं पंचायत मंत्री, हरियाणा**

क) हां सर, यह तथ्य है वर्ष 2019-20 में फरीदाबाद एन.आई.टी विधानसभा निर्वाचन क्षेत्र में विधायक आदर्श ग्राम योजना के अन्तर्गत धौज, गोठड़ा मोहबताबाद, मादलपुर तथा कुरैशीपुर गांव गोद लिए गए थे ।

ख) उक्त योजना के अन्तर्गत मादलपुर गांव का एक कार्य पूर्ण हो चुका है, जिसका विवरण अनुबंध पर है।

ग) गोठड़ा मोहबताबाद गांव का एक कार्य 31.03.2023 तक तथा धौज तथा कुरैशीपुर गांव के शेष 2 कार्य 30.04.2023 तक पूर्ण किए जाएंगे। गोठड़ा मोहबताबाद गांव का एक कार्य जमीन विवाद के कारण शुरू नहीं हुआ है।

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Annexure** | | | | | | | |
|  | | | | | | | |
| **Vidhan Sabha Assembly un-starred question No. 14/15/110** | | | | | | | |
| **List of works under VAGY Scheme in District: Faridabad** | | | | | | | |
| **Sr. No.** | **Name of Work** | **Name of Village** | **Name of Block** | **Name of constituency** | **Expenditure**  **(Rs. In Lacs)** | **Status of work** | **Remarks** |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| 1. | IPB Street from H/o Islamuddin to H/o Pappu Suleman, Emaran to Primary School | Madalpur | FBD | NIT | 13.35 | Completed | Completed |
| 2. | Pav of streets with IPB (H/o Togri to H/o LalaNaresh, Guilya to H/o Mazid Esha, H/o Amin to H/o Mazid, PWD road Silakhari to H/o Jakir, PWD road Sohna to Kayum S/o Hatum, Azad to H/o Sattar, From H/o Saddam S/o Sattar to Ahmad S/o Hansu, from Crusher Zone to Kamru S/o Gungal) &Roof Top Solar Plant and Solor Street lights | Dhauj | FBD | NIT | 10.17 | In-Progress | This work will be completed by 30.04.2023 |
| 3. | IPB Street from H/o Satbir S/o Jairam to H/o Naresh S/o Gajraj | G.M. Baad | FBD | NIT | 0 | Not Started | This work is not started due to Site Dispute |
| 4. | Const. of Hall in C.Center | G.M. Baad | FBD | NIT | 8.59 | In- Progress | This work will be completed by 31.03.2023 |
| 5. | IPB Street from H/o Guddu to H/o JaanMohd. Miyan, Nanak Bhagatji to Hazi Ebrahim,Jakir to H/o Jamshid Asawati to H/o Hazi Hukum | Kureshipur | FBD | NIT | 8.93 | In-Progress | This work will be completed by 30.04.2023 |