**Starred Question No. \*2**

**To Construct the Railway Under Pass and ROB.**

 **Sh. JAGDISH NAYAR (Hodal) :**

Will the Deputy Chief Minister be pleased to state whether there is any proposal under consideration of the Government to construct the railway underpass and railway over bridge on the Gorauta railway crossing at Hodal road, Bhulwana railway crossing, Banchari to Dakora railway crossing, Mitrol, Deeghot, Maroli, Banchari to Gorauta railway crossings; if so, the details thereof?

-------------------------------------------------------------

**DUSHYANT CHAUTALA, DEPUTY CHIEF MINISTER, HARYANA**

 **Sir,**

 **Statement of reply to the question is laid on the table of the house.**

**Statement of reply to question no. \*14/16/582 asked by Sh. JAGDISH NAYAR (Hodal)**

|  |  |  |
| --- | --- | --- |
| **LC No.**  | **Location**  | **Status/ reply**  |
| **ROB at LC-554**  | **Gorauta railway crossing on Hodal road** | A revised GADhas been submitted to Railways on dated 12.08.2023 for approval. After approval of the GAD, DPR will be prepared and sent to the Government for according Administrative Approval |
| **ROB / RUB at LC-552**  | **Bulwana to Chamelivan road** | ROB/RUB is not feasible in this location on account of site conditions and restricted Right of Way (ROW). |
| **ROB at LC-556-A Spl**  | **Banchari to Dakora road** | ROB in this location is being taken up by Railways at their own level. |
| **ROB at LC-560 Spl.**  | **Mitrol to Deeghot road** | ROB in this location is being taken up by Railways at their own level. |
| **ROB at LC-557-B**  | **Road from Delhi-Mathura Road to village Maroli** | GAD has been approved by the Railways on dated 27.07.2023, DPR is under preparation and will be sent to the Government for according Administrative Approval shortly. |
| **ROB / RUB at LC 556**  | **Banchari to Gorauta road** | LC 556 falls onBanchari to Gorauta road which is under the jurisdiction ofHaryana State Agriculture Marketing Board (HSAMB) and at present there is no proposal of construction of ROB / RUB at this LC on this road.  |

**EXECUTIVE SUMMARY**

1. **Construction of two lane ROB at LC-554 on Mumbai Delhi Railway track crossing on Hodal to Khambi via Pangaltu, Railway km. 1452/14-16 in Palwal District (Road from Hodal to village Gorauta).**

The GAD of ROB was sent to office of Dy. Chief Engineer/ RSW/Gwalior vide letter no. 358/HSRDC dated 15.03.2023 for approval. The GAD was re-submitted by Railways vide letter No. DYCE/CE/GSU/AGC/ROB/554 dated 08.06.2023 which has been further corrected as per site requirement in consultation with Railway Authorities and sent by the Consultant vide letter No. JCTPL/PB/HSRDC/LC-554/39156 dated 12.08.2023 for approval and approval is awaited from the Railways. After approval of GAD, Detailed Project Report will be prepared and sent to the Government for arranging Administrative Approval.

1. **Construction of ROB at LC-552 on Delhi Agra Railway line crossing Bulwana to Chamelivan road in Palwal District.**

The Right of Way (ROW) of road at the location is 33 feet before LC & less than 33 feet after level crossing towards, Chamelivan. The area in and around level crossing is thickly populated and ROB/RUB is not feasible without demolition of private structure and land acquisition.

1. **Construction of ROB at LC-556-A Spl. On Delhi Agra Railway line crossing Banchari to Dakora road in Palwal District.**

The Right of Way (ROW) of road is 33 feet. Additional land shall have to be acquired for construction of ROB. GAD for construction of ROB has been sent by Executive Engineer, Provincial Division, PWD B&R Br., Palwal vide letter no. 1568 dated 01.05.2023 to Northern Central Railway. Railways is taking up the work of construction of this ROB including land acquisition at its own level as intimated by Railways vide its letter no. AGRA/GSU/DY.CE/MISC/300 dated 21.08.2023.

1. **Construction of ROB at LC-560 on Delhi Agra Railway line crossing Mitrol to Deeghot road in Palwal District.**

The Right of Way (ROW) of road is 33 feet. Additional land shall have to be acquired for construction of ROB. GAD for construction of ROB has been sent by Executive Engineer, Provincial Division, PWD B&R Br., Palwal vide letter no. 1568 dated 01.05.2023 to Northern Central Railway. Railways is taking up the work of construction of this ROB including land acquisition at its own level as intimated by Railways vide its letter no. AGRA/GSU/DY.CE/MISC/300 dated 21.08.2023.

1. **Construction of ROB at LC-557-B on Delhi Agra Railway line crossing Delhi-Mathura Road to Maroli Road in Palwal District (Road from NH -19 to village Maroli).**

For construction of ROB at LC-557-B additional private land measuring 1.5 Acres shall have to be acquired. The GAD of proposed ROB at LC-557-B has been approved by the Chief Engineer/ Construction, AGC, Agra on dated 27.07.2023. Now DPR is under preparation and will be sent to the Government for according Administrative Approval.

1. **Construction of ROB at LC 556 on Delhi Agra Railway line crossing Banchari to Gorauta road in Palwal District.**

The Level crossing is existing on road under the jurisdiction of Haryana State Agriculture Marketing Board (HSAMB). Right of Way of the road is 22 feet. Drain is exiting after crossing of level crossing so RUB is not feasible. ROB is feasible only with acquisition of additional private land. At present there is no proposal of construction of ROB / RUB at LC 556.

**\*\*\***

तारांकित प्रश्न संख्या \*2

**रेलवे अंडर पास तथा रेलवे उपरि पुल का निर्माण करना**

 **श्री जगदीश नायर (होडल):**

 क्या उप मुख्यमंत्री कृपया बताएंगे की क्या होडल सड़क पर गोरोटा रेलवे क्रॉसिंग, भुलवाना रेलवे क्रॉसिंग, बन्चारी से डाकोरा रेलवे क्रॉसिंग, मितरोल, डीघोट, मरोली, बन्चारी से गोरोटा रेलवे क्रॉसिंग पर रेलवे उपरि पुल बनाने का कोई प्रस्ताव सरकार के विचाराधीन है; तथा यदि हां, तो उसका ब्यौरा क्या है?

-------------------------------------------------------------

**दुष्यंत चौटाला, उपमुख्यमंत्री, हरियाणा**

श्रीमान जी,

प्रश्न के उत्तर का विवरण सदन के पटल पर रखा गया है।

प्रश्न संख्या \*2 श्री जगदीश नायर (होडल) द्वारा पूछे गए प्रश्न के उत्तर का विवरण

|  |  |  |
| --- | --- | --- |
| एलसी न०  | स्थान  | स्थिति / उत्तर  |
| **एलसी-554 पर रेलवे उपरगामी पुल** | होडल रोड पर गोरौटा रेलवे क्रॉसिंग | रेलवे को संशोधित जीएडी अनुमोदन के लिए दिनांक 12.08.2023 को प्रस्तुत की गई है। जीएडी की मंजूरी के बाद डीपीआर तैयार कर प्रशासनिक स्वीकृति के लिए सरकार को भेजी जाएगी ।  |
| **एलसी-552 पर रेलवे उपरगामी पुल / रेलवे अन्डर ब्रिज**  | बुलवाना से चमेलीवन सड़क | साइट की स्थितियों और प्रतिबंधित राइट ऑफ वे (आरओडब्ल्यू) के कारण इस स्थान पर **रेलवे उपरगामी पुल** / रेलवे अन्डर ब्रिज बनाना संभव नहीं है। |
| **एलसी-556-A स्पेशल पर रेलवे उपरगामी पुल** | बन्चारी से डाकोरा सड़क  | इस स्थान पर **रेलवे उपरगामी पुल** का निर्माण रेलवे अपने स्तर पर कर रहा है। |
| **एलसी-560 स्पेशल पर रेलवे उपरगामी पुल** | मित्रोल से दीघोट सड़क | इस स्थान पर **रेलवे उपरगामी पुल** का निर्माण रेलवे अपने स्तर पर कर रहा है। |
| **एलसी-557-B पर रेलवे उपरगामी पुल** | दिल्ली-मथुरा रोड से ग्राम मरोली तक सड़क | जीएडी को रेलवे द्वारा दिनांक 27.07.2023 को मंजूरी दे दी गई है, डीपीआर तैयार की जा रही है और शीघ्र ही प्रशासनिक अनुमोदन के लिए सरकार को भेजी जाएगी । |
| **एलसी-556 पर रेलवे उपरगामी पुल** | बन्चारी से गोरौटा सड़क | एलसी 556 बन्चारी से गोरौटा रोड पर पड़ता है जो हरियाणा राज्य कृषि विपणन बोर्ड (एचएसएएमबी) के अधिकार क्षेत्र में है और वर्तमान में इस सड़क की एलसी पर **रेलवे उपरगामी पुल** / रेलवे अन्डर ब्रिज के निर्माण का कोई प्रस्ताव नहीं है। |