**To Complete Sanctioned works**

**98 Sh. SUBHASH GANGOLI (Safidon):**

Will the **Development & Panchayats Minister** be pleased to state:-

a) whether there is any proposal under consideration of the Government to complete the works sanctioned under Vidhayak Adarsh Gram Yojana of last year, works sanctioned under CM code 25284 and work of Tyagi/Chamar Chaupal of village Muana sanctioned under the D-plan for which tender has been invited 8 months back in Safidon Assembly Constituency; if so, the details thereof; and

b) whether there is also any proposal under consideration of the Government to complete the work of passages sanctioned under Khet Khaliyan Yojana after inviting the tender in Safidon Assembly Constituency; if so, the time by which the said works are likely to be completed?

**DEVENDER SINGH BABLI, DEVELOPMENT & PANCHAYATS MINISTER, HARYANA**

1. 20 works amounting to Rs.142.67 lacs were sanctioned under Vidhayak Adarsh Nagar Avam Gram Yojana (VANGY) for the last financial year i.e. 2022-23 for Safidon Constituency. Detail about physical progress of all these works is enclosed at **Annexure ‘A’**.

 71 works were sanctioned under CM announcement Code 25284. Details are enclosed at **Annexure ‘B’**.

 Work of Tyagi/Chamar Chaupal of Village Muana was sanctioned under D-Plan Scheme for the financial year 2022-23. Work order has been issued to the agency on 23.12.2022. Reminders to start work have also been issued including the last one on 20.08.2023. If the agency fails to start the work, then it will be debarred & penalised. Likely date of completion of the project is 30.09.2023.

b) 48 works amounting to Rs.447.45 lacs were sanctioned under Khet Khaliyan Yojana. These works will be completed by 31.12.2023 as most of the works will be taken up after crop cutting. Details are enclosed at **Annexure ‘C’**.

**स्वीकृत कार्यों को पूरा करना**

**98 श्री सुभाष गांगोली (सफीदों):**

क्या विकास एवं पंचायत मंत्री कृपया बताएंगे किः-

क) क्या सफीदों विधानसभा निर्वाचन क्षेत्र में गत वर्ष के विधायक आदर्श ग्राम योजना के अंतर्गत स्वीकृत कार्यों, मुख्यमंत्री कोड 25284 के अंतर्गत स्वीकृत कार्यों तथा डी-प्लान के अंतर्गत गांव मवाना की त्यागी/चमार चैपाल के स्वीकृत कार्य जिसके लिए आठ माह पहले निविदा आमंत्रित की जा चुकी है, को पूरा करने का कोई प्रस्ताव सरकार के विचाराधीन है; यदि हां, तो उसका ब्यौरा क्या है; तथा

ख) क्या सफीदों विधानसभा निर्वाचन क्षेत्र में निविदा आमंत्रित करने के बाद खेत खलिहान योजना के अंतर्गत स्वीकृत रास्तों का कार्य पूरा करने का कोई प्रस्ताव सरकार के विचाराधीन है; यदि हां, तो उक्त कार्यों को कब तक पूरा किए जाने की संभावना है?

**देवेन्द्र सिंह बबली, विकास एवं पंचायत मंत्री**, **हरियाणा**

क) सफीदों विधानसभा निर्वाचन क्षेत्र में गत वर्ष के विधायक आदर्श नगर एवं ग्राम योजना (वी.ए.एन.जी.वाई) के अंतर्गत 142.67 लाख रुपये की राशि के 20 कार्य स्वीकृत किए गए थे। इन सभी कार्यों की भौतिक प्रगति का विवरण अनुलग्नक ’ए’ पर संलग्न है।

 मुख्यमंत्री घोषणा कोड 25284 के अंतर्गत 71 कार्य स्वीकृत किए गए थे। विवरण अनुलग्नक ’बी’ पर संलग्न है।

 डी-प्लान योजना के अंतर्गत गांव मवाना की त्यागी/चमार चैपाल का कार्य वित्तीय वर्ष 2022-23 के लिए स्वीकृत किया गया था। एजेंसी को कार्यादेश दिनांक 23.12.2022 को जारी किया गया। कार्य शुरू करने के लिए स्मरण पत्र भी जारी किए गए, जिसमें अतिंम 20.08.2023 भी शामिल हैं। यदि एजेंसी काम शुरू करने में विफल रहती है, तो उसे वंचित व दंडित किया जाएगा। परियोजना पूरा होने की संभावित तिथि 30.09.2023 है।

ख) खेत खलिहान योजना के अंतर्गत 447.45 लाख रुपये की राशि के 48 कार्य स्वीकृत किये गये थे। ये कार्य 31.12.2023 तक पूर्ण हो जायेंगे क्योंकि अधिकांश कार्य फसल कटाई के बाद किये जायेंगे। विवरण अनुलग्नक ’सी’ पर संलग्न है।

|  |
| --- |
| **Status Report of Safidon Constituency Vidhayak Adarsh Nagar Gram Yojana (VANGY) as on 20.08.2023** |
| **Annexure 'A'** |
| **Sr No** | **District** | **Constituency** | **Block** | **Village** | **Name of Work** | **Admin Approval** | **Mode of Execution Tender/ Deptt** | **Target date of completion** | **Status** | **Remarks** |
| **No** | **Date**  | **Amount (In lakh)** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | **11** | **12** | **13** |
| 1 | Jind | Safidon | Safidon | Aftabgarh | Const. of ILPB Street from H/o Joginder S/o Amar Singh to J.D. School | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 9.46 | Tender | 02.02.2024 | In Progress | Work order issued vide Lt. No. HEWP/AL-28484 Dt. 17.07.2023 |
| 2 | Jind | Safidon | Safidon | Rampura | Const. of Saini Choupal | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 9.71 | Tender | 02.02.2024 | In Progress | Work order issued vide Lt. No. HEWP/AL-29011 Dt. 17.07.2023 |
| 3 | Jind | Safidon | Pillukhera | Kalwa | Comp. of Saini Choupal | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 5.53 | Tender | 29.02.2024 | Not Start | Tender opened on Dt. 19.08.2023 & LOA will be issued. |
| 4 | Jind | Safidon | Pillukhera | Kalwa | Comp. of Panchal Choupal | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 5.37 | Tender | 29.02.2024 | Not Start | Tender re-floated & will be received on Dt. 30.08.2023. |
| 5 | Jind | Safidon | Pillukhera | Malshari Khera | Comp. of Brahman Choupal | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 8.42 | Tender | 31.03.2024 | Not Start | Tender opened on Dt. 19.08.2023 & LOA will be issued. |
| 6 | Jind | Safidon | Pillukhera | Gangoli | Comp. of Hall in Dhanak Choupal | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 9.18 | Tender | 31.03.2024 | Not Start | Tender opened on Dt. 19.08.2023 & LOA will be issued. |
| 7 | Jind | Safidon | Pillukhera | Beri Khera | Const. of Hall in Guru Vishavkarma Choupal | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 9.92 | Tender | 31.03.2024 | Not Start | Tender re-floated & will be received on Dt. 30.08.2023. |
| 8 | Jind | Safidon | Pillukhera | Amarawali Khera | Const. of Kumhar Choupal | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 8.90 | Tender | 31.03.2024 | Not Start | Tender re-floated & will be received on Dt. 30.08.2023. |
| 9 | Jind | Safidon | Pillukhera | Dhatrath | Const. of Pandit Choupal in Main Bazar | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 8.99 | Tender | 31.03.2024 | Not Start | Tender opened on Dt. 19.08.2023 & LOA will be issued. |
| 10 | Jind | Safidon | Pillukhera | Bhurain | Comp. Payment of Street with ILPB from Bhurain Jamini Road to Nursery | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 3.42 | Tender | 31.01.2024 | Not Start | Tender opened on Dt. 19.08.2023 & LOA will be issued. |
| 11 | Jind | Safidon | Safidon | Anchra Kalan | Comp. of Balmiki Choupal | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 6.90 | Tender | 10.01.2024 | Not Start | Work order issued vide Lt. No. HEWP/AL-30326 Dt. 12.08.2023 |
| 12 | Jind | Safidon | Safidon | Anta | Comp. of Balmiki Choupal | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 5.00 | Tender | 10.01.2024 | Not Start | Work order issued vide Lt. No. HEWP/AL-30323 Dt. 12.08.2023 |
| 13 | Jind | Safidon | Safidon | Anta | Comp. of Muslim Choupal | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 5.00 | Tender | 10.01.2024 | Not Start | Work order issued vide Lt. No. HEWP/AL-30325 Dt. 12.08.2023 |
| 14 | Jind | Safidon | Safidon | Hatt | Comp. of Malik Choupal | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 7.00 | Tender | 31.03.2024 | Not Start | Estimate prepared on HEWP. Tender to be floated shortly. |
| 15 | Jind | Safidon | Safidon | Hatt | Comp. of Khayali Choupal | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 7.00 | Tender | 10.01.2024 | Not Start | Work order issued vide Lt. No. HEWP/AL-30322 Dt. 12.08.2023 |
| 16 | Jind | Safidon | Safidon | Kharkhana | Const. of Hall in First Floor of Dhanak Choupal | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 6.28 | Tender | 31.03.2024 | Not Start | Estimate prepared on HEWP. Tender to be floated shortly. |
| 17 | Jind | Safidon | Safidon | Kharkhana | Const. of Neem Wali Choupal | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 11.13 | Tender | 31.03.2024 | Not Start | Estimate prepared on HEWP. Tender to be floated shortly. |
| 18 | Jind | Safidon | Safidon | Harigarh | Comp. of Dhanak Choupal | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 3.69 | Tender | 31.01.2023 | Not Start | Tender floated & will be received on Dt. 30.08.2023. |
| 19 | Jind | Safidon | Safidon | Hatt | Re Const. of Street with ILPB and side drain of PWD Safidon road to Banquet Hall | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 1.55 | Tender | 31.12.2023 | Not Start | Estimate prepared on HEWP. Tender to be floated shortly. |
| 20 | Jind | Safidon | Safidon | Kharkhara | Const. of ILPB Street from H/o Joginder Dera to Ramdiya Dera | CEO DRDA JIND Lt. No. 233-35 | 04.05.2023 | 10.22 | Tender | 03.03.2024 | Not Start | Work order issued vide Lt. No. HEWP/AL-20266 Dt. 15.08.2023 |
|   | **Total**  | **142.67** |  |  |  |  |

|  |
| --- |
| **CM Announcement Code 25284 - Safidon Constituency Village wise Report of Jind District** |
| **Annexure 'B'** |
| **S. NO.** | **SCHEME** | **BLOCK** | **VILLAGE** | **NATURE OF WORK** | **SANCTIONED AMOUNT** | **RELEASED AMOUNT** | **Exp.** | **LETTER NO.** | **DATE** | **HAS FUNDS BEEN RECEIVED OR NOT (YES/ NO)** | **LIKELY DATE OF COMPLETION** | **Executing Agency (XEN/GP/PS)** | **STATUS OF WORK** |
| 1 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | ANCHRA KHURD | Const. of General Choupal | 914000 | 914000 | 0.00 | 890 | 06-Mar-21 | Yes | 31.10.2023 | XEN | In progress |
| 2 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | BUTANI | Const. of Hall Room in General Chaupal (Bichwali) | 912000 | 912000 | 0.00 | 1114 | 18-Aug-20 | Yes | 31.10.2023 | XEN | In progress |
| 3 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | GANGOLI | Const. of Chilyan Pana Chopal | 1166000 | 1166000 | 0.00 | 1114 | 18-Aug-20 | Yes | 31.10.2023 | XEN | In progress |
| 4 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | GANGOLI | Const. of street from Randheer master home to PWD road | 468000 | 468000 | 0.00 | 1626 | 07-Apr-21 | Yes | 31.12.2023 | XEN | Not Start not start due to demarcation issues  |
| 5 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | JAMNI | Const. of General Choupal (Brahman) | 842000 | 842000 | 0.00 | 1114 | 18-Aug-20 | Yes | 31.10.2023 | XEN | In progress |
| 6 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | MANDI KHURD | Const. of General Choupal | 835000 | 835000 | 0.00 | 890 | 06-Mar-21 | yes | 31.10.2023 | XEN | In progress |
| 7 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | MOHAMMAD KHERA | Complition of Urlaniya Chopal | 1642000 | 1642000 | 0.00 | 1114 | 18-Aug-20 | yes | 31.12.2023 | XEN | In progress |
| 8 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | RATTA KHERA | Const. of Panchal Chaupal | 500000 | 500000 | 0.00 | 1114 | 18-Aug-20 | Yes | 31.10.2023 | XEN | In progress |
| 9 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | RITOLI | Const. of General Choupal | 835000 | 835000 | 0.00 | 890 | 06-Mar-21 | Yes | 31.10.2023 | XEN | In progress |
| 10 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | ROJHLA | Const. of Balmiki Choupal | 448000 | 448000 | 0.00 | 888 | 06-Mar-21 | Yes | 31.10.2023 | XEN | In progress |
| 11 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | Rod | Comp. of Balmiki Choupal | 385000 | 385000 | 0.00 | - | - | YES | 02.02.2024 | XEN | In progress |
| 12 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | Dhatrath | Comp. of Dr. Bhim Rao Ambedkar Bhawan | 787000 | 787000 | 0.00 | - | - | YES | 31.10.2023 | XEN | In progress |
| 13 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | Nimnabad | Comp. of Ravidash Choupal | 447000 | 447000 | 0.00 | - | - | YES | 31.12.2023 | XEN | Tender Re-floated & will be received on Dt. 30.08.2023 |
| 14 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | Muana | Const. of Sirsali Choupal | 1024000 | 1024000 | 0.00 | - | - | YES | 28.02.2024 | XEN | Tender Re-floated & will be received on Dt. 30.08.2023 |
| 15 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | Singhana | Comp. of Kashyap Choupal | 1754000 | 1754000 | 0.00 | - | - | YES | 31.03.2024 | XEN | In progress |
| 16 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | Kalwa | Comp. of Slaper Pana (Gen) Choupal | 824000 | 824000 | 0.00 | - | - | YES | 31.12.2023 | XEN | Tender Re-floated & will be received on Dt. 30.08.2023 |
|  |  |  |  | **Total**  | **13783000** | **13783000** | **0** |  |  |  |  |  |  |
| 1 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | AHLANJOGI KHERA | Const of B/Wall of playground | 350000 | 350000 | 350000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 2 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | BAGRU KALAN | Completion of General Chaupal (Bichwali) | 666000 | 666000 | 666000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 3 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | BAGRU KHURD | Const. of waste water Nala Govt. School to Siwanamal Road | 391000 | 391000 | 391000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 4 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | BAGRU KHURD | Const. of ILPB Street H/o Mukhtyara S/o Pyare Lal to Reghbir S/o Hari Ram | 426000 | 426000 | 426000 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
| 5 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | BASINI | Const. Of ILPB Street in front of Ramphal & Reghubir House | 598000 | 598000 | 598000 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
| 6 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | BHAMBHEWA | Const. of B/Wall of Ghangas Bhawan | 794000 | 794000 | 794000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 7 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | BHIRTANA | Const. of street with ILPB from PWD Road to H/o shamsher S/o Ram Swaroop | 235000 | 235000 | 235000 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
| 8 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | BHURAIN | Complition of Brahman Chopal | 1330000 | 1330000 | 1330000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 9 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | BHUSLANA | Const. of Harijan Chaupal | 589000 | 589000 | 589000 | 1115 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 10 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | BHUSLANA | Const. of Balmiki Chaupal | 835000 | 835000 | 835000 | 1115 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 11 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | DHAROLI | Const. B.C Choupal | 835000 | 835000 | 835000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 12 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | DHATHRATH | B/wall of Community Centre | 581000 | 581000 | 581000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 13 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | DHATHRATH | Const of Hall in Ambedkar Bhawan near Mahila Mandal | 865000 | 865000 | 865000 | 1115 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 14 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | GANGOLI | Const. of Paver Block Street from H/o Rammehar S/o Bhagwana to shop of Dharampal S/o Mansa | 1481000 | 1481000 | 1481000 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
| 15 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | GANGOLI | Const. of Street From Rammehar S/o Bhagwana | 807000 | 807000 | 807000 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
| 16 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | GANGOLI | Const. of street with ILPB from PWD Road to waste water Drain | 989000 | 989000 | 989000 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
| 17 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | GANGOLI | Const. of street from Subhash Foji home to Sarif Doom home | 850000 | 850000 | 850000 | 1626 | 07-Apr-21 | Yes | \_ | GP | Complete  |
| 18 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | HADWA | Const of R/Wall with cow Ghat at on Bhag Khera Road | 1510000 | 1510000 | 1510000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 19 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | HATT | Compl. Of Dr. Ambedkar Bhawan | 826000 | 826000 | 826000 | 1115 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 20 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | HATT | Compl. of Gen. Chaupal ( Malik Panna ) | 740000 | 740000 | 740000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 21 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | HATT | Const. of Hall Room General Chaupal (Khyali Panna) | 965000 | 965000 | 965000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 22 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | HATT | Pavement of Rasta Ramnagar Road to Ram Kumar S/o Pirthi | 178000 | 178000 | 178000 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
| 23 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | HOSHIARPURA | Compl. Of Balmiki Chaupal | 286000 | 286000 | 286000 | 1115 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 24 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | JAIPUR | Const. of ILPB Street from Patwarkhana to Pir Baba Shyad (Firni)) | 923000 | 923000 | 923000 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
| 25 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | KALWA | Const of Saleper Pana Choupal | 835000 | 835000 | 835000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 26 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | KALWA | Complition of SC Choupal | 358000 | 358000 | 358000 | 1115 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 27 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | KALWA | Const of Rasta With Brick on edge from PWD road to Satyawan Hechery | 924000 | 924000 | 924000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 28 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | KHARAK GAGAR | Const of R/Wall with cow Ghat at ghagar wala pond | 893000 | 893000 | 893000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 29 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | LUDANA | Complition of Manbhar Pana Choupal | 644000 | 644000 | 644000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 30 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | MALIKPUR | Const. of ILPB Street PWD Road to Mohinder S/o Uttam Singh | 963300 | 963300 | 963300 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
| 31 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | MORKHI | Complition of SC Choupal | 835000 | 835000 | 835000 | 1115 | 18-Aug-20 | yes | \_ | GP | Complete  |
| 32 | HARYANA GRAMIN VIKAS YOJANA | PILLUKHERA | MORKHI | Const of Rasta With Brick on edge from PWD road to Mishan Hechery | 1470000 | 1470000 | 1470000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 33 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | MUANA | Completion of Odd Chaupal | 494000 | 494000 | 494000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 34 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | MUANA | Completion of Gen. Chaupal (Moh Patti) | 591000 | 591000 | 591000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 35 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | MUANA | Compl. Of General Chaupal Thoh Pana | 578000 | 578000 | 578000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 36 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | MUANA | Completion of Gen. Chaupal (Rohat Patti) | 517000 | 517000 | 517000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 37 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | MUANA | Const. of Ambdekar Bhawan | 994000 | 994000 | 994000 | 1115 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 38 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | PAJU KALAN | Const. of ILPB Street from Satpal S/o Jaimal to Sr. Sec. School | 847000 | 847000 | 847000 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
| 39 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | PAJU KHURD | const. of street from PWD road to Shamsher s/o Beliram home | 248000 | 248000 | 248000 | 1626 | 07-Apr-21 | Yes | \_ | GP | Complete  |
| 40 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | PAJU KHURD | Const. of street from Firni to Rajbir s/o Shri Karma home to Ram Kishan home | 777000 | 777000 | 777000 | 1626 | 07-Apr-21 | Yes | \_ | GP | Complete  |
| 41 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | RAMPURA | Const. of ILPB Street PWD Road to Rajeshwar | 593700 | 593700 | 593700 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
| 42 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | RATTA KHERA | Const. of Ambdekar Bhawan | 958000 | 958000 | 958000 | 1115 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 43 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | ROJHLA | Const. of ILPB Street from Karan Singh Nehra to Joginder Singh | 287000 | 287000 | 287000 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
| 44 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | ROJHLA | Const. of ILPB Street PWD Road to Karan Singh Saini | 142000 | 142000 | 142000 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
| 45 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | SARFABAD | Const. of R/wall of Pond | 224000 | 224000 | 224000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 46 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | SARFABAD | Const. of Ambedkar Bhawan | 957000 | 957000 | 957000 | 1115 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 47 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | SARFABAD | Pavement of Street with Dry Bricks on edge paying PWD Road Anchra alongwith drain to Shamshanghat | 243000 | 243000 | 243000 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
| 48 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | SILLA KHERI | Const. of ILPB Street Ramphal to Lokesh S/o Shiv Kumar | 719000 | 719000 | 719000 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
| 49 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | SINGHANA | Compl. of Brahman Chaupal | 700000 | 700000 | 700000 | 1114 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 50 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | SINGHPURA | Const. of ILPB Street in BPL Colony near Godam | 614600 | 614600 | 614600 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
| 51 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | SINGHPURA | Const. Of ILPB Street from Ramphal S/o Soran to Ishwar Singh Gulia | 138500 | 138500 | 138500 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
| 52 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | SIWANAMAL URF NAYA GAON | Completion of Harijan Chaupal | 481000 | 481000 | 481000 | 1115 | 18-Aug-20 | Yes | \_ | GP | Complete  |
| 53 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | SIWANAMAL URF NAYA GAON | Const. Of ILPB Street to Rodo wala Dera | 967000 | 967000 | 967000 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
| 54 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | SIWANAMAL URF NAYA GAON | Pavement of Street with Dry Bricks on edge PWD Road Bagru to Brahman wali Gali | 251000 | 251000 | 251000 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
| 55 | HARYANA GRAMIN VIKAS YOJANA | SAFIDON | SIWANAMAL URF NAYA GAON | Const. Of ILPB Street in Govt. School | 514000 | 514000 | 514000 | 2107 | 04-Dec-20 | Yes | \_ | GP | Complete  |
|   |   |   |  | **Total**  | **37808100** | **37808100** | **37808100** |  |   |   |   |   |   |
|   |   |   |  | **G. Total**  | **51591100** | **51591100** | **37808100** |  |   |   |   |   |   |

|  |
| --- |
| **Status Report of Safidon Constituency MMKKKSY as on 20.08.2023** |
| **Annexure 'C'** |
| **S. No.** | **Constituency** | **Block**  | **Village** | **Name of Work** | **Admn. Approval** | **Mode of Execution Tender/ Dept.** | **Likely date of completion** | **Status** | **Remarks (full reason WIP or WNS)** |
| **No.** | **Date** | **Amount(In lakh)** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | **11** | **12** |
| 1 | Safidon | Pillukhera | Gangoli | Pav. Of Rasta with Dry bricks on edge from Bhirtana Minor F/o Ramehwar S/o Ram Kisan to F/o Bheera S/o Deiya | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 23.75 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 30.08.2023 |
| 2 | Safidon | Pillukhera | Gangoli | Pav. Of Rasta with Dry Bricks on edge 12 from Kalwa road F/o Jora Singh S/o Maha Singh to F/o Karampal Shastri | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 2.38 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 30.08.2023 |
| 3 | Safidon | Safidon | Paju Kalan | Const. of Rasta with Dry Brick on Edge from Khet of Jaspal master to Khet of Ballbir S/o Gyani Ram | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 11.81 | Tender | 31.12.2023 | Not Start | Estimate under prepration on HEWP. Tender to be floated shortly.(Site Dispute) |
| 4 | Safidon | Safidon | Nimnabad | Const; of Rasta With Dry Brick from PWD road Malikpur (Khet of Azad Singh s/o Joga Singh to Khet of Gurumukh S/o Tal Singh | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 5.24 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 30.08.2023 |
| 5 | Safidon | Safidon | Malikpur | Const. of Pav. Of Rasta from Depadi roda to Malak Singh S/o Harbhaj Singh Field | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 3.69 | Tender | 31.12.2023 | Not Start | Tender eceived on Dt. 18.08.2023 & technically under process. |
| 6 | Safidon | Safidon | Nimnabad | Rasta from Dera of Jarnal S/o Bakhta Singh to Dera of Balkar Singh S/o Kapoor Singh | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 11.71 | Tender | 31.12.2023 | Not Start | Tender eceived on Dt. 18.08.2023 & technically under process. |
| 7 | Safidon | Safidon | Anta | Rasta form PWD road Gohana to Khet of Rajinder Mann S/o Chattar Singh to Khet of Gurcharan S/o Jagir Signh | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 13.18 | Tender | 31.12.2023 | Not Start | Tender eceived on Dt. 18.08.2023 & technically under process. |
| 8 | Safidon | Safidon | Anta | Anta Rasta from PWD Panipat (Pull of India Drain Left Side Bank) to Dera of Pardeep Deswal S/o Surender Deswal | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 11.34 | Tender | 31.12.2023 | Not Start | Tender eceived on Dt. 18.08.2023 & technically under process. |
| 9 | Safidon | Safidon | Muana | Rasta from of Suresh S/o Jagdish (PWD Road Budha Khera to H/o Balwan S/o Badlu | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 4.30 | Tender | 31.12.2023 | Not Start | Tender eceived on Dt. 18.08.2023 & technically under process. |
| 10 | Safidon | Pillukhera | Hadwa | Pav. Of Rasta with dry bricks on edge from Dera Talab to Satnarayan S/o Ram Sanehi | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 7.36 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 19.08.2023. |
| 11 | Safidon | Pillukhera | Dhatrath | Pav. Of Rasta with dry bricks on edge from Dhatrath Alewa road to f/o Binder S/o Balbir | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 4.90 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 19.08.2023. |
| 12 | Safidon | Pillukhera | Kalwa | Pav. Of Rasta with Dry Bricks on edge from Dharoli road F/o Satnarayan s/o Deep Chand to F/o Prem Singh S/o Surjeet | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 17.42 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 19.08.2023. |
| 13 | Safidon | Pillukhera | Dhatrath | Pav. Of Rasta with Dry bricks on edge from Jamni rasta to F/o Hawa Singh S/o Phule Singh | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 2.68 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 19.08.2023. |
| 14 | Safidon | Pillukhera | Dharoli | Pav. Of Rasta with Dry Bricks on edge from Dharoli Kalwa road F/o Raja S/o Tek Ram to F/o Hawa Singh S/o Desraj | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 6.70 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 24.08.2023. |
| 15 | Safidon | Pillukhera | Dharoli | Pav. Of Rasta with dry bricks on edge from Dharoli Bhirtana road F/o Prithivi S/o Devak Ram to F/o Balbir S/o Pyare Lala | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 5.56 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 24.08.2023. |
| 16 | Safidon | Pillukhera | Kalwa | Pav. Of Rasta with Dry bricks on edge from Pillukhera road F/o Ramdhri S/o Saria to F/o Zile Singh S/o Rangi Ram | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 7.37 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 24.08.2023. |
| 17 | Safidon | Pillukhera | Dharoli | Pav. Of Rasta with Dry bricks on edge from kalwan road to Mandir | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 2.50 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 24.08.2023. |
| 18 | Safidon | Pillukhera | Kharak Gagar | Pav. Of Rasta with Dry bricks on edge from Kharak Gagar Hadwa road to F/o Bijender S/o Randhir | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 4.98 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 24.08.2023. |
| 19 | Safidon | Pillukhera | Dharoli | Pav. Of Rasta with Dry bricks on edge from Dharoli Bhirtana road F/o Surender S/o Bhikha Ram to Chabri Minor | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 9.85 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 24.08.2023. |
| 20 | Safidon | Pillukhera | Kalawati | Pav. Of Rasta with dry bricks on edge from Kalawati Hosiyarpura road F/o Kaptan S/o Ujala to F/o Om Parkash S/o Baba Mangal Dass | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 15.33 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 24.08.2023. |
| 21 | Safidon | Pillukhera | Bhag Khera | Pavment of Rasta of Dry Brick on Edge From PWD Bagru Road to F/o Girdhari S/o Lichman | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 4.01 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 24.08.2023. |
| 22 | Safidon | Safidon | Rodh | Const. of Pav. Of Rasta PWD road Asandh to Jagir S/o Bhana Singh Dera | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 2.65 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 30.08.2023 |
| 23 | Safidon | Safidon | Malikpur | Const. of Pav. Of Rasta from Pardhan wali Sadak to Dera Sarabjit S/o Joginder Singh | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 1.56 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 30.08.2023 |
| 24 | Safidon | Safidon | Muana | Const. of Pav. of Rasta with dry brick on edge from PWD road Bahri Khera to Arya Samaj Sanstha | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 9.77 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 30.08.2023 |
| 25 | Safidon | Safidon | Bagru Khurd | Const. of Pav. Of Rasta with Dry Brick on Edge from PWD Road Sarfabad H/o Naresh to Dalbir | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 4.15 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 30.08.2023 |
| 26 | Safidon | Safidon | Bagru Khurd | Const; of Pav. Of Rasta with Dry Brick on Edge from PWD road Sarfabad to F/o Ishwar S/o Kanshi Ram | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 3.16 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 30.08.2023 |
| 27 | Safidon | Safidon | Bagru Khurd | Const. of Pav. Of rasta with Dry Brick on edge from Morkhi wala rasta via Pandit Ram Singh to F/o Manish S/o Sajan Singh | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 9.48 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 30.08.2023 |
| 28 | Safidon | Safidon | Sarna Khera | Const. of Pav. Of Rasta with Dry Brick on Edge from Shamshan Ghat to Ramphal Ex. Sarpanch | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 14.33 | Tender | 31.12.2023 | Not Start | Tender floated & will be received on Dt. 30.08.2023 |
| 29 | Safidon | Pillukhera | Baniya Khera | Pav. Of Rasta with Dry bricks on edge from Baniya Khera Kharak Gadiya roda to F/o Mahender S/o Ganga Ram | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 22.04 | Tender | 31.12.2023 | Not Start | Tender re-floated & will be received on Dt. 27.08.2023. |
| 30 | Safidon | Safidon | Ram Nagar | Rasta From Vet. Hospital to Up Ward Khet of Naresh S/o Ratan Singh | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 17.73 | Tender | 31.12.2023 | Not Start | Tender re-floated & will be received on Dt. 27.08.2023. |
| 31 | Safidon | Safidon | Ram Nagar | Rasta from Bitani road to Khet of Amit S/o Pal Singh | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 7.12 | Tender | 31.12.2023 | Not Start | Tender re-floated & will be received on Dt. 27.08.2023. |
| 32 | Safidon | Safidon | Siwanamal | Rasta from Bhag Khera Khet of Rajesh S/o Mangeram to Upward Siwanamal Minor | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 23.38 | Tender | 31.12.2023 | Not Start | Tender re-floated & will be received on Dt. 27.08.2023. |
| 33 | Safidon | Safidon | Barod | Const. of Pavment of Rasta with dry brick on edge from Minor to Sahab Singh S/oRamdhari Malik | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 4.98 | Tender | 31.12.2023 | Not Start | Work order issued vide Lt. HEWP/AL-30378 Dt. 15.08.2023. |
| 34 | Safidon | Safidon | Malikpur | Const. of Pav. Of rasta from Malakpur ashand roda to Korse Singh S/o Kulwant Singh Dera | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 7.59 | Tender | 31.12.2023 | Not Start | Work order issued vide Lt. HEWP/AL-30783 Dt. 15.08.2023. |
| 35 | Safidon | Safidon | Malar | Const. of Pav. Of Rasta with Dry brick on edge from PWD Road Budha Khera Malar to Dera Bhaiya Ram | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 4.90 | Tender | 31.12.2023 | Not Start | Work order issued vide Lt. HEWP/AL-30795 Dt. 15.08.2023. |
| 36 | Safidon | Safidon | Karsindhu | Const. of Pav. Of Rasta with Dry brick on edge from Kuldeep S/o Beera to Mahender S/o Harichand | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 2.21 | Tender | 31.12.2023 | Not Start | Work order issued vide Lt. HEWP/AL-30862 Dt. 15.08.2023. |
| 37 | Safidon | Safidon | Muana | Pavment of Street with Dry Brick on Edge Jimari Khera Wala Rasta Subhash S/o Jogi Ram to Krishan S/o Roop Singh | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 20.33 | Tender | 31.12.2023 | Not Start | Work order issued vide Lt. HEWP/AL-30868 Dt. 15.08.2023. |
| 38 | Safidon | Safidon | Muana | Const. of Pav. Of Rasta with Dry brick on Edge from PWd road Koul Khera to Ramphal S/o Hukam Singh | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 13.06 | Tender | 31.12.2023 | Not Start | Work order issued vide Lt. HEWP/AL-30871 Dt. 15.08.2023. |
| 39 | Safidon | Pillukhera | Mandi Khurd | Pav. Of Rasta with Dry bricks on edge from main Firni to f/o Suresh s/o Bhale Ram | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 9.95 | Tender | 31.12.2023 | Not Start | Work order issued vide Lt. No. HEWP/AL-30506 Dt. 08.08.2023 |
| 40 | Safidon | Pillukhera | Mandi Khurd | Pav. Of Rasta with dry bricks on edge from Hasanpur road H/o Karambir S/o Molad to F/o Suresh S/o Bhale Ram | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 16.35 | Tender | 31.12.2023 | Not Start | Work order issued vide Lt. No. HEWP/AL-30512 Dt. 08.08.2023 |
| 41 | Safidon | Safidon | Rodh | Const. of Pav. Of Rasta from Ardhana to Road Jasbir S/o Gyan Singh Dera | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 4.73 | Tender | 31.12.2023 | Not Start | Work order issued vide Lt. No. HEWP/AL-30733 Dt. 12.08.2023 |
| 42 | Safidon | Safidon | Bahadurpur | Const. of Pav. Of rasta with dry brick on edge from Kalar Khera Sadak to Buljora and Lilu S/o Ramchander Field | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 3.98 | Tender | 31.12.2023 | Not Start | Work order issued vide Lt. No. HEWP/AL-30746 Dt. 12.08.2023 |
| 43 | Safidon | Safidon | Singhpura | Const. of Pav. Of Rasta with dry brick on edge from Dairy farm to Satnarayan farm & Dera of suresh Halwai | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 9.44 | Tender | 31.12.2023 | Not Start | Work order issued vide Lt. No. HEWP/AL-30752 Dt. 12.08.2023 |
| 44 | Safidon | Safidon | Ratta Khera | Const. of Pav. Of Rasta with dry brick on edge from Pandit Tika Ram Field to Sh. Azad Layer farm | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 10.06 | Tender | 31.12.2023 | Not Start | Work order issued vide Lt. No. HEWP/AL-30759 Dt. 12.08.2023 |
| 45 | Safidon | Safidon | Malikpur | Const. of Pav; of Rasta from Dharamgarh road to Via Satnam Singh S/o Darshan Dera to Nishan Singh Field  | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 22.06 | Tender | 31.12.2023 | Not Start | Work order issued vide Lt. No. HEWP/AL-30801 Dt. 12.08.2023 |
| 46 | Safidon | Safidon | Bahadurgarh | Const. of Pav. Of Rasta with Dry Brick on Edge from PWD Rod Jind Safidon to F/o Hukam Singh | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 7.95 | Tender | 31.12.2023 | Not Start | Work order issued vide Lt. No. HEWP/AL-30874 Dt. 12.08.2023 |
| 47 | Safidon | Pillukhera | Dhatrath | Pav. Of Rasta with Dry bricks on edge from baniya Krasta to F/o Subha S/o Abhay Ram | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 9.83 | Tender | 31.12.2023 | Not Start | Work order issued vide Lt. No. HEWP/AL-31769 Dt. 08.08.2023 |
| 48 | Safidon | Pillukhera | Dhatrath | Pav. Of Rasta with dry bricks on edge from Dhatrath Alewa road to F/o Parveen S/o Randhir | Endst. No. 392-BAP-II-(9)-2023/1873 | 15.06.2023 | 8.60 | Tender | 31.12.2023 | Not Start | Work order issued vide Lt. No. HEWP/AL-32042 Dt. 08.08.2023 |
|  |  |  |  |  |  |  | **447.45** |  |  |  |  |