Sewerage Line Under AMRUT Yojana

5	Smt. SEEMA TRIKHA (Badkhal):

Will the Urban Local Bodies Minister be pleased to state:-

a) whether the work of sewerage line under the AMRUT Yojana has been functional in the following areas:-

i) village Badkhal;

ii) village Ankhir;

iii) SGM city P Block;

iv) SGM city F and G Block;

v) village Bhankari;

vi) village Navada; and

b) if not, the reasons thereof togetherwith the time by which it is likely to be made functional?

Dr. Kamal Gupta, Urban Local Bodies Minister, Haryana

Sir,

a) The details regarding functioning of sewer lines under the AMRUT 1.0 Yojana in the following areas are as under:

- Village Badkhal - No

- Village Ankhir - Yes, Partially

- SGM city P Block – No Sewerage line laid under AMRUT 1.0 Yojana

- SGM city F and G Block - No Sewerage line laid under AMRUT 1.0 Yojana

- Village Bhankari - No

- Village Navada – No Sewerage line laid under AMRUT 1.0 Yojana

b) The area wise details are as under:

i) Village Badkhal - A nallah of width 1.5 metres is coming in the alignment of the sewer pipeline which is obstructing the interlinking of the lateral sewer lines to the main sewer lines. The work is expected to be completed by 15.06.2024.

ii) 	Village Ankhir - Some rocky strata has been found during the laying of sewer line in a part of the village due to which this work is getting delayed. The work is expected to be completed by 30.05.2024.

iii) 	SGM city P Block - The streets of SGM city P block are narrow and sewer line already exists in this area. Due to this reason, new sewer lines are not laid under AMRUT 1.0.

iv) 	SGM city F and G Block - The streets of SGM city F and G blocks are narrow and sewer line already exists in this area. Due to this reason, new sewer lines are not laid under AMRUT 1.0.

v) 	Village Bhankari -Some rocky strata has been found during the laying of sewer line in a part of the village due to which this work is getting delayed. The work is expected to be completed by 30.06.2024.

vi) 	Village Navada – There is no provision to lay the sewer line in Navada village under AMRUT 1.0 Yojana.

ve:r ;kstuk ds varxZr lhojst ykbu

5	Jherh lhek f=[kk ¼cM+[ky½%

D;k “kgjh LFkkuh; fudk; ea=h d`i;k crk,axs fd%&

d½ D;k fuEufyf[kr {ks=ksa esa ve:r ;kstuk ds varxZr lhojst ykbu dk dk;Z fØ;k”khy dj fn;k x;k gS%&

1½ xkao cM+[ky(

ii½ xkao vu[khj(

iii½ ,l-th-,e- flVh ih CykWd(

iv½ ,l-th-,e- flVh ,Q vkSj th CykWd(

v½ xkao Hkkadjh(

vi½ xkao uoknk ( rFkk

[k½ ;fn ugha] rks blds dkj.k D;k gSa rFkk blds dc rd fØ;k”khy gksus dh laHkkouk gS\

Mk0 dey xqIrk] “kgjh LFkkuh; fudk; ea=h] gfj;k.kk

Jheku th]

d) ve`r 1-0 ;kstuk ds rgr lhoj ykbuksa dh fØ;k”khyrk dk {ks=kuqlkj fooj.k bl izdkj gS %

- xkao cM+[ky & ugha

- xkao vu[khj & gka] vkaf”kd :Ik ls

- ,l-th-,e- flVh ih CykWd & ve`r 1-0 ;kstuk ds rgr dksbZ lhojst ykbu ugha fcNkbZ xbZ A

- ,l-th-,e- flVh ,Q vkSj th CykWd & ve`r 1-0 ;kstuk ds rgr dksbZ lhojst ykbu ugha fcNkbZ xbZ A

- xkao Hkkadjh & ugha

- xkao uoknk & ve`r 1-0 ;kstuk ds rgr dksbZ lhojst ykbu ugha fcNkbZ xbZ A

[k) {ks=kuqlkj fooj.k bl izdkj gS%

- xkao cM+[ky & lhoj ikbi ykbu ds ekxZ esa 1-5 ehVj pkSM+k ,d ukyk vk jgk gS tks ihNs ls vk jgh lhoj ykbuksa dks eq[; lhoj ykbuksa ls tksM+us esa ck/kk mRiUu dj jgk gSA dk;Z 15-06-2024 rd iw.kZ gksus dh laHkkouk gSA

- xkao vu[khj & xkao ds ,d fgLls esa lhoj ykbu fcNkus ds nkSjku dqN pV~Vkuh ijrsa ikbZ xbZ gS] ftlds dkj.k dk;Z esa nsjh gks jgh gSA dk;Z                  30-05-2024 rd iw.kZ gksus dh laHkkouk gSA

- ,l-th-,e- flVh ih CykWd &,l-th-,e- flVh ih CykWd dh lM+dsa rax gSa rFkk bl bykds esa lhoj ykbu igys ls gh ekStwn gSA bl otg ls               ve`r 1-0 ds rgr ubZ lhoj ykbusa ugha fcNkbZ xbZ gSa A

- ,l-th-,e- flVh ,Q vkSj th CykWd & ,l-th-,e- flVh ,Q vkSj th CykWd dh lM+dsa rax gSa rFkk bl bykds esa lhoj ykbu igys ls gh ekStwn gSaA bl otg ls ve`r 1-0 ds rgr ubZ lhoj ykbusa ugha fcNkbZ xbZ gSa A

- xkao Hkkadjh & xkao ds ,d fgLls esa lhoj ykbu fcNkus ds nkSjku dqN pV~Vkuh ijrsa ikbZ xbZ gS] ftlds dkj.k dk;Z esa nsjh gks jgh gSA dk;Z                30-06-2024 rd iw.kZ gksus dh laHkkouk gSA

- xkao uoknk & xkao uoknk esa ve`r 1-0 ;kstuk ds rgr lhoj ykbu fcNkus dk dksbZ izko/kku ugha gSA